## GCP Procs
ENA Energy Operations
Global Counterparty
Y2K Preparations and Test Plan
| December | [6 empty] | January
| S | M | T | W | T | F | S | S | M | T | W | T | F | S
1
|  |  |  | 1 | 2 | 3 | 4 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| 5 | 6 | 7 | 8 | 9 | 10 | 11 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 12 | 13 | 14 | 15 | 16 | 17 | 18 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| 19 | 20 | 21 | 22 | 23 | 24 | 25 | 23 | 24 | 25 | 26 | 27 | 28 | 29
| 26 | 27 | 28 | 29 | 30 | 31 |  | 2: 30; 3: 31
I. | Critical Processes
| A. | Set up new counterparties
| B. | Update counterparty payment ( invoice ) information
| C. | Process Name Changes
| D. | Process Mergers, Acquisitions
| E. | Request Dun & Bradstreet information
II. | Critical Dates
| A. | Month end - December 31
| B. | First week of month - January 1 - January 7
III. | Dependencies
| A. | Trade Capture/Confirmation - Selection of counterparty
| B. | Settlements - payment advice
| C. | Logistics - DUNs number for EDI nominations
IV. | Preparations
A. Run Hardcopy Reports
|  | I. | 12/28/1999 |  |  | Print Merger/Name Change List
|  | ii. | 12/30/1999 |  |  | Print Active Counterparty List - Alphabetical
|  | iii. | 12/30/1999 |  |  | Print Inactive Counterparty List - Alphabetical
| B. | Test Online Connection from home - 12/27/99
|  | I. | Global Counterparty application
|  | ii. | Excel
|  | iii. | Dun & Bradstreet
|  | iv. | E Mail
|  | v. | Lotus Notes Database
| C. | Confirm Y2K test plans with dependent parties - 12/27/99
V. | Equipment/Supplies required for Disaster Scenario
| A. | One Fax Machine
| B. | Telephone - voice line
| C. | Telephone - data line for D&B communication
| D. | Laptop with modem
| E. | Manual Deal Ticket process for trade capture
| F. | General office supplies
VI. | Y2K Global Counterparty Contacts
|  | Jason Moore |  |  |  | X3-3198 |  | 2: (713) 681-2038; 7: (713) 788-9458
|  | Samuel Schott |  |  |  | X3-9890 |  | 2: (713) 721-5714; 7: (713) 788-9458 | backup
VII. | Test Plans for 1/1/2000
| A. | Execute tasks as outlined on GCP Test template using inputs from other areas
such as Deal Validation and Credit
| B. | Capture screen print of all entries and verification of integrated systems
| C. | Test online connection from home on 1/1/00

## GCP Test
Global Counterparty 1/1/2000 Test /Plan
| Procedure | System | Expected Result | Contingency Plan | Date/Time | Responsible Person
| Set up New Counterparty | Global Counterparty | Using name of 'Early Y2K Dummy', process new setup utilizing address roles/legacy groups for all products - Phys Gas, Phys Power, Financial, and Liquids. Include a contact name setup as well. Duns link id should be assigned with no errors. London should use 'Early Y2KL Dummy'. Use valid bank so that record will not be rejected from SAP. COE team to provide bank. | This record is to support testing of name changes etc on 1/1/00 | 1999-12-30 | Jason Moore
| Set up New Counterparty | Global Counterparty | Using name of 'Y2K Dummy', process new setup utilizing address roles/legacy groups for all products - Phys Gas, Phys Power, Financial, and Liquids include a contact name setup as well. Duns link id should be assigned with no errors. LONDON should use 'Y2KL Dummy'. Put Fax number for Power on 30 in as Power settlement contact to support test of autofax. The number is 713-646-4061. Use valid bank so that record will not be rejected from SAP. COE team to provide bank. | Track requests for new CP setups for later input. | 1/1/00 9:30am | Jason Moore
CALL SAP/COE TEAM TO PROCESS CHANGE
AFTER SETUP IS COMPLETE, KIM THERIOT (x3-1771) and NOTIFY CONTRACTS
CALL DBA ON-CALL @ 888-993-3793 or SECONDARY DBA ON-CALL @ 888-993-3795 for REFRESH
| Set up New Counterparty | TAGG | After view refresh, verify cp exists in TAGG drop downs (DBA: refresh snapshot on ERMS GCP_Group) | If new CPs do not flow to TAGG, then RISK and Deal Validation must have a contingency plan for capturing and confirming these trades. | 1/1/00 10:00am | Will Kelly
| Set up New Counterparty | ERMS | After view refresh, verify cp exists in ERMS (DBA: refresh snapshot on ERMS GCP_Group) | If new CPs do not flow to ERMS, then RISK must have a contingency plan for valuing these trades. | 1/1/00 10:00am | Will Kelly
| Set up New Counterparty | SITARA | After server bounce, verify cp exists in Sitara drop downs | If new CPs do not flow to Sitara, then RISK and Deal Validation must have a contingency plan for capturing and confirming these trades. | 1/1/00 10:00am | Will Kelly
| Set up New Counterparty | SOLARC | After view refresh, verify cp exists in SOLARC drop downs | If new CPs do not flow to Solarc, then RISK must have a contingency plan for capturing and confirming these trades. | 1/1/00 10:00am | Cindy Horn
| Set up New Counterparty | Unify | Verify cp exists in Unify | If new CPs do not flow to Unify, then Settlements and Logistics must have a contingency plan for settling and scheduling these trades. | 1/1/00 10:00am | Jason Moore
| Set up New Counterparty | SIFT | After view refresh, verify cp exists in SIFT | If new CPs do not flow to SIFT, then Settlements must have a contingency plan for settling these trades. | 1/1/00 10:00am | Becky Ford
| Set up New Counterparty | SAP | Verify CP is on bridge transfer to SAP (DBA: refresh SAP_GROUP after Xref server is refreshed on SAP side) | If new CPs do not flow to SAP, then Enron-Europe must have a contingency plan for adding customers and vendors directly to SAP. | 1/1/00 10:00am | Marilyn Colbert / SUNDAR
| Set up New Counterparty | POPs | After refresh (5 mins), verify cp is in POPs | If new CPs do not flow to POPs, then Texas Logistics must have a contingency plan for scheduling these trades. | 1/1/00 10:00am | Mary Smith
| Set up New Counterparty | Enpower | After view refresh, verify new cp appears in Enpower drop downs. (DBA:refresh from Enpower) | If new CPs do not flow to Enpower, then RISK and Deal Compliance must have a contingency plan for capturing and confirming these trades. | 1/1/00 10:00am | Kim Theriot
| Set up New Counterparty | DCAF2 | After view refresh, verify new cp appears in drop downs. (DBA: refresh GCP_GROUP) | If new CPs do not flow to DCAF2, then Deal Compliance must have a contingency plan for confirming these trades. | 1/1/00 10:00am | Jeff Sorenson
| Set up New Counterparty | Global Credit | After view refresh, verify new cp appears in Global Credit. (DBA: run bridge job) | If new CPs do not flow to Global Credit, then RAC must have a contingency plan for capturing exposure related to these parties. | 1/1/00 10:00am | Debbie Brackett
ALL Users : Contact Jason Moore to indicate results of test
After all groups have tested a deal all the way through, process the next step. Check with Risk and Settlements to see when they are finished.
| Process Name Change | Global Counterparty | Change name of 'Early Y2K Dummy' to 'Y2K DummyA'. There should be no errors on update. Party is searchable by new or old (formerly) name. | No name changes will be processed until system errors are corrected. | 1/1/2000 10:00am | Marilyn Colbert
CALL DBA ON-CALL @ 888-993-3793 or SECONDARY DBA ON-CALL @ 888-993-3795 for REFRESH
| Process Name Change | Sitara | After server is bounced, the new name is reflected on existing deals and is available for selection. | Any deals will reflect old name. | 2000-01-01 | Will Kelly
| Process Name Change | Unify | Verify CP new name is reflected in drop downs and invoices. | Invoices/Payments will be processed under old name or manually if new name must be reflected. | 2000-01-01 | Jason Moore
| Process Name Change | SIFT | After view refresh, verify new CP name is reflected in drop downs and on invoices. | Invoices/Payments will be processed under old name or manually if new name must be reflected. | 2000-01-01 | Becky Ford
| Process Name Change | TAGG | After view refresh and job to move deals to new shortname is run, verify new CP name appears in drop downs and existing deals show new short name. | Short name updates will not be processed in GCP. | 2000-01-01 | Will Kelly
| Process Name Change | ERMS | After view refresh and job to move deals to new shortname is run, verify new CP name appears in drop downs and existing deals show new short name. | Short name updates will not be processed in GCP. | 2000-01-01 | Will Kelly
| Process Name Change | SAP | Verify name change appears on bridge. | GCP and SAP names will need to be synchronized after system problems are corrected. | 2000-01-01 | Marilyn Colbert
| Process Name Change | POPs | Verify name change appears in drop downs and on existing deals. | Deals and scheduling will reflect old name. | 2000-01-01 | Mary Smith
| Process Name Change | SOLARC | After view refresh, verify new name appears in drop downs and on existing deals. | Invoices/Payments will be processed under old name or manually if new name must be reflected. | 2000-01-01 | Cindy Horn
| Change Settlement Address | Global Counterparty | Change Wire info and physical address. No errors should occur. | Payments affected will need to be made manually. | 2000-01-01 | Jason Moore
| Change Settlement Address | UNIFY | Verify settlement address change is reflected in statement group. | Payments affected will need to be made manually. | 2000-01-01 | Bryce Baxter
| Change Settlement Address | SIFT | After view refresh, verify settlement address change is reflected on payments. | Payments affected will need to be made manually. | 2000-01-01 | Becky Ford
| Change Settlement Address | SOLARC | After view refresh, verify settlement address change is reflected on payments. | Payments affected will need to be made manually. | 2000-01-01 | Cindy Horn
CALL SAP/COE TEAM TO PROCESS CHANGE
ALL DEALS / CONTRACTS SHOULD BE KILLED OR TERMINATED.
| Process Merger | Global Counterparty | Inactive parties show status of inactive. Be sure to change status on both 'Y2K Dummy' and ' Y2K DummyA' records. | Notify all not to use this party even though it shows available for use. | 1/1/00 Last thing | Marilyn Colbert
| Process Merger | Sitara | After server bounce, verify that no deals exist under inactive party and that party does not appear in drop downs. | Notify all not to use this party even though it shows available for use. | 2000-01-04 | Will Kelly
| Process Merger | TAGG | After view refresh, ensure no deals exist under the inactive party and that the party does not appear in drop downs. | Notify all not to use this party even though it shows available for use. | 2000-01-04 | Will Kelly
| Process Merger | SOLARC | After view refresh, ensure no deals exist under the inactive party and that the party does not appear in drop downs. | Notify all not to use this party even though it shows available for use. | 2000-01-04 | Cindy Horn
| Process Merger | ERMS | After view refresh, ensure no deals exist under the inactive party. | Notify Credit that exposure is potentially split among multiple parties. | 2000-01-04 | Will Kelly
| Process Merger | Unify | After view refresh, ensure no deals exist under the inactive party and that the party does not appear in drop downs. | Do not process payments or invoices for this party without instruction from Credit/Legal. | 2000-01-04 | Bryce Baxter
| Process Merger | POPs | Verify inactive party does not appear in drop downs. | Notify all not to use this party even though it shows available for use. | 2000-01-04 | Mary Smith
| Process Merger | Enpower | After view refresh, ensure no deals exist under the inactive party and that the party does not appear in drop downs. | Do not process payments or invoices for this party without instruction from Credit/Legal. | 2000-01-04 | Kim Theriot
| Process Merger | SIFT | After view refresh, ensure no deals exist under the inactive party and that the party does not appear in drop downs. | Do not process payments or invoices for this party without instruction from Credit/Legal. | 2000-01-04 | Becky Ford
| Process Merger | SAP | Have dummy records removed/inactivated in SAP. | GCP and SAP names will need to be synchronized after system problems are corrected. | 2000-01-04 | Marilyn Colbert
| Setup New Bank | GCP |  |  | 2000-01-01 | Jason Moore
| Access D&B | D&B Proprietary | Look up company and obtain DUNs number, World Parent | Telephone D&B to obtain DUNs otherwise no DUNs available for new parties to support EDI nominations | 1/1/00 9:45am | Jason Moore

## GK Procs
ENA Energy Operations
Global Contracts
Y2K Preparations and Test Plan
| December | [6 empty] | January
| S | M | T | W | T | F | S | S | M | T | W | T | F | S
1
|  |  |  | 1 | 2 | 3 | 4 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| 5 | 6 | 7 | 8 | 9 | 10 | 11 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 12 | 13 | 14 | 15 | 16 | 17 | 18 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| 19 | 20 | 21 | 22 | 23 | 24 | 25 | 23 | 24 | 25 | 26 | 27 | 28 | 29
| 26 | 27 | 28 | 29 | 30 | 31 |  | 2: 30; 3: 31
I. | Critical Processes
| A. | Set up new contracts - Buy/Sale
| B. | Set up new contracts - Service
| C. | Expire Contract - Buy/Sale
| D. | Expire Contract - Service
| E. | Assign Contract - Buy/Sale
| F. | Assign Contract - Service
II. | Critical Dates
| A. | Bid Week
| B. | First day of month - January 1, 2000
III. | Dependencies
| A. | Deal Validation - Contract attachment
| B. | Settlements - payment terms
| C. | Logistics - contracts for nominations
IV. | Preparations
A. Run Hardcopy Reports
|  | I. | 12/27/1999 |  |  | Print Contract Termination/Assignment Listing
|  | ii. | 12/30/1999 |  |  | Print Active Contract List by Counterparty
|  | iii. | 12/30/1999 |  |  | Print Active Contract List by Global Contract number
|  | iv. | 12/27/1999 |  |  | For service contracts, print list of pipelines and contacts
| B. | Test Online Connection from home - 12/27/99
|  | I. | Global Contracts application
|  | ii. | Excel
|  | iii. | Lotus Notes
|  | iv. | Sitara
| C. | Confirm Y2K test plans with dependent parties - 12/27/99
V. | Equipment/Supplies required for Disaster Scenario
| A. | Telephone - voice line
| B. | Telephone - data line for D&B communication
| C. | Laptop with modem
| D. | Manual Deal Ticket process for trade capture
| E. | General office supplies
| F. | Pipeline list and contact names and phone numbers
VI. | Y2K Global Contracts Contacts
|  | Amelia Alland |  |  |  | X3-3440 |  | 2: (281) 894-2131; 7: (713) 509-6186
|  | Sylvia Campos |  |  |  | X3-5755 |  | 2: (713) 807-0550; 7: (713) 509-4650
|  | Karen Lambert X3-0605 | [5 empty] | 2: (713) 849-5506; 7: (713) 707-6571 | backup
|  | Linda Bryan X3-3538 | [5 empty] | 2: (281) 431-2875; 7: (713) 509-4650 | backup
|  | Connie Sutton X3-5686 | [5 empty] | 2: (409) 321-6102; 7: (713) 761-5036 | backup
VII. | Test Plans for 1/1/2000
| A. | Execute tasks as outlined on GK Test template using inputs from other areas such as Deal Validation
| B. | Capture screen print of all entries and verification of integrated systems
| C. | Test online connection from home on 1/1/00

## GK Test
Global Contracts 1/1/2000 Test /Plan
| Procedure | System | Expected Result | Contingency Plan | Date/Time | Responsible Person
| Set up new Contract | Global Contracts | New GTC, New Master BUY/SALE for both ENA and HPL. New Transport Revenue for HPL and Expense for ENA - Global number is assigned with no errors. Contracts should have an effective date of 1/1/00. | Keep track of contract requests using Lotus Notes Contract Request and Contract tracking databases. | 1/1/00 9:40am | Amelia Alland / Sylvia Campos/Kim Theriot
RUN SITARA SERVER BOUNCE / ENPOWER VIEW REFRESH
CALL DBA ON-CALL @ 888-993-3793 or SECONDARY DBA ON-CALL @ 888-993-3795 for REFRESH
| Set up new Contract | UNIFY | Verify Contract appears in drop downs. | Scheduling will have to be completed manually. | 1/1/2000 10:00:00am | Amelia Alland / Sylvia Campos/Kim Theriot
| Set up new Contract | POPs | Verify Contract appears in drop downs. | Scheduling will have to be completed manually. | 1/1/2000 10:00:00am | Mary Smith
| Set up new Contract | Sitara | After server bounce, attach contract to deal. | How do we get deals into Unify ? | 1/1/2000 10:00:00am | Kathryn Cordes
| Set up new Contract | Enpower | After view refresh, attach contract to deal. | ? | 1/1/2000 10:00:00am | Kim Theriot
| Add point to contract | Global Contracts | Add 'Y2K Dummy' point to HPL contracts for party 'Y2K Dummy' | ? | 1/1/2000 10:15am | Amelia Alland/Sylvia Campos
| Expire Contract | Global Contracts | Verify that overnight batch job ran without errors and that all contracts with expiration of 12/31/99 appear with an expired status | Manually expire contracts or run expiration batch job when system problems are corrected. | 1/1/00 9:45am | Amelia Alland / Sylvia Campos/Kim Theriot
| Expire Contract | Unify | Verify contract status as expired. | Notify all not to utilize contract for current or forward month activity. | 1/1/00 9:45am | Amelia Alland / Sylvia Campos/Kim Theriot
| Expire Contract | POPs | Verify contract status as expired. | Notify all not to utilize contract for current or forward month activity. | 1/1/2000 10:00:00am | Mary Smith
| Expire Contract | Sitara | Verify contract cannot be attached to deals. | Notify all not to utilize contract for current or forward month activity. | 1/1/2000 10:00:00am | Kathryn Cordes
| Expire Contract | Enpower | Verify contract cannot be attached to deals. | Notify all not to utilize contract for current or forward month activity. | 1/1/2000 10:00:00am | Kim Theriot
| Assign Contract | Global Contracts | Process any real assignments that are effective 1/1/00. Contract appears with new name and amendment level with Operational effective date of 1/1/00. List of assignments will be distributed mid December. | Set up new contract and track for later corrections to original contract. | 1/1/2000 10:00:00am | Amelia Alland / Sylvia Campos/Kim Theriot
Call Kim Theriot to see if her assignments are done, then :
CALL DBA ON-CALL @ 888-993-3793 or SECONDARY DBA ON-CALL @ 888-993-3795 for REFRESH
| Assign Contract | Unify | Verify contract appears under new party name. | Set up new contract and track for later corrections to original contract. | 1/1/00 11:00am | Amelia Alland / Sylvia Campos/Kim Theriot
| Assign Contract | POPs | Verify contract appears under new party name. | Set up new contract and track for later corrections to original contract. | 1/1/00 11:00am | Mary Smith
| Assign Contract | Sitara | Attach contract to deals for new party. | Set up new contract and track for later corrections to original contract. | 1/1/00 11:00am | Kathryn Cordes
| Assign Contract | Enpower | After view refresh, attach contract to deal for new party. | Set up new contract and track for later corrections to original contract. | 1/1/00 11:00am | Kim Theriot
After all groups have tested a deal all the way through, process the next step. Check with Settlements to see if they are finished.
| Terminate Contract | GK | Terminate Power contracts created on 'Y2K Dummy' party |  | 2000-01-01 | Kim Theriot
| Terminate Contract | GK | Terminate all gas contracts created on 'Y2K Dummy' party |  | 2000-01-01 | Amelia Alland/Sylvia Campos
| Terminate Contract | Unify | Make sure contract is no longer available. |  | 2000-01-04 | Amelia Alland
| Terminate Contract | Enpower | Make sure contract is no longer available. |  | 2000-01-04 | Kim Theriot
| Terminate Contract | Sitara | Make sure contract is no longer available. |  | 2000-01-04 | Kathryn Cordes
| Terminate Contract | POPs | Make sure contract is no longer available. |  | 2000-01-04 | Amelia Alland/Sylvia Campos

## GFD Procs
ENA Energy Operations
Global Facilities
Y2K Preparations and Test Plan
| December | [6 empty] | January
| S | M | T | W | T | F | S | S | M | T | W | T | F | S
1
|  |  |  | 1 | 2 | 3 | 4 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| 5 | 6 | 7 | 8 | 9 | 10 | 11 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 12 | 13 | 14 | 15 | 16 | 17 | 18 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| 19 | 20 | 21 | 22 | 23 | 24 | 25 | 23 | 24 | 25 | 26 | 27 | 28 | 29
| 26 | 27 | 28 | 29 | 30 | 31 |  | 2: 30; 3: 31
I. | Critical Processes
| A. | Set up new facility
| B. | Inactivate facility
| C. | Update DRN
| E. | Access PI/IHS for meter research
| G. | Access MIPS for meter research
II. | Critical Dates
| A. | Bidweek
| B. | First of month - January 1, 2000
III. | Dependencies
| A. | Sitara meter assignment
| B. | Logistics - Meter information and DRN number for EDI nominations
IV. | Preparations
A. Run Hardcopy Reports
|  | I. | 12/30/1999 |  |  | Print active facilities and meters by meter number
| B. | Test Online Connection from home - 12/27/99
|  | I. | Global Facilities application
|  | ii. | Lotus Notes
|  | iii. | PI Grid Apps / IHS
|  | iv. | MIPS
| C. | Confirm Y2K test plans with dependent parties - 12/27/99
V. | Equipment/Supplies required for Disaster Scenario
| A. | One Fax Machine
| B. | Telephone - voice line
| C. | Telephone - data line for D&B communication
| D. | Laptop with modem
| E. | General office supplies
VI. | Y2K Global Facilities Contacts
|  | Donna Consemiu |  |  |  | X3-3446 |  | 2: (281) 528-9834; 6: (713) 761-3469
|  | Faye Ellis X3-5817 | [5 empty] | 2: (281) 441-1454; 6: (713) 761-3469 | backup
VII. | Test Plans for 1/1/2000
| A. | Execute tasks as outlined on GFD Test template using inputs from other areas such as Logistics
| B. | Capture screen print of all entries and verification of integrated systems
| C. | Test online connection from home on 1/1/00

## GFD Test
Global Facilities 1/1/2000 Test /Plan
| Procedure | System | Expected Result | Contingency Plan | Date/Time | Responsible Person
| Set up New Facility | Global Facilities | New facility number for HPL with name of 'Y2K Dummy'. Setup should complete with no errors. | Track meter requests using Lotus Notes Request database. Obtain DRN info manually for scheduling. | 1/1/00 9:30am | Donna Consemiu
| Add new Region / Delivery Point | Global Facilities | Use 'Y2K Dummy'. Setup should complete with no errors. |  | 1/1/00 9:30am | Kim Theriot
Call for Sitara Server Bounce
| Set up New Facility | Sitara | After server bounce, verify facility/meter appears in facility assignment window. | ? | 1/1/00 10:00am | Gary Payne
| Set up New Facility | Unify | Verify facility appears in facility listing. | Schedule manually. | 1/1/00 10:00am | Donna Consemiu
| Set up New Facility | POPs | Verify facility appears in drop downs. | Schedule manually. | 1/1/00 10:00am | Mary Smith/Pat Klein ?
| Set up New Facility | Global Contracts | Verify facility appears in drop downs. | Keep track of meter attachments for later processing. All point specific contracts for On-system should be set to ALL POINTS until system problems can be corrected. | 1/1/00 10:00am | Amelia Alland/Sylvia Campos
| Set up New Facility | Enpower | Verify facility appears in drop downs. (DBA: refresh from Sitara) | ? | 1/1/00 10:00am | Kim Theriot
| Update Trade Zone | Global Facilities/Sitara | After new facility is setup, notify Sitara team to update trade zone. | ? | 1/1/00 10:00am | Donna Consemiu
After all groups have tested a deal all the way through, process the next step. Check with Logistics.
| Update DRN | Global Facilities | Update accepted with no errors. | Schedule manually. | 2000-01-01 | Donna Consemiu
Call for Sitara Server Bounce
| Update DRN | Unify | DRN reflected in facility/meter listing. | Schedule manually. | 2000-01-01 | Gary Payne
| Update DRN | POPs | DRN reflected in facility/meter listing. | Schedule manually. | 2000-01-01 | Mary Smith/Pat Klein ?
After all groups have tested a deal all the way through, process the next step. Check with Settlements to see when they are finished.
| Inactivate Facility | Global Facilities | Status should reflect inactive with no errors. | Notify all parties not to utilize this facility/meter. | 2000-01-01 | Donna Consemiu
| Inactivate Region / Delivery Point | Global Facilities | Status should reflect inactive with no errors. | Notify all parties not to utilize this region / delivery point. | 2000-01-01 | Kim Theriot
Call for Sitara Server Bounce
| Inactivate Facility | Sitara | After server bounce, verify facility does not appear in meter assignment window. | Notify all parties not to utilize this facility/meter. | 2000-01-04 | Gary Payne
| Inactivate Facility | Unify | Verify status as inactive in facility listing. | Notify all parties not to utilize this facility/meter. | 2000-01-04 | Donna Consemiu
| Inactivate Facility | POPs | Verify status as inactive. | Notify all parties not to utilize this facility/meter. | 2000-01-04 | Mary Smith/Pat Klein ?
| Inactivate Facility | Global Contracts | Verify facility/meter is not reflected on an active contract. | Notify all parties not to utilize this facility/meter. | 2000-01-04 | Amelia Alland / Sylvia Campos
| Inactivate Facility | Enpower | After view refresh, verify facility status as inactive. | Notify all parties not to utilize this facility/meter. | 2000-01-04 | Kim Theriot
| Access PI/I.H.S. & MIPS Database | PI / I.H.S. & MIPS | Retrieve meter information including DRN number for scheduling. | Telephone PI for DRN information. Have a paper copy of meter numbers or call measurement accounting to see if they can access meter information. | 1/1/00 9:40am | Donna Consemiu

## SAP Procs
ENA Energy Operations
Global Counterparty/SAP COE
Y2K Preparations and Test Plan
| December | [6 empty] | January
| S | M | T | W | T | F | S | S | M | T | W | T | F | S
1
|  |  |  | 1 | 2 | 3 | 4 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| 5 | 6 | 7 | 8 | 9 | 10 | 11 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 12 | 13 | 14 | 15 | 16 | 17 | 18 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| 19 | 20 | 21 | 22 | 23 | 24 | 25 | 23 | 24 | 25 | 26 | 27 | 28 | 29
| 26 | 27 | 28 | 29 | 30 | 31 |  | 2: 30; 3: 31
I. | Critical Processes
| A. | Process new counterparty to SAP
| B. | Process settlement address change to SAP
| C. | Set up new bank
II. | Critical Dates
| A. | First week of month - January 1 - January 7
III. | Dependencies
| A. | ENA - none at this time
| B. | Enron - Europe - settlements
IV. | Preparations
A. Run Hardcopy Reports
|  | ii. | 12/30/1999 |  |  | Active Customer/Vendor list
|  | iii. | 12/30/1999 |  |  | Bank list
| B. | Confirm Y2K test plans with dependent parties - 12/27/99
V. | Equipment/Supplies required for Disaster Scenario
| A. | Telephone - voice line
| B. | General office supplies
VI. | Y2K Global Counterparty/SAP COE Contacts
|  | Marilyn Colbert |  |  |  | X3-6517 |  | 2: (713) 862-2066
|  | Mary Botello |  |  |  | X3-3103 |  | 2: (281) 370-2363; 6: backup
|  | Bill Hare |  |  |  | X3-9249 |  | 2: (281) 893-4012
VII. | Test Plans for 1/1/2000
| A. | Execute tasks as outlined on SAP Test template using inputs from other areas
such as Global Counterparty
| B. | Capture screen print of all entries and verification of integrated systems
| C. | Test online connection from home on 1/1/00

## SAP Test
GCP/SAP COE 1/1/2000 Test /Plan
| Procedure | System | Expected Result | Contingency Plan | Date/Time | Responsible Person
| Verify new record in SAP | SAP | Verify that the Early Y2K record set up 12/30 went across to SAP. |  | 2000-01-01 | Marilyn Colbert
| Set up New Counterparty | Global Counterparty | SAP program needs to run after the 'Early Y2K Dummy' record is set up so that there are transactions in SAP to check on 1/1/00. | This record is to support testing of name changes etc on 1/1/00 | 1999-12-30 | Marilyn Colbert
| Process new counterparty setup to SAP | SAP | Bridge cleared and SAP updated with no errors. | Track requests for new CP setups for later input or if Enron-Europe, input manually into SAP | 1/1/00 10:00am | Marilyn Colbert
| Process settlement address change to SAP | SAP | Bridge cleared and SAP updated with no errors. (DBA: SAP refresh Xref server, GCP_Group) | Track requests for new CP setups for later input or if Enron-Europe, input manually into SAP | 2000-01-01 | Marilyn Colbert
| Process counterparty Name Change | SAP | Should see 'Early Y2K Dummy' change |  | 2000-01-01 | Marilyn Colbert
| Verify SAPID | GCP | SAP ID should be passed back and updated on 'Y2K Dummy A' party |  | 2000-01-01 | Marilyn Colbert
| Setup dummy new bank | SAP | Set up a "dummy" bank to create an error in order to check the exception report function | Track requests for new bank setups for later input or if Enron-Europe, input manually into SAP | 1/1/00 9:30am | Marilyn Colbert

## GRS Test
Global Rate Services 1/1/2000 Test /Plan
| Procedure | System | Expected Result | Contingency Plan | Date/Time | Responsible Person
| Load Exchange rates into ERMS | Telerate/ERMS | Reload Thursday 12/30 prices with 1/1000 added to the price (2.251 vs. 2.25) for Thursday 12/30 and a January futures price. Load should run with no errors. | Hold book calc until IT can assist with getting prices loaded. | 1/1/00 9:40am | Veronica Arriaga
| Enter manually calc'd prices into Unify | Excel/Unify | Input with no errors. | Manually invoice. | 1/1/00 10:00am | Judy Barnes
| Enter prices into Enpower | Enpower | Enter PX prices into Enpower for weekend. | Hold book calc until IT can assist with getting prices loaded. | 1/1/00 10:00am | Veronica Arriaga
| Check PJM/NEPOOL price load into Enpower | Enpower | Verify prices match between PJM internet and Enpower. | Hold book calc until IT can assist with getting prices loaded. | 1/1/00 11:00am | Veronica Arriaga
| Run Phoenix to ERMS exceptions | Phoenix/ERMS | Minimal exceptions | If Phoenix is in error, any payments or invoices should be manually prepared. If ERMS is in error, books should not be calced until problem is corrected. | 1/1/2000 9:30am | Apolak Borthakur
| Refresh Unify with Phoenix prices | Phoenix/Unify | Refresh with no errors. Verify prices in Unify. | Payments or invoices should be manually prepared. | 1/1/2000 10:15am | Russ Whitton
| Access Internet Sites used | Netscape | Verify required pages are accessible and provide information needed | Call publishers for prices. | 1/1/00 9:50am | Veronica Arriaga
| Access Telerate Pages | Telerate | Market closed 1/1/00. Cannot verify updates. | Seek Reuters source if problems of 1/4/00 | 1/1/00 9:30am | Veronica Arriaga

## GRS Procs
ENA Energy Operations
Global Rate Services
Y2K Preparations and Test Plan
| December | [6 empty] | January
| S | M | T | W | T | F | S | S | M | T | W | T | F | S
1
|  |  |  | 1 | 2 | 3 | 4 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| 5 | 6 | 7 | 8 | 9 | 10 | 11 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 12 | 13 | 14 | 15 | 16 | 17 | 18 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| 19 | 20 | 21 | 22 | 23 | 24 | 25 | 23 | 24 | 25 | 26 | 27 | 28 | 29
| 26 | 27 | 28 | 29 | 30 | 31 |  | 2: 30; 3: 31
I. | Critical Processes
| A. | Load Exchange prices into ERMS
| B. | Process rate additions in Unify
| C. | Load PX rates into Enpower
| D. | Check PJM price load into Enpower
| E. | Monitor Telerate
II. | Critical Dates
| A. | Everyday
III. | Dependencies
| A. | Risk - valuation
| B. | Settlements - published prices
IV. | Preparations
A. Run Hardcopy Reports
|  | I. | 12/30/1999 |  |  | Print last known published prices for current day
| B. | Test Online Connection from home - 12/27/99
|  | I. | Internet
|  | ii. | Enpower
|  | iii. | Unify
| C. | Confirm Y2K test plans with dependent parties - 12/27/99
V. | Equipment/Supplies required for Disaster Scenario
| A. | One Fax Machine
| B. | Telephone - voice line
| C. | Telephone - data line for D&B communication
| D. | Laptop with modem
| E. | Unix and Excel with Mastic macro
| F. | Telerate
| G. | General office supplies
VI. | Y2K Global Rate Services Contacts
|  | Veronica Arriaga |  |  |  | X3-3898 |  | 2: (713) 802-9776; 6: (713) 761-3469
|  | Judy Barnes X3-7966 | [5 empty] | 2: (281) 980-4875; 6: (713) 618-2524
VII. | Test Plans for 1/1/2000
| A. | Execute tasks as outlined on GRS Test template
| B. | Capture screen print of all entries and verification of integrated systems
| C. | Test online connection from home on 1/1/00

## DBA Notes
Refreshes by Global System and Interface
SAP
Global : This interface is done via snapshots and stored procedures. This refresh can only be done AFTER sap has refreshed their cross-reference server.
| Refresh Host: | moe
Refresh job: /common/dba/server/oracle/bin/refresh_sap_gbl.ksh –g gdb –l GCP_LOGIN –g SAP_GROUP
Normal Refresh Schedule
5AM, 2PM, 5PM – at 30 minutes past the hour
Global Counterparties
TAGG/ERMS: These interfaces have both views and snapshots on their side.
Refresh host: larry
Refresh job: /common/dba/server/oracle/bin/refresh_ss.ksh –s ermt –l GCP_REMOTE_LOGIN –n GCP_GROUP –m f –g
Normal Refresh Schedule:
6AM – 9M, at 20 and 50 minutes after the hour
3AM, 5AM, 11PM – on the hour
DCAFII: This interface has both views and snapshots on their side
Refresh host: aurora
Refresh job: /common/dba/server/oracle/bin/refresh_ss.ksh –s dcfprod –l GCP_REMOTE_LOGIN –n GCP_GROUP –m f –g
Normal Refresh Schedule:
11AM, 8PM – at 15 minutes after the hour
*** For Enpower Refreshes certain users have the capability of performing this via their application
ENPOWER (Houston): This interface utilizes views and poor-man’s replication
Refresh host: neutron (pwrprod1)
Refresh job: /u301/home/dba/oracle/admin/pwrprod1/bin/refresh_lookup.ksh –s pwrprod1
Normal Refresh Schedule:
|  | 3AM | #NAME?
Refresh host: moe (pwrprod2)
Refresh job: /u201/home/dba/oracle/admin/pwrprod2/bin/refresh_lookup.ksh –s pwprod2 –b NA
Normal Refresh Schedule:
3AM – on the hour
ENPOWER (London): This interface utilizes views and poor-man’s replication
Refresh host: neutron (europwrp)
Refresh job: /u301/home/dba/oracle/admin/europwrp/bin/refresh_lookup.ksh –s europwrp
Normal Refresh Schedule:
6PM – on the hour
Global Contracts
*** For Enpower Refreshes certain users have the capability of performing this via their application
This job for Enpower will refresh Counterparties and Contracts data (both)
ENPOWER (Houston): This interface utilizes views and poor-man’s replication
Refresh host: neutron (pwrprod1)
Refresh job: /u301/home/dba/oracle/admin/pwrprod1/bin/refresh_lookup.ksh –s pwrprod1
Normal Refresh Schedule:
|  | 3AM | #NAME?
Refresh host: moe (pwrprod2)
Refresh job: /u201/home/dba/oracle/admin/pwrprod2/bin/refresh_lookup.ksh –s pwprod2 –b NA
Normal Refresh Schedule:
3AM – on the hour
ENPOWER (London): This interface utilizes views and poor-man’s replication
Refresh host: neutron (europwrp)
Refresh job: /u301/home/dba/oracle/admin/europwrp/bin/refresh_lookup.ksh –s europwrp
Normal Refresh Schedule:
6PM – on the hour
Global Facilities
TAGG/ERMS: These interfaces have both views and snapshots on their side.
Refresh host: larry
Refresh job: /common/dba/server/oracle/bin/refresh_ss.ksh –s ermt –l GDB_REMOTE_LOGIN –n GFD_GROUP –m f –g
Normal Refresh Schedule:
6AM – 9M, at 5 and 35 minutes after the hour
3AM, 5AM, 11PM – at 40 minutes after the hour
*** For Enpower Refreshes certain users have the capability of performing this via their application
ENPOWER (Houston): This interface utilizes snapshots
Refresh host: neutron (pwrprod1)
Refresh job: /common/dba/server/oracle/bin/refresh_ss.ksh –s pwrprod1 –l PWR_LOGIN –n GFD_GROUP –m f –g
Normal Refresh Schedule:
|  | 8PM | #NAME?
Refresh host: moe (pwrprod2)
Refresh job: /common/dba/server/oracle/bin/refresh_ss.ksh –s pwrprod2 –l PWR_LOGIN –n GFD_GROUP –m f –g
Normal Refresh Schedule:
8PM – on the hour
ENPOWER (London): This interface utilizes snapshots
Refresh host: neutron (europwrp)
Refresh job: //common/dba/server/oracle/bin/refresh_ss.ksh –s europwrp –l PWR_LOGIN –n GFD_GROUP –m f –g
Normal Refresh Schedule:
7PM – on the hour
Trading Decision Support (TDS) : This interface utilizes snapshots
Refresh host: neutron (tdsprod)
Refresh job: //common/dba/server/oracle/bin/refresh_ss.ksh –s tdsprod –l CDS_LOGIN –n GFD_GROUP –m f –g
Normal Refresh Schedule:
3AM – 30 minutes after the hour