## Sheet1
ENRON TRANSPORTATION & STORAGE
CERTIFICATE FILING
GALLUP EXPANSION
EXHIBITS AND RESPONSIBLE PARTIES
| EXHIBIT |  | INFO NEEDED
EXHIBIT | DESCRIPTION | RESPONSIBLE PARTY | TO COMPLETE | DUE DATE
SECTION 7(c) PORTION
A | Articles of Incorporation and Bylaws | Certificate Analyst - (Secretary Division)
B | State authorization | Certificate Analyst - (Secretary Division)
C | Company Officials | Certificate Analyst - (Secretary Division)
D | Subsidiaries and Affiliation | Certificate Analyst - (Secretary Division)
E | Other pending applications and filings | Certificate Analyst -
F | Location of facilities | Facility Planning - (maps)
F-I | Environmental Report - 13 Resource Reports | Regional DES
needs info on unit
use ETS or FERC Plans & Proc?
ground disturbance?
assume FERC will require post construction noise survey
file Gallup post construction noise survey (what are we going to do about the trailer north of the station who was paid to move?)
clearances
G | Flow diagrams showing daily design capacity and reflecting operations with and without proposed facilities added | Facility Planning -
G-I | Flow diagrams reflecting maximum capabilities | Facility Planning - | Refer to G
G-II | Flow diagram data | Facility Planning -
H | Total gas supply data | Marketing/Customers
I | Market data | Marketing/Customers
J | Conversion to natural gas | N/A
K | Cost of facilities | Technical Services - Engineering/Construction- (pipeline to compressor) | Send to COS for Exhibit N
L | Financing | Business Analysis - (example available if using internal funds)
M | Construction, operation, and management | Construction - (examples available) | STANDARD LANGUAGE
N | Revenues, Expenses, and Income | COS | Need Exhibit K Rates needs Exhibit N
O | Depreciation and depletion | Business Analysis - (example available) | STANDARD LANGUAGE
P | Tariff | Rates -
Z-I | Additional Exhibits begin at Exhibit Z-I | IF REQUIRED TO SUPPORT APPLICATION
Need project scope
Identify the location (address & phone number) of the nearest Library or public access
building in each county within the project area.
Identify the appropriate newspaper(s) with general circulation in the project area. What
is the circulation timing (daily, weekly, etc.)
Provide description and location of appurtenant facilities (including abandonments)
Make sure everyone understands this includes any facilities even if at another location.
Landowner Notification requirements.
Are there any third party facilities?
Marketing data/support for Public Convenience and Necessity
Policy Statement Support:
Affect on other pipeline/customers
Not subsidized by existing customers
Environmental impact