## Open
SUPPORT SERVICES GROUP
Support Type | Deal Name | Responsible Person | Impact ($MM) | Background/Key Issues | Updated | Strategies/Comments/Next Actions
Regulatory Risk | SW Gas Rate Case | Leslie Lawner |  | SW Gas has billed EES $8 million or so in imbalance fees because gas scheduled to be delivered into SW was curtailed by El Paso. | 2001-09-10 | Testimony filed and hearing was conducted. Negotiations were conducted but without much success. Awaiting AZ PUC decision. Case in Briefing stage. Also trying to get better transportation rules.
| North West Refund Case (FERC) | Bob Frank |  | FERC has ordered hearings on potential refunds and overcharges occuring in the northwest during CA crisis period. | 2001-09-27 | Taking lead role in coordinating internal position and responses. ALJ proposed order is very favorable in that no refunds are ordered.
| Georgia Power Rate Case | Harry Kingerski & Bob Frank |  | GP has filed a plan to implement automatic rate increases and refund certain weather-related revenues. | 2001-09-10 | Hearings begin 9/10. Enron will file testimony to help support book position and advocate for weather risk management. Working with weather desk to quantify illustrative weather products.
| TX Implementaion Cases | Pat Keene |  | Implementaiton dockets still open on how stranded costs will be handled. | 2001-09-10 | Monitoring. Big issue is whether negative stranded costs will be allowed.
| IL Rate cases | Harry Kingerski |  | Com Ed and IP have both filed rate cases that would increase rate to shopping customers by more than to non-shoppers. | 2001-09-27 | Providing technical and case maangement support to EWS and Janine Migden. Testimony has been filed in Com Ed case. IP strategy is to object that increase is illegal and violates restructuring law.
| CA PUC cases | Robert Neustaedter & Harry Kingerski |  | PUC continues to debate and study how to assess rate increases and when to kill direct access. | 2001-09-27 | Providing technical and case management support to GA West group as appropriate. San Diego rate increase implemented without affect to Direct Access; based on 9/20 PUC order.
| Gulf Power Rate Case | Harry Kingerski |  | Gulf Power has filed a rate increase that will affect EWS retail positions. Key deal is with ECS for supply of compression services to FGT. | 2001-09-27 | Reviewing case filing and developing case strategy. Case involves interests of EWS, ECS, FGT and EGM.
Advocacy | Ohio Operational Support | Gloria Ogenyi |  | PUC conducting workshops on implementation issues, such as minimum stay, purchase of receivables, slamming, UDC billing | 2001-09-10 | Reviewing utility filings. Preparing interventions on behalf of EES. Meeting with staff and commissioners as appropriate.
| ERCOT retail rules | Nancy Hetrick |  | Act as chair of retail rule subcommittee. Handling integration of retail needs with wholesale market rules. | 2001-09-10 | Working through standardized electronic transactions. Early problems associated with TX pilot being addressed.
| TX Operational Support | Gloria Ogenyi |  | Telemarketing rules, customer lists, registration as a supplier, ballot procedures | 2001-09-10 | Registered to participate in TXU and Reliant areas. Working to identify applicable telemarketing rules. Ballot procedure needs to go forward; Staff may be trying to delay until next year.
| NV Open Access Implementation | Pat Keene |  | Industry subcommittee is writing implementation rules that will be submitted for PUC approval. | 2001-09-10 | Pat Keene is member of subcommitte. Rules need to address how departing customers do not act to detriment of other customers, as required by law. Initial meetings have been held and rule is being written.
| AZ Hedging | Leslie Lawner |  | ACC conducting investigation into hedging practices of utilities. | 2001-09-10 | Participated in first workshop. More will be scheduled soon. Goal is to promote use of hedging. Part of national effort, in support of Sue Landwehr.
| Marketing Affiliate Rule | Leslie Lawner |  | FERC is considering revisions to its gas marketing affiliate rule. | 2001-09-10 | Meeting with FERC staff occurred Aug. 28. A NOPR is expected soon and we will prepare comments. Working with Becky Cantrell and Donna Fulton.
| El Paso Cases (FERC) | Leslie Lawner |  | Several cases pending involving reallocation of receipt points, system expansion, and demand charge refunds for unavailable capacity. | 2001-09-10 | Comments will be filed Oct. 2 on reallocation of receipt points and comments have been filed in other cases. Continuing to monitor as appropriate. Working with Becky Cantrell and EES/ENA as appropriate.
Deal Support | AEP compliance in TX with Retail Requirements | Gloria Ogenyi |  | AEP has not complied with requirements to disclose customer lists or price that large customers will be supplied under starting 1/02. | 2001-09-10 | Informal complaint has been sent to Staff of TX PUC. Will be scheduling a meeting to further review and discuss. EES has identified AEP compliance as a key issue.
| IL Supplier Agreements | Gloria Ogenyi & Nancy Hetrick |  | Supplier agreements need to be negotiated and finalized with Com Ed and IP. | 2001-09-10
| Market Analyses | Nancy Hetrick & Vinio Floris |  | EES has requested market analysis reports for Central Hudson. | 2001-09-27 | Reports being prepared.
| SW Gas Case in NV | Leslie Lawner & Pat Keene |  | SW has proposed a rule that would require transporting gas customers to stay with the utility for 5 years if they return to utility service. | 2001-09-10 | Testimony will be filed. Case will be handled internally except for small amount of outside legal support.
| OR Market Opening | Robert Neustaedter |  | Market for large customers opens in OR Spring 2002. | 2001-09-27 | Meetings conducted with EWS and EES Origination to explain regulatory rules. Helping identify future opportunities and rate obligations.
| Elba Island LNG | Robert Neustaedter |  | EGM trying to deliver LNG to Southern Gas at Elba with El Paso Mktg as receiver. Liquification costs are point of contention. | 2001-09-10 | Identifying appropriate level of costs that Southern should charge. Costs have been modelled. May need to address through FERC proceeding. EGM is eager to address these issues.
| Williston Basin Pipeline Base Gas Monetization | Robert Neustaedter |  | ENA West Gas Origination is evaluating monetizing storage base gas, replacing with pipeline compression and pipeline looping. | 2001-09-10 | Identitying regulatory issues, and developing strategies to address such issues.
| EDI development and implementation in NY | Vinio Floris, Nancy Hetrick |  | EDI is being developed by all market players, including Enron. We are making sure appropriate standards are adopted in a very narrow timeframe. EDI implementation has one of the highest priorities for pursuing large commercial operations in NY. | 2001-09-27 | Enron is actively participating in the development, testing and implementation of the EDI standards. We have created an ESCO/Marketer working group to focus support and concerns.
| New York Operational Support | Vinio Floris, Nancy Hetrick |  | Enrollment of new customers in ConEd's territory has experienced billing problems. | 2001-09-27 | EES and GA are in the process of executing a Billing Agency Agreement (which includes bill testing, security/parental guarantee, etc.). GA is facilitating this process which is expected to be completed before mid-October.
| EDI and regulatory issues in BG&E (Maryland) | Vinio Floris |  | EES has plans to enter the BG&E market territory. Supplier Consolidated Billing is being offered in a limited basis. | 2001-09-27 | GA is researching on this even though further EDI development and implementation is unlikely in the near future. Other regulatory/commercial issues are also being researched (v.g. Internet-based systems replacing VANs).
| Canada and Mexico natural gas issues | Leslie Lawner |  | Preparing an application to be filed with the Department of Energy to reauthorize our import/export authorization for natural gas in and out of Canada and Mexico. | 2001-09-27 | Application should be filed by October 1.
| Tex-Mex: HVDC Tie with Mexico | Robert Frank |  | EWS is building a transmission tie from ERCOT to Mexico. | 2001-09-27 | Ongoing support on state and federal regulatory issues.
| Equity Office Properties | Robert Frank |  | EES is evaluating a large-scale distributed generation initiative with this existing commodity customer. | 2001-09-27 | Ongoing analysis/evaluation of regulatory issues.
Regulatory Ventures