## Executive (hidden)
Deal Description Sheet - 6/18/01
Executive
YTD P & L | 6190000
Project Name | Counterparty | Description | Potential Valuation | Last Customer Contact | Probability | Expected Closing (Month/Year) | Weekly Updates / Comments
Total Upstream Products P & L |  | 16061000
W/out Production Offshore |  | 12346000
Note : All Upstream Products P&L includes other, origination and accrual.
The accrual numbers used are actual and do not include forecasts the remaining months of the year (June - Dec).
The P&L from Production Offshore is derived from the Pluto / MEGS deal.

## Bridgeline (hidden)
Deal Description Sheet - 6/18/01
Bridgeline
YTD EBIT forecast | -10828000 |  | 2nd Qtr EBIT forecast | -5182000
YTD EBIT plan | -13490000 |  | 2nd Qtr EBIT plan | -3372000
Variance | 2662000 |  | Variance | -1810000
Project Name | Description | Potential Valuation | Last Customer Contact | Probability | Expected Closing (Month/Year) | Weekly Updates / Comments
Compensation Plan | Incentive Plan for BHLP Employees and Upper Management. Recommend Accrual Bonus Funding based on EBITDA performance targets. Revision of Performance Review to incorporate new catergories. | 0 | 2001-05-31 | 100% | 2001-05-25 | Since Randy Curry refuses to sing the proposed BHLP compensation plan, the board has two alternatives : 1. Have another officer of BHLP sign the plan, 2. Make all secunded employees from both parents Bridgeline employees. Since our intent is to sell our equity interest and based on our experience with HPL, I think it would be best to make all individuals working or hired, BHLP employees. Brian and I will be meeting with Texaco next week.
Blowfish | Sale of Napoleonville Land led by Eva Rainer, Storage. | $5 MM | 2001-06-05 | 100% | 2001-09-01 | Paul Bienaiwski and Eva Rainer had lunch with Texas Brine who operates and drills for salt on OXY's behalf. OXY's preception of actual brine reserves is much greater than reality. Informed Texas Brine of Dow's interest for the land. Texas Brine is going to send a proposal for the land and is going to make and introduction to another OXY representative.
13 & 14 Workorder | Workorder drafted by Technical Services for infrastructure to get pad gas out of Wells 13 & 14 on Dow property. | $ -847 K | 2001-04-30 | 100% | 2001-05-01 | Received revised work order with new numbers for labor. Accepted by Brian Redmond. Signed and approved.

## E-Commerce 50+
Deal Description Sheet - 7/24/01
Producer E-Commerce
Project Name | Lead Originator | Counterparty | Description | Potential Valuation | Last Customer Contact | Probability | Expected Closing (Month/Year) | Weekly Updates / Comments
Andex | Linda Roberts | Andex | ATS accounting services and software. | 20000 | 2001-07-12 | 50% | 2001-07-01 | Andex has elected to pursue other options for their production management, however, Andex is interested in several ATS products.
Preston | Gary Bryan | Preston Energy | Sale of ATS software and/or ASP. Enron commision from ATS. | 40000 | 2001-06-19 | 80% | 2001-09-01 | Preston is expected to purchase several of the ATS products.
Columbia Natural Resources | John Singer |  | Application Service Provider, gas and liquids, E&P accounting, forecasting. | *$250,000 | 2001-04-16 | 50% | 2001-09-30 | ENA missed the supply deal, but is working on the outsourcing. Lost to AEP who bid 3 1/4 for the pool gas. ENA bid 1/4. CMR will start trading this summer.
VR84 | Nelson Ferries | Continental Land & Fur (CL&F) | ATS E&P accounting services and commodity management services | *$10,000 | 2001-07-13 | 90% | 2001-10-01 | ATS is currently providing E&P accounting services on VR 84. CL&F has an additinoal 300 wells producing 100 mmcfd that they could take in kind.
Mariner | Kevin Miller | Mariner | Integrated outsourcing products. | *$100,000 | 2001-07-24 | 50% | 2001-10-01 | Luncheon with Richard Clark in August.
Project Deep Blue Sea | Kevin Miller | Ocean Energy | Integrated outsourcing products and operations related to Harve Pipeline System. | *$500,000 | 2001-06-11 | 50% | 2001-11-01 | Project meeting scheduledfor July 26th with Ocean, Enron and HMS to outline project scope and other project parameters.
* Accrual

## E-Commerce -50 (hidden)
Deal Description Sheet - 7/24/01
Producer E-Commerce
Project Name | Lead Originator | Counterparty | Description | Potential Valuation | Last Customer Contact | Probability | Expected Closing (Month/Year) | Weekly Updates / Comments
Oilman | Kevin Miller | EOTT | Back office accounting services. | *$500,000 | 2001-07-13 | 25% | 2001-10-01 | EOTT met HMS in mid-June. ENA has reviewed ATS proposal. ENA will work with ATS to re-submit a more competitive proposal. Meeting scheduled for July 25th.
Callon | Kenn Loch | Callon | Outsourcing | 100000 | 2001-07-14 | 10% | 2001-10-01 | Rescheduled meeting with COO for August.
GW Pure | Jill Zivley | Pure Resources | Integrated outsourcing products. | *$250,000 | 2001-06-11 | 25% | 2001-12-01 | Met with Pure senior management on 6/29. Pure executive meeting on 7/2. Pure has signed a CA and data gathering trip is planned.
Gather Company | John Singer | Gather Company | Monetization and metering services. | 200000 | 2001-05-10 | 25% | 2001-12-01 | Follow up meeting in July, 2001.
Running Man | Kevin Miller | Marathon | Integrated outsourcing products. | *$1,000,000 | 2001-06-11 | 10% | 2001-12-01 | Meeting scheduled for August 2nd with VP marketing.
*Accrual

## Wellhead 50+ (hidden)
Deal Description Sheet - 7/2/01
Wellhead
YTD P&L |  | 81988
Project Name | Lead Originator | Counterparty | Description | Potential Valuation | Last Customer Contact | Probability | Expected Closing (Month/Year) | Weekly Updates / Comments
CL&F I |  | Continental Land & Fur | Accounting. | *$10,000 | 2001-05-22 | 90% | 2001-07-01 | Initial deal to close in June. 2 wells. ATS & ENA commodity.
Aspect Resources |  | Aspect Resources | Well Connect Offsystem - Cross Media #1, TNCT #1, Galveston County, TX, Meter 098-9815 and 098-9816, FGT Meter 092-0490 and 092-0489. | *$50,000 | 2001-06-08 | 50% | 2001-07-01 | Meeting June 8, 2001. Proposed total outsourcing and supply acquisition.
CL&F II |  | Continental Land & Fur | Accounting and scheduling, outsourcing. | 50000 | 2001-05-22 | 50% | 2001-09-01 | 300 wells depending on the success of CL&F II.
* Accrual

## Wellhead -50 (hidden)
Deal Description Sheet - 7/2/01
Wellhead
Project Name |  | Counterparty | Description | Potential Valuation | Last Customer Contact | Probability | Expected Closing (Month/Year) | Weekly Updates / Comments
Apache | Lead Originator | Apache | Outsourcing- scheduling, balancing, settlement, deal confirmations and measurement. | *$250,000 | 2001-06-06 | 25% | 2001-08-01 | Will be meeting with Roger Plank and Craig Clark on 6/6/01.
Crosstimbers |  | Crosstimbers | Outsourcing- scheduling, balancing, settlement, deal confirmations and measurement. | *$125,000 | 2001-05-22 | 25% | 2001-09-01 | Meeting set up for first part of June with Linda Roberts.

## Offshore +50 (hidden)
Deal Description Sheet - 7/9/01
Production Offshore
YTD P&L |  | 3715000
Project Name | Lead Originator | Counterparty | Description | Potential Valuation | Last Customer Contact | Probability | Expected Closing (Month/Year) | Weekly Updates / Comments

## Offshore -50 (hidden)
Deal Description Sheet - 7/9/01
Production Offshore
Project Name | Lead Originator | Counterparty | Description | Potential Valuation | Last Customer Contact | Probability | Expected Closing (Month/Year) | Weekly Updates / Comments
Freeport McMoRan | Kenn Loch | Freeport McMoRan | Volumetric Production payment on McMoRan Offshore Reserves. | 500000 | 2001-06-26 | 10% | 2001-08-01 | Working with Phil Ballard and KimYates of Enron Energy Capital Resources (ECR) on a VPP proposal. ECR recently provided McMoran Treasurer, Kathleen Quirk, a pitchbook outlining a high level proposal. ECR is in the process of setting up a meeting with Kathleen to discuss further.
Shallow-Water | Gary Bryan | VanKirk & Riles | Shallow-water used platform and gathering line sale & lease/financing business with small to mid-sized E&P independents. | 500000 | 2001-06-26 | 10% | 2001-09-01 | Working on HI 52 and WC 43 proposal for Gryphon Exploration. Craig Fox is upbeat on the HI 52 reserves. Gary Bryan and Kenn Loch are deal originators. Lisa Druzbik is structuring and pricing the deal. Non-binding proposal to go out in the next week.

## Compression +50
Deal Description Sheet - 7/24/01
Compression Services
Project Name | Lead Originator | Counterparty | Description | Potential Valuation | Last Customer Contact | Probability | Expected Closing (Month/Year) | Weekly Updates / Comments
Project Seebreeze Phase II A | Hilgert | Duke Field Services (El Paso-Matagorda Plant) | Duke upfront payment for connection of El Paso Matagorda plant to system. | $1.00 MM | 2001-06-01 | 75% | 2001-07-01 | Transaction closure upon delivery of El Paso contract. Duke proposal currently under consideration by El Paso.
Oakhill | Knippa (Hilgert) | Oakhill Pipeline LP | 7,000 HP retrofit. | 1.01 | 2001-07-12 | 75% | 2001-08-01 | Discussions with Alliant Energy (partnering company) to finalize terms and conditions. Meeting with Alliant on 7/30.
Carthage | Higgins (Hilgert) | Anadarko | 12,000 HP Compression Station | $500 M (early) | 2001-07-12 | 50% | 2001-09-01 | CA is forthcoming per Anadarko. Working on refined proposal. Technical meeting held on 7/13.
Stagecoach | Miles (Meyer) | Tennessee Gas Pipeline (EPG) | 14,000 HP expansion of Tennessee 300 line. | $0.98 MM | 2001-06-22 | 75% | 2001-10-01 | FERC certificate not accepted. EPG to re-file in August/September pending new open season for transport.
Nicor | Higgins (Hilgert) | Nicor | 22,000 - 72,000 HP replacement project. | $2.50 MM | 2001-07-11 | 50% | 2001-10-01 | Met with Nicor on 6/12 and laid out forward plan to finalize scope definition and deal structure requirements. Planning on submitting detailed proposal by 7/31. Working to schedule follow-up technical meeting. Coordinating with NICOR Regulatory to structure proposal.
Crestone | Miles (Hilgert) | Norther Border Pipeline | 5,000 - 15,000 HP greenfield for NBP expansion. | $500 M | 2001-07-23 | 50% | 2001-10-01 | Initial information presented to customer on 7/6/01. Model in development. Visiting site on 7/31. Definitive documents to follow.
JM Huber | Hilgert (Miles) | JM Huber | Producer asset/HP outsourcing deal. | $500 M | 2001-07-18 | 50% | 2001-10-01 | Gathering data and devloping proposal. Working with Crestone.
Kinder Morgan CO2 | Hilgert | Kinder Morgan | 34,000 HP | $500 M (early) | 2001-07-23 | 50% | 2001-10-01 | Developing strategy. Meeting with customer on 7/23. Working on Texas Power RFP w/ Mid-Marketing Origination.
Eastchester Phase II | Miles (Meyer) | Iroquois Gas Pipeline | 17,500 - 25,000 HP grass roots expansion. | $1.00 MM | 2001-07-19 | 50% | 2001-11-01 | Customer is waiting on FERC approval by the end of summer for two potential projects. FERC approval of either project will initiate deal with ECS.
Project Seebreeze Phase III | Hilgert | TBD | Final monetization of Enron position. | $3.00 MM | N/A | 50% | 2001-12-01 | Working market and awaiting initial Williams production. Will develop Information Memorandum for sale to appropriate counterparties in 4th Qtr.

## Compression -50 (hidden)
Deal Description Sheet - 7/24/01
Compression Services
Project Name | Lead Originator | Counterparty | Description | Potential Valuation | Last Customer Contact | Probability | Expected Closing (Month/Year) | Weekly Updates / Comments
Project Seebreeze Phase II B | Hilgert | TBD | Additional gas procurement into NGL system benefiting Enron net profit interest. | $3.00 MM | N/A | 25% | 2001-08-01 | Negotiating with counterparites for wellhead contracts.
Cross Timbers | Hilgert | Cross Timbers | 6,200 HP of Gathering Compression | $500 M (early) | 2001-07-16 | 25% | 2001-09-01 | Developing proposal. Meeting with client week of 7/23.
La Gloria | Higgins (Hilgert) | Duke Energy Field Services | 20,000 HP NGL processing plant retrofit. | $0.81 MM | 2001-07-06 | 25% | 2001-09-01 | Met with Duke on 6/6 and presented additional options. Gathering additional information for detailed proposal.Waiting on CA return.
Kinder Morgan New Caney | Knippa | Kinder Morgan New Caney | 13,000 HP | $500 M (early) | 2001-06-22 | 10% | 2001-09-01 | Waiting on RFP.
Red Cedar Gathering | Hilgert (Miles) | Red Cedar | 6,000 HP | $500 M (early) | 2001-07-10 | 10% | 2001-10-01 | Met with customer on 7/10. Developing strategy.
Citgo Lakemont P/L | Knippa | Citgo Lakemont P/L | Lake Charles 1,500 HP; Port Arthur 1,000 HP; Houston 1,000 HP | $500 M (early) | 2001-06-26 | 10% | 2001-11-01 | Developing strategy.
Unocal | Higgins (Meyer) | Unocal | 7,000 HP grass roots station. | $2.00 MM | 2001-06-25 | 25% | 2001-12-01 | Customer is reviewing proposal. Unocal recently received gas driven compression proposals and is in the process of doing comparative evaluation.
Southern Trails | Miles (Meyer) | Questar Pipeline Co. | 6,000 HP Beaumont Station | $0.50 MM | 2001-07-19 | 25% | 2001-12-01 | Met with customer on 6/13 to present proposal and scenarios. Electric tariff doubled on June 3rd, rendering this project an installation only with potential for a future energy deal.
Explorer P/L Expansion | Knippa | Explorer P/L | Explorer P/L expansion. | $500 M (early) | 2001-06-26 | 10% | 2001-12-01 | Developing strategy. Flowserve setting meeting. Working on power pricing & structure via EGM.
MCN Belle River Mills | Meyer | MCN / DTE | Storage facility upgrade and expansion 10,000 HP | $500 M (early) | 2001-07-12 | 10% | 2001-12-01 | Initial proposal sent 7/12/01.
TECO Eagle/Downing Stations | Meyer | TECO Eagle Station | Proposed HP to support proposed FP&L plant. 6,000 HP to 12,000 HP | $500 M (early) | 2001-07-09 | 10% | 2001-12-01 | HP addition predicated on Marcus Hooks (FP&L) plant. Initial proposal sent.
( ) = Denotes Backup/Oversight Role

## Storage +50
Deal Description Sheet - 7/24/01
Storage
YTD P&L |  | 375000
Project Name | Lead Originator | Counterparty | Description | Potential Valuation | Last Customer Contact | Probability | Expected Closing (Month/Year) | Weekly Updates / Comments
Big Red-1 | Bieniawski | Halliburton Energy Services | Origination credit from Wellhead Desk. Wellhead Desk would manage HES' 100-150,000 MMBtu of flowing supply. | 75 | 2001-07-11 | 50% | 2001-08-01 | Met with SVP. Forwarded CA and list of due diligence items.
Big Red-2 | Bieniawski | Halliburton Energy Services | Manage HES' commodity position derived from storage capacity assigned by Northern Natural as payment for HES services. | 500 | 2001-07-11 | 50% | 2001-08-01 | HES' wants to begin promoting product to its customers.
Blowfish | Rainer | Dow Chemical, OxyChem, or Texas Brine | Sale of 330-acre tract of land at Napoleonville salt dome, LA | 1500 | 2001-06-22 | 100% | 2001-09-01 | Texas Brine has verbally expressed interest in the land, meeting scheduled for 7/20/01. In process of obtaining bid or confirmation of interest from Dow.

## Storage -50 (hidden)
Deal Description Sheet - 7/24/01
Storage
Project Name | Lead Originator | Counterparty | Description | Potential Valuation | Last Customer Contact | Probability | Expected Closing (Month/Year) | Weekly Updates / Comments
| Vasquez | Western Hub Properties | Base gas financing at Lodi Storage Field (6.0 Bcf). Base gas financing at Atkinson Storage Field (4.5 Bcf). | 1500 | 2001-07-13 | 40% | 2001-09-01 | WHP is still in the process of sorting out its sale (of the company), we need to reach them again to find their interest when the sale is completed.
Big Bird-1 | Vasquez | Falcon Gas Storage | Base gas financing @ Worsham Steed Storage Field (8 Bcf). Base gas financing @ Hill Lake Storage Field (7.7 Bcf). | 1500 | 2001-07-06 | 35% | 2001-10-01 | Financing structure to finance additional base gas for their Hill Lake facility and to take current base gas as well as the new base gas as collateral. We are waiting to get firm contracts from the client. Total financing 7.7Bcf. Client has bridge financing offer from a bank for 3 Bcf, we are vying to get the full package when they refinance, they are still in the process of getting the contracts that will allow them to collateralize it.
| Vasquez | Columbia Gas | Base gas monetization | 1000 | 2001-05-16 | 40% | 2001-11-01 | Planning on new visit to present our monetization alternatives including the type of transaction and the type of risks involved as outlined by the lawyers we hired to provide support.
Cowboys | Vasquez | TXU | Base gas monetization | 1000 | 2001-07-10 | 35% | 2001-12-01 | Interested in setting up a CA to discuss numbers. TX PUC regulated. They just hired someone who will do "financial trading" on their storage (apparently someone from Enron), waiting for availability and go for a second visit.
| Bieniawski | Dominion | Base gas monetization | 2000 | 2001-07-12 | 30% | 2001-12-01 | Presented more detailed information regarding structure. Presented CA and list of due diligence items. DTI is currently going though some regulatory hearings but remain very interested in the structures.
| Bieniawski | Questar Regulated Services | Base gas monetization | 1000 | 2001-06-26 | 30% | 2002-02-01 | Have expressed interest pending results of regulatory investigation. In process of signing CA and letter of interest.
| Rainer | Montana Power | Base gas monetization | 1000 | 2001-06-27 | 30% | 2002-02-02 | Expecting their revisions of CA soon. Fielded initial questions about our data request for model, expecting initial data this week.