## Sheet1
Alamac Outstanding Issues
Issue | Resolution | Timing | Responsible Party
RAC Approval | Update model with new prices from coal desk, power desk (capacity), ReUse proposal, NOx prices. Submit to RAC for analysis and approval. | Approval by Jan 12 | Beach, Kroll
O&M Agreement | Contract sent to Jerry Campbell, Jerry coming to Houston week of Jan. 8 to negotiate terms and complete agreement | Contract complete by Jan 15 | Pagan, Beach, Kroll, Nemec
O&M Structure | Discuss with Jerry, Enron will consult with Jerry on setting up health plans, payroll and benefits packages. Discuss with Cogentrix extending employment through Jan. | Structure complete week of Jan 8, Jerry to begin operating Feb 1 | Kroll, Pagan, Cash, Melodick
Coal Handling, Ash Disposal | ReUse to send revised proposal Jan. 8, negotiate terms week of Jan 8 | Contract complete by Jan 15 | Beach, Kroll
Coal Contract | Meeting with Kevin McGowan and Tom McQuade to discuss options for coal supply, we have ability to have Cogentrix supply coal under their existing contract for an interim period (approx $75/ton or $3.00/mmBtu). We need to decide if we want to enter into a fixed price deal or an indexed-based contract. | Coal meeting Monday (Jan 8) 9:00. | Beach, Pagan, McGowan
CSX Transport Agreement | McQuade to negotiate with CSX | ?? | McQuade, Beach
Interconnection Agreement | CP&L to get results of Facilities Study week of Jan 8, Draft Interconnect and Operating Agreement sent week of Jan 8, costs to interconnect and maintain determined by Facilities Study. | Interim Interconnect Agreement by Feb 1, ability to sell to any third party by Apr 1 | Kroll
Interim Sale of Power | CP&L claims 2 - 3 months necessary to complete upgrades to telemetry systems at interconnection facilities. Interim sales possible if made to either CP&L or NCEMC on exclusive basis. CP&L pricing up bid on power, I will contact NCEMC this week for same. | Bid from CP&L week of Jan 8, expect same from NCEMC. | Kroll
Permits | Verifying transfer of permits, applying for additional permits needed for continued operation of facilities | Permit matrix complete week of Jan 8 | Rorschach, Van Hooser
EWG Certification | Application completed Jan 5, to be submitted week of Jan 8 (Van Hooser verifying we can apply for EWG Status before purchasing the facilities) | Week of Jan 8 | Van Hooser, Watkiss
Power Marketer Certification | Verifying whether or not facilities need Power Marketer Certification to sell power to affiliate EPMI or directly to CP&L | Week of Jan 8 | Van Hooser, Watkiss, Pagan
NOx, SO2 Credits | Emissions Desk pricing up a call option on NOx credits at $6,500/ton (plants need approx 100 additional credits to run 5 x 16 during summer). SO2 market very liquid, prices will be index based | Week of Jan 8 | Massey, Beach, Kroll
CPCN | Tom Chapman met with NCUC Staff on Jan 5 to confirm and coordinate the Interim CPCN needed to operate the facilities as merchant plants. I am waiting for his report and status update. | ?? | Chapman, Kroll