## J. Westenberger
# | Category | Finding | Action Item | Responsible Person | Target Date | Confirm Reviewer | Completion Date | Comments
PSM
115 | Operating Procedures | Rotating shafts on some equipment is exposed to accidental entry. | Insure that all rotating shaft guards are in place to prevent accidental entry. (Picture #10 ) | Jeff Westenberger | 2001-12-31 | Rick Suderman
59 | Operating Procedures | No Coupling alignment reports on all plants rotating equipment. | Assure that coupling alignments are performed to all plants rotating equipment as per vendor recommendations and frequencies. Assure this is tracked on MP2 or Maximo. | Jeff Westenberger | 2001-12-31 | Rick Suderman