## Sheet1
UNIT # | ASSIGNMENT/RESERVATION | COMMITMENT | FUTURE COMMITMENT | READY to SHIP DATE | UNIT LOCATION/ NOTES
PROBABILITY
1 | PESCO (West Coast) |  | 75% | 2000-07-08 | in-storage
2 | North Carolina |  | 75% | 2000-07-26 | in paint facility
3 | North Carolina |  | 75% | 2000-08-15 | finished testing moving to final paint facility
4 | PESCO (West Coast) |  | 75% | 2000-07-09 | in-storage
5 | PESCO (West Coast) |  | 75% | 2000-07-10 | in-storage
6 | PESCO (West Coast) |  | 75% | 2000-07-21 | in paint facility
7 | Florida |  | 10% | 2000-06-29 | in-storage
8 | Florida |  | 10% | 2000-06-30 | in-storage
9 | City of Austin | 100% |  | 2000-08-19 | on assembly line "D"
10 | City of Austin | 100% |  | 2000-09-01 | on assembly line "C"
11 | City of Austin | 100% |  | 2000-09-06 | on assembly line "B"
12 | City of Austin | 100% |  | 2000-09-14 | on assembly line "A"
13 | ESA |  | 75% | 2000-09-21 | on skid assembly line
14 | ESA |  | 75% | 2000-09-28 | on skid assembly line
15 | ESA |  | 75% | 2000-10-25 | on skid assembly line
16 | ESA |  | 75% | 2000-11-01 | on skid assembly line
17 | Florida |  | 10% | 2000-11-13 | in fabrication at sub-vendors
18 | Florida |  | 10% | 2000-11-20 | in fabrication at sub-vendors
19 | Florida |  | 10% | 2000-11-27 | in fabrication at sub-vendors
20 | Florida |  | 10% | 2000-12-10 | in fabrication at sub-vendors
21 | Las Vegas |  | 25% | 2001-01-05 | not started yet
22 | Las Vegas |  | 25% | 2001-01-12 | not started yet
23 | Las Vegas |  | 25% | 2001-01-20 | not started yet
24 | Las Vegas |  | 25% | 2001-03-13 | not started yet