## L. Campbell
# | Category | Finding | Action Item | Responsible Person | Target Date | Confirm Reviewer | Completion Date | Comments
PSM
21 | AIR GMP | Need a system for maintaining compliance with permit requirements. | Incorporate permit conditions requiring an action into the Maintenance Control System (MCS). | Larry Campbell | 2001-03-31 | Rick Suderman
29 | HAZARDOUS WASTE Regulation Condition | An assessment of cooling tower area found chromium contamination, but no plan for remediation has been developed. | Determine vertical and lateral extent of chromium contamination. | Larry Campbell | 2001-06-30 | Rick Suderman
30 | HAZARDOUS WASTE Regulation Condition | An assessment of the wash rack area found elevated levels of lead, barium, chromium, copper, and mercury. | Determine extent of metals contamination. | Larry Campbell | 2001-06-30 | Rick Suderman
31 | HAZARDOUS WASTE Regulation Condition | An assessment of the propane compressor area found elevated levels of lead and chromium. | Determine extent of metals contamination. | Larry Campbell | 2001-06-30 | Rick Suderman
32 | HAZARDOUS WASTE Regulation Condition | An assessment of the propane compressor area found elevated levels of benzene. | Determine extent of benzene contamination. | Larry Campbell | 2001-06-30 | Rick Suderman