## Sheet1
Support Type | Deal Name | Responsible Person | Impact ($MM) | Background/Key Issues | Updated | Strategies/Comments/Next Actions
Deal Support | Interconnection with Georgia Power (Athens Development Company) | Susan Lindberg |  | Negotiate interconnection agreement between Georgia Power and Athens Development for 564 MW combined cycle plant. | 2001-10-05 | Deadline for executing agreement is 9/20/01. If no agreement is reached, unexecuted agreement will be filed with FERC.
Deal Support | Interconnection with WAPA | Susan Lindberg |  | Provide information on regulatory precedent. | 2001-10-05 | Interconnection study has been requested; next step would be to negotiate interconnection agreement if indicated.
Deal Support | Interconnection with FPL (Midway Project). | Susan Lindberg |  | Negotiate interconnection agreement between Enron Midway Development Company and FPL. | 2001-10-05 | Deadline for executing agreement has been extended. If no agreement is reached, unexecuted agreement will be filed with FERC.
Deal Support | Doyle I LLC Sale | Susan Lindberg |  | Obtain FERC approval for disposition of assets. | 2001-10-05 | Filing Sec 203 application Oct 12, 2001. Follow application through FERC to expedite approvals.
Deal Support | Interconnection with Entergy | Susan Lindberg |  | Negotiate interconnection study agreement | 2001-10-05 | Focus on Notice to Proceed concept with finalized Interconnection agreement.
Advocacy | FERC - Proposed Rulemaking on Generation Interconnection Standards | Susan Lindberg |  | FERC has issued Discussion paper that recommended short-term Rulemaking standardizing interconnection procedures and long-term Rulemaking on cost assignment issues. | 2001-10-05 | Support FERC through EPSA.
Advocacy | FERC - NOPR on Public Utility Filing Requirements | Susan Lindberg |  | Assist ENA Legal in developing Enron's comments on NOPR | 2001-10-05 | File comments with EPSA and as Enron to FERC. Key issues involve what transactions are included (e.g., bookouts) and timeliness.