## Sun Dec 10 to 17
Week summary (Dec 10-17)
Category | Description | Total | Breakdown of Cat 1
1 | Human Errors |  | Process in place but not followed
2 | IT Hardware problems |  | Officialized on time but needed recalc
3 | IT Software Problems |  | Book not officialized
4 | Miscellaneous |  | No process in place
5 | Uncontrollable |  | Total | 0
| Total | 0
Breakdown of Cat 2
Computer breakdown
|  |  | Other | 0
|  |  | Total | 0
Breakdown of Cat 3
Correct inputs, incorrect outputs
Slow feeds
Books shown as officialized in ERMS, but not RiskTrac
Other
|  |  | Total | 0
Breakdown of Cat 4
|  |  | Credit interface | 0
|  |  | Other | 0
|  |  | Total | 0

## Sum Nov 22 to 28
Week summary (Nov 22-28)
Cat. | Description | Total | Breakdown of Cat 1
1 | Human Errors | 4 | Process in place but not followed | 3
2 | IT Hardware problems |  | Officialized on time but needed recalc
3 | IT Software Problems |  | Book not officialized | 1
4 | Miscellaneous | 4 | No process in place
5 | Uncontrollable |  | Total | 4
| Total | 8
Breakdown of Cat 2
Computer breakdown
|  |  | Other | 0
|  |  | Total | 0
Breakdown of Cat 3
Correct inputs, incorrect outputs
|  |  | Slow feeds | 2
|  |  | Books shown as officialized in ERMS, but not RiskTrac | 2
Other
|  |  | Total | 4
Breakdown of Cat 4
|  |  | Credit interface | 0
|  |  | Other | 0
|  |  | Total | 0

## Sum Nov 15 to 21
Week summary (Nov 17-21)
Cat. | Description | Total | Breakdown of Cat 1
1 | Human Errors | 16 | Process in place but not followed | 3
2 | IT Hardware problems |  | Spreadsheet had illegal character
3 | IT Software Problems | 12 | Book not officialized | 2
4 | Miscellaneous |  | No process in place
5 | Uncontrollable |  | Other | 11
| Total | 28 | Total | 16
Breakdown of Cat 2
Computer breakdown
|  |  | Other | 0
|  |  | Total | 0
Breakdown of Cat 3
|  |  | Correct inputs, incorrect outputs | 1
|  |  | Slow feeds | 5
|  |  | Books shown as officialized in ERMS, but not RiskTrac | 1
|  |  | Problems with new feed process (UK) | 2
|  |  | Other | 3
|  |  | Total | 12
Breakdown of Cat 4
|  |  | Credit interface | 0
|  |  | Other | 0
|  |  | Total | 0

## Sum Nov 8 to 14
Week summary (Nov 9-14)
Cat. | Description | Total | Breakdown of Cat 1
1 | Human Errors | 3 | Process in place but not followed | 1
2 | IT Hardware problems | 1 | Spreadsheet had illegal character | 2
3 | IT Software Problems | 6 | Book not officialized | 0
4 | Miscellaneous | 0 | No process in place | 0
5 | Uncontrollable | 0 | Total | 3
| Total | 10
Breakdown of Cat 2
|  |  | Computer breakdown | 1
|  |  | Other | 0
|  |  | Total | 1
Breakdown of Cat 3
|  |  | Correct inputs, incorrect outputs | 1
|  |  | Slow feeds | 2
|  |  | Books shown as officialized in ERMS, but not RiskTrac | 1
|  |  | Other | 2
|  |  | Total | 6
Breakdown of Cat 4
|  |  | Credit interface | 0
|  |  | Other | 0
|  |  | Total | 0

## Sum Nov 1 to 7
Week summary (Nov 1-7)
Cat. | Description | Total | Breakdown of Cat 1
1 | Human Errors | 10 | Book not officialized | 7
2 | IT Hardware problems | 0 | Other | 3
3 | IT Software Problems | 19 | Total | 10
4 | Miscellaneous | 4
5 | Uncontrollable | 0
| Total | 33 | Breakdown of Cat 3
|  |  | System problems | 19
|  |  | Other | 0
|  |  | Total | 19
Breakdown of Cat 4
|  |  | Credit interface | 1
|  |  | Other | 3
|  |  | Total | 4

## Daily log - date
COB Date | Reported by: | Book | Commodity/office | Desk/BA | Office/ Trader | Responsibility for to do | Class | Problem | Long description/To do's | Var Rerun? | Credit affected? | Impact cash flows? | # of open to do's
2000-12-12 | Risk Controls | DABHOL-HO-AFF-IDX | Heating Oil/ Global Markets | Pat Stafford |  | Risk Mgmt | 1 | ba forgot to officialize. As book is an affiliate book it does not impact VAR, Credit or other Departments. | Set up processes | no | no | no | 1
2000-12-12 | Risk Controls | GAS-EXEC-BAS | GAS |  |  | IT/RM | 3 | book was officialized and posted, however not captured by RMS. | Resolve problem | no | yes | yes | 1
2000-12-12 | Risk Controls | GAS-EXEC-GDL | GAS |  |  | IT/RM | 3 | book was officialized and posted, however not captured by RMS. | Resolve problem | no | yes | yes | 1
2000-12-12 | Risk Controls | UKGASGSA1 | UK GAS |  |  | IT/RM | 3 | The spreadsheet Posted at 4:51, but did not receive Post ID, which caused it to be picked up by query. | Set up alternate process | no | no | no | 1
2000-12-11 | UK RAC | several Enron Europe books | UK |  |  | IT/UK RM | 3 | files came in late, books could not be seen in RisktRAC, book ID for one book was changed and would not work | Fix problems | yes | yes | yes | several
2000-12-11 | Risk Controls | FT-WEST-OPT-BAS | US GAS |  |  | Risk mgmt | 1 | ba officialized book but did not calc it (normal BA was out). | Set up processes | yes | yes | yes | 1
2000-12-11 | Risk Controls | NG-INDEX-CAND-IDX | Cand gas |  |  | Risk mgmt | 1 | ba forgot | Set up processes | yes | yes | yes | 1
2000-12-08 | Risk Controls | EU-PWR-BILATERAL | UK |  |  | IT | 3 | There is a problem with the feed, RisktRAC said it was being updated but was not | Database admin in US needs to fix | yes | yes | yes | 1
2000-12-08 | Risk Controls | EU-PWR-POOLS | UK |  |  | IT | 3 | Came in at 7:10. MTM failed over the weekend, curve did not load into valuation engine |  | yes | yes | yes | 1
2000-12-08 | Risk Controls | FT-EOL-TEXAS-PRC | US GAS | Denver Plachy |  | Risk mgmt | 1 | BA forgot to officialize, used portcalc instead of metacalc as thought issue from Thurs was not resolved. | Why was this not caught in mini bench? To update process. | yes | yes | yes | 1
2000-12-08 | Risk Controls | FT-NORTHWEST-IDX | US GAS |  |  | IT | 3 | This book has nothing in it but was officialized and had a post id. This book was not picked up by RisktRAC. | Why not caught in mini bench? | no | no | no | 1
2000-12-08 | UK RAC | MG METALS | UK (primarily NY concentrates) |  |  | IT | 3 | Late, primarily due to an issue with Aquarius. |  | yes | yes | yes | 1
2000-12-07 | IT | NG-PRICE-GDL | GAS |  |  | IT | 3 | Book was official but did not have a post ID and did not show up on Risk Controls reporting | Figure out what is wrong | yes | yes | yes | 1
2000-12-07 | Risk Controls | EU-PWR-POOLS | European power |  |  | IT | 3 | Feeds slow so did not make it in by 6am. | change sequential to parallel processing | yes | yes | yes | 1
2000-12-06 | Risk Controls | EES-BOOKS-ENPOWER | EES |  |  | IT | 3 | Metacalc was down so ba's had to use port calc. They were not used to doing this and officialized the wrong day. They had to reofficialized | Fix Metacalc (done) | yes | yes | yes | 0
2000-12-06 | Risk Controls | ST-SPINDLETOP-BAS | US GAS |  |  | IT | 3 | Metacalc was down so ba's had to use port calc. They were not used to doing this and forgot to officialize these small storage books (small so no VAR to be rerun) | Fix Metacalc (done) | no | no | no | 0
2000-12-06 | Risk Controls | ST-SPINDLETOP-IDX | US GAS |  |  | IT | 3 | Metacalc was down so ba's had to use port calc. They were not used to doing this and forgot to officialize these small storage books (small so no VAR to be rerun) | Fix Metacalc (done) | no | no | no | 0
2000-12-06 | Risk Controls | ST-SPINDLETOP-PRC | US GAS |  |  | IT | 3 | Metacalc was down so ba's had to use port calc. They were not used to doing this and forgot to officialize these small storage books (small so no VAR to be rerun) | Fix Metacalc (done) | no | no | no | 0
2000-12-06 | Risk Mgmt - UK | UK POWER | UK |  |  | IT | 3 | UK power feed failed | Fix feed (done) | yes | yes | yes | 0
2000-12-06 | Risk Mgmt - US gas | Shankman Executive book | US GAS |  |  | risk controls/ risk mgmt | 1 | This intercompany book had a 3rd party pos with Smith Barney. The book should have been officialized but wasn't. It did not shw up on the late officialization list. | Start officializing, add to list (done) | no | yes | no | 0
2000-12-06 | RAC Credit |  |  |  |  | IT | 3 | ERMS load in credit failed | ensure this does not happen again (done) | no | yes | no | 0
2000-12-05 | Risk Controls | FT-CAND-PWR-PRC | Canada power | Brian Kristjansen | Bill Greenizan | CA RM | 1 | BA sent officialized spreadsheet but did not send it to Houston to upload. | expidite canada getting access to RisktRAC to upload things themselves, ensure ba's telephone each other to ensure e-mail has been sent. | yes | yes | yes | 1
2000-12-05 | RAC | John Arnold's book | US GAS |  | John Arnold | Risk management | 1 | Issue with interdesk deal - calc times did not match and only one side got picked up | Ensure processes are in place so this would be caught. | yes | yes | yes | 1
2000-12-05 | IT | UK power | UK |  |  | UK RM/US IT | 3 | Book officialized on time, but feeds did not make 6am cut-off | Work on feed speed. | yes | yes | yes | 1
2000-12-04 | RAC | EES | EES |  |  | EES Risk Mgmt | 1 | cals missed a position and had to be recalced and officialized in the afternoon of the 5th | Process needs to be put in place to ensure all trades are captured | yes | yes | yes | 1
2000-12-04 | IT | UK power | UK |  |  | US IT | 3 | Book officialized on time but feeds were slow. | Feeds are sequential and they need to be changed to be parallel. | yes | yes | yes | 1
2000-12-01 | Risk Controls | EI-ARG-GAS-PRC | Argentina gas | Sarah Smith | Rodolpo Freyre | Risk management | 1 | BA forgot to officialize | Ensure risk management has process in place to ensure that this cant happen. | yes | yes | yes | 1
2000-12-01 | Risk Controls | FT-CAND-PWR-PRC | Canada power | Brian Kristjansen | Bill Greenizan | CA RM | 1 | BA sent officialized spreadsheet to Houston to upload but person in Houston was out. | expidite canada getting access to RisktRAC to upload things themselves | yes | yes | yes | 1
2000-12-01 | IT | UK power | UK |  |  |  | 3 | Book officialized on time, but feeds did not make 6am cut-off | Work on feed speed. | yes | yes | yes | 1
2000-12-01 | UK RAC | Bilateral book in Continental power | UK |  |  |  | ? | Book showed up as being officialized numerous times | ?
2000-11-30 | IT | Continental Power | UK |  |  | UK | 1 | The fx rate was X1000 - P&L was off and book had to be reofficialized. | Figure out why, perform necessary process changes. | yes | yes | yes | 1
2000-11-30 | IT | UK power | UK |  |  | US IT | 3 | Book officialized on time but feeds were slow. | Feeds are sequential and they need to be changed to be parallel. | yes | yes | yes | 1
2000-11-29 | Risk Controls | Continental Power | UK |  |  | US IT | 3 | Book officialized on time but feeds were slow. Book came in at 7:33. | Feeds are sequential and they need to be changed to be parallel. | yes | yes | yes | 1
Total errors for week |  | 8
2000-11-28 | Risk Controls | NG-LTX-GDL | Gas | Robin Rodrigue | John Arnold | Risk Management | 1 | Book officialized on time, but positions had to becalced and reofficialized. Caught on bench this morning. | System enhancements where book admin's do not have to calc same book 4 & 5 times (different positions needed during due to index settlement bid-week for VAR, trader, head trader). | yes | yes | yes | 1
2000-11-28 | Risk Controls | NG-PRICE-GDL | Gas | Robin Rodrigue | John Arnold | Risk Management | 1 | Book officialized on time, but positions had to becalced and reofficialized. Caught on bench this morning. | System enhancements where book admin's do not have to calc same book 4 & 5 times (different positions needed during due to index settlement bid-week for VAR, trader, head trader). | yes | yes | yes | 1
2000-11-28 | IT | Nordic Power | UK |  |  |  | 3 | Book officialized on time, but feeds did not make 6am cut-off | Work on feed speed. | yes | yes | yes | 1
2000-11-27 | IT | UK power | UK |  |  |  | 3 | Feeds did not make the 6am cut off |  | yes | yes | yes | 1
2000-11-22 | Risk Controls (not to be included on summary) | DUB-ERMS-XL-PRC | EES | Monica Hwang |  | EES Risk Mgmt | 1 | Price book not included on spreadsheet, therefore had to be downloaded after the VAR run. | Discuss with BA | yes | yes | yes | 1
2000-11-22 | UK RAC | UK Gas | UK |  |  |  | 1 | BA entered deal incorrectly and book needed to be recalced. | Discuss with BA | yes | yes | yes | 1
2000-11-22 | Risk Controls | PLAST-C2-HEDGE-PRC | Global Products |  |  |  | 3 | RisktRAC did not capture the correct positions (notional) | Virendra Patel reofficialized the book and the correct positions were captured by RisktRAC. The BA calced and officialized as required. | yes | yes | no | 1
2000-11-22 | Risk Controls | PLAST-C3-HEDGE-PRC | Global Products |  |  |  | 3 | RisktRAC did not capture the correct positions (notional) | Virendra Patel reofficialized the book and the correct positions were captured by RisktRAC. The BA calced and officialized as required. | yes | yes | no | 1
2000-11-22 | Risk Controls | RLL-XL-PRC | Global Products |  |  |  | 1 | Spreadsheet was not fully updated to include positions to 2003 | Mark Fondren made the correction on the spreadsheet, which was reofficialized and downloaded to RisktRAC | yes | yes | yes | 1
Total errors for week |  | 28
2000-11-21 | Risk Controls | EPMI-ST-CA-PRC | West power | Monica Lande/Valarie Sabo/Fran Chang | Jeff Richter |  | 1 | Enpower issue - ba did officialize, but desk did not show up for Risk Controls. | Sanjay Gupta, Burton McIntyre and Virendra Patel are working on the problem. | yes | yes | yes | 1
2000-11-21 | Risk Controls | EPMI-ST-NW-PRC | West power | Monica Lande/Valarie Sabo/Fran Chang | Sean Crandall |  | 1 | Enpower issue - ba did officialize, but desk did not show up for Risk Controls. | Sanjay Gupta, Burton McIntyre and Virendra Patel are working on the problem. | yes | yes | yes | 1
2000-11-21 | Risk Controls | EPMI-ST-PLT-PRC | West power | Monica Lande/Valarie Sabo/Fran Chang | Tim Belden |  | 1 | Enpower issue - ba did officialize, but desk did not show up for Risk Controls. | Sanjay Gupta, Burton McIntyre and Virendra Patel are working on the problem. | yes | yes | yes | 1
2000-11-21 | Risk Controls | EPMI-ST-SW-PRC | West power | Monica Lande/Valarie Sabo/Fran Chang | Tom Alonso/Mark Fischer |  | 1 | Enpower issue - ba did officialize, but desk did not show up for Risk Controls. | Sanjay Gupta, Burton McIntyre and Virendra Patel are working on the problem. | yes | yes | yes | 1
2000-11-21 | Risk Controls | FT-CAND-PWR-PRC | US GAS | ? | ? | Canada | 1 | The Canadian gas and power books are officialized and then e-mailed to the US gas desk who is responsible for uploading them. This spreadsheet did not get fully uploaded. | Move process to Canada | yes | yes | yes | 1
2000-11-21 | UK RAC | UK & Continental Gas | UK |  |  |  | 3 | reval did not work properly | ? | yes | yes | yes | ?
2000-11-21 | UK RAC | Nordic Power | UK |  |  |  | 3 | Feeds were slow and did not make the 6am run. | Work on feed speed | yes | yes | yes | ?
2000-11-21 | UK RAC | UK power | UK |  |  |  | 3 | Officialization done on time, but the feeds, which worked in the test environment, do not work in the production environment. | ? | yes | yes | yes | ?
2000-11-20 | Risk Controls | FT-CAND-PWR-PRC | Canada power | Brian Kristjansen | Bill Greenizan | US GAS | 1 | The Canadian gas and power books are officialized and then e-mailed to the US gas desk who is responsible for uploading them. This spreadsheet did not get fully uploaded. | Task force needs to develop process to ensure all books have been officialized and commodity risk management needs to implement it | yes | yes | yes | 1
2000-11-20 | Risk Controls | INTRA-MKT4-GDL | US GAS |  |  | UK Risk Mgmt | 3 | BA officialized book but it did not resolve to a book name | IT to determine what problem is. | yes | yes | yes | 1
2000-11-20 | Risk Controls | UK-COAL-EURO-PRC | COAL |  |  | US IT | 3 | it appears the Meta Calc was marked official. However, the translation to ERMS did not include this book. | Jeremy said sometimes Port Calc can lock a particular post id and someone can do this. Therefore, MetaCalc can not officialize. | yes | yes | yes | 1
2000-11-20 | UK RAC | European Power | UK |  |  | UK Risk Mgmt/IT | 3 | The Portcalc valuation failed 4 X as a result of IT problems and resultted in missing the deadline. | Work on feed speed - since feed is consistently taking longer, should deadline to submit feed be earlier? | yes | yes | yes | 1
2000-11-20 | UK RAC | Nordic Power | UK |  |  | UK Risk Mgmt/IT | 3 | Feeds were not in by 6am cutoff time, but book was officialized before deadline (11am London time) | Work on feed speed - since feed is consistently taking longer, should deadline to submit feed be earlier? | yes | yes | yes | 1
2000-11-20 | UK RAC | UK Power | UK |  |  | UK Risk Mgmt | 1 | On the UK power book there was a (GBP 30) mil topside adjustment which does not feed into credit. The GBP 30 mil is due to PD deal E000535 peer ID 41957 being valued in EnPower when it was supposed to be excluded from the MTM. Officialization was done on time. | Determine how to eliminate top side adjustments | yes | yes | yes | 1
2000-11-20 | UK RAC | UK Power | UK |  |  | UK Risk Mgmt | 1 | BA forgot to officialize | Task force needs to develop process to ensure all books have been officialized and commodity risk management needs to implement it | yes | yes | yes | 1
2000-11-17 | Risk Controls | FT-CAND-EGSC-BC-PRC | Canada gas | Nicole Laporte | John Disturnal | US GAS | 1 | The Canadian gas and power books are officialized and then e-mailed to the US gas desk who is responsible for uploading them. This spreadsheet did not get fully uploaded. | Task force needs to develop process to ensure all books have been officialized and commodity risk management needs to implement it | yes | yes | yes | 1
2000-11-17 | Risk Controls | OIL-NG-HDG-CAB-GDL | Gas | Kori Liobl | John Lavorato | NA | 1 | BA forgot to officialize (JL's book which all positions are done with desk so no credit implications) | Task force needs to develop process to ensure all books have been officialized and commodity risk management needs to implement it | yes | no | yes | 1
2000-11-17 | Risk Controls | PLANT-EP-BOOKS | Power | NA |  | Chris Abel | 3 | Why did this book show up on the risktrac list? | Determine why showed up on list | yes | yes | yes | 1
2000-11-17 | UK RAC | Power | Power 99 | NA | NA | UK IT | 3 | Power 99 failed - enpower will be live tomorrow to replace power 99 | nothing | yes | yes | yes | 0
2000-11-16 | Risk Controls | EPMI-LT-NW-EXT | Power | Mike Swerzbin | Monica Lande/Valarie Sabo/Fran Chang | task force | 1 | Enpower issue - ba did officialize, but commodity codes did not show up. | Per Sanjay Gupta, he could not diagnose the problem. He will investigate it further if the problem recurs in the near future | yes | yes | yes | 1
2000-11-16 | Risk Controls | EPMI-LT-SW-EXT | Power | Matt Motley | Monica Lande/Valarie Sabo/Fran Chang | task force | 1 | Enpower issue - ba did officialize, but commodity codes did not show up. | Per Sanjay Gupta, he could not diagnose the problem. He will investigate it further if the problem recurs in the near future | yes | yes | yes | 1
2000-11-16 | Risk Controls | EPMI-ST-SW-EXT | Power | Tom Alonso/Mark Fischer | Monica Lande/Valarie Sabo/Fran Chang | task force | 1 | Enpower issue - ba did officialize, but commodity codes did not show up. | Per Sanjay Gupta, he could not diagnose the problem. He will investigate it further if the problem recurs in the near future | yes | yes | yes | 1
2000-11-16 | Risk Controls | PLANT-EP-BOOKS (risktrac book name) | Power |  |  | task force | 1 | Enpower issue - ba did officialize, but commodity codes did not show up. | ? | yes | yes | yes | 1
2000-11-16 | IT | All but metals and cont. power | UK |  |  | IT | 3 | Feeds were not in by 6am cutoff time. | Work on feed speed | yes | yes | yes | 1
2000-11-15 | Risk Controls | EBS - bandwidth exotic spreadsheet | EBS - bandwidth | Gary Stadler |  | Risk management | 1 | There was a new spreadsheet format rolled out and the new format does not allow certain things that the old format did (ie deals now need to be in the appropriate sequence, counterparty errors). EBS was not informed of the switch to new feeds | IT and risk management to determine appropriate format of spreadsheets. Also this did not come out on Risk Controls error log. | yes | yes | yes | 0
2000-11-15 | Risk Controls | Advertising exotic spreadsheet | Advertising | Gary Stadler |  | Risk management | 1 | There was a new spreadsheet format rolled out and the new format does not allow certain things that the old format did (ie deals now need to be in the appropriate sequence, counterparty errors). EBS was not informed of the switch to new feeds | IT and risk management to determine appropriate format of spreadsheets. Also this did not come out on Risk Controls error log. | yes | yes | yes | 0
2000-11-15 | RAC | several power books (previously accrual) | Power | Jenny Lathem |  | Risk mgmt/ risk controls | 3 | changes made to RiskTrac to move two gas books from accrual to MTM were not initially effective | Figure out why not caught on morn. Report, figure out what the problem was with the change | yes | yes | yes | 2
2000-11-15 | IT | several UK books | several |  |  | IT | 3 | UK Gas & metals not started, UK power, in process | Feeds slow or not started | yes | yes | yes | 1
Total errors for week |  | 10
2000-11-14 | UK RAC | Continental Power | UK |  |  | UK IT | 3 | The book calcs came across incorrectly 2X. | IT to figure out why, fix problem. | yes | yes | no | 0
2000-11-14 | IT | All but UK GAS and Continental GAS | UK |  |  |  | 3 | Not in on time (6am) - feed coming across, but take a long time. | IT working on change to feeds | yes | yes | yes | 0
2000-11-14 | Risk Controls | UK-COAL-BUNK-PRC | Coal | Virginia Hill |  | Risk Controls/ IT | 1 | The book was changed in RisTrac but not ERMS so the attributes did not match. | Risk Contols need to get ERMS and RiskTrac matched. | yes | no | no | 0 (done)
2000-11-10 | Risk Controls | FT-NW-XL-OPT-BAS | US Gas | Carol Frank (consolidation level person is Rahmaan Mongozi) | Frank Ermis | IT | 1 | Spreadsheets had 98 contracts on them (however net contracts of 2 only). The gas benchmark person (gas consolidation group) was not able to upload these spreadsheets. They only know about this the next day. This type of thing happens when there is something in the spreadsheet that shouldn't be (an extra comma etc). | Discussed with Ramesh - until the roll out happens (due to happen in the next couple weeks) there is no way to change this. The BA's need to be extremely accurate and precise when dealing with the current spreadsheets. | no (too small) | no (too small) | no (too small) | 0
2000-11-10 | Risk Controls | FT-NW-XL-OPT-PRC | US Gas | Carol Frank (consolidation level person is Rahmaan Mongozi) | Frank Ermis |  | 1 | Spreadsheets had 98 contracts on them (however net contracts of 2 only). The gas benchmark person (gas consolidation group) was not able to upload these spreadsheets. They only know about this the next day. This type of thing happens when there is something in the spreadsheet that shouldn't be (an extra comma etc). | Discussed with Ramesh - until the roll out happens (due to happen in the next couple weeks) there is no way to change this. The BA's need to be extremely accurate and precise when dealing with the current spreadsheets. | no (too small) | no (too small) | no (too small) | 0
2000-11-09 | IT | Nordic power | London |  |  | London Risk | 3 | Nordic Power was not in before 6am. | New feeds should clear this issue (update 11/13 - new gas feed halted, concentrating on Enpower. Much improved - 95% of Enpower tieing out). | yes | yes | yes | 0
2000-11-09 | Oliver Gaylard (RAC) | London test feeds into RiskTrac | UK, Continental Gas |  |  | London Risk | 3 | The vol curve goes to 2002 but positions go to 2005. Curve needs to be extended. Vol curves are being incorrectly loaded into the spreadsheet feeds. | 1) Extend vol curves, 2) roll volumes correctly (according to front month) | yes | yes | ? | 0 (done)
2000-11-09 | Oliver Gaylard (RAC) | London test feeds into RiskTrac | UK, Continental Gas |  |  | IT | 3 | The test feeds did not all work properly (production feed data wrong). | IT to work on obtaining proper production feeds. | ? | ? | ? | 1
2000-11-09 | Risk Controls | FINANCIAL-AFF-PRC (ERMS) | FX/INTEREST RATES | Clara Carington | Pushcar Shahi | IT | 3 | Books were shown as officialized to FX/Int rate group, but did not show as officialized to Risk Controls | These books are duplicates of the Infinity books and are used only to get information to the settlements department. Infinity feeds VAR, Credit, and cash flows. These books are only officialized because ERMS requires them to be. To do's - 1) check to ensure that no duplicate information is coming in from Infinity and ERMS (as these are usually officialized) - checked no duplicate info, 2) determine if there is a way that these books do not have to be officialized (to save system resources) - per Ramesh server resource not an issue for these books, and 3) determine why this problem happened and if it could happen to other ERMS books that are required to be officialized - could be attributes don't translate or 1 post id gives 2 books or 1 book gives 2 post id's | no | no | no | 0 (done)
2000-11-09 | Risk Controls | FINANCIAL-EM-PRC (ERMS) | FX/INTEREST RATES | Clara Carington | Pushcar Shahi | IT
2000-11-09 | Risk Controls | FINANCIAL-PROP-PRC (ERMS) | FX/INTEREST RATES | Clara Carington | Pushcar Shahi | IT
2000-11-09 | Risk Controls | FINANCIAL-TN10-PRC (ERMS) | FX/INTEREST RATES | Clara Carington | Pushcar Shahi | IT
2000-11-09 | Risk Controls | FINANCIAL-TN5-PRC (ERMS) | FX/INTEREST RATES | Clara Carington | Pushcar Shahi | IT
2000-11-08 | Risk Controls | EES-EST-FWD-XL-PRC | EES | Jerald Surface | Charles Decker & Suneet Shorma | IT (has been fixed) | 2 | problem with upload of spreadsheets (Burton’s computer was being fixed and the fix destroyed some upload capability) | Get Burton's computer fixed, process needs to be changed: spreadsheets to upload to a file server | yes | yes | no | 1
2000-11-08 | Risk Controls | EES-WST-FWD-XL-PRC | EES | Jerald Surface | Jubran Whallon & Neil Bresnan | IT (has been fixed)
2000-11-08 | Risk Controls | EI-ARG-PWR-IDX | Argentina- power | Sarah Smith | Julian Poole | IT (has been fixed)
2000-11-08 | Risk Controls | EI-ARG-PWR-PRC | Argentina - power | Sarah Smith | Julian Poole | IT (has been fixed)
2000-11-08 | Risk Controls | EI-BRAZIL-PWR-PRC | Brazil - power | Sarah Smith | Remi Collonges | IT (has been fixed)
2000-11-08 | Risk Controls | EI-SC-GASLX-PRC | Argentina - gas | Sarah Smith | Roldofo Freyre | IT (has been fixed)
2000-11-08 | Risk Controls | EI-SC-XL-PRC | Argentina - power | Sarah Smith | Fredrico Cerisoli | IT (has been fixed)
2000-11-08 | Risk Controls | MG-AGRI-COCOA-PRC | Metals | Andrew Cornfield | Ed Dablin | IT (has been fixed)
Total errors for week |  | 33
2000-11-07 | Risk Controls |  | All | US | Houston | Credit | 4 | Credit issue | Need to check to make sure daily update from GCP to test is being completed so CAS and RisktRAC will be OK.
2000-11-07 | Risk Controls |  | Gas | UK | London | IT/ Energy Ops | 3 | system problems | Due to 11/6 problems with UK Gas the data will be officialized today and sent across but will not be officialized until Saturday 11/11/00.
2000-11-07 | Risk Controls |  | Liquids | US | Houston | Energy Ops | 1 | incorrect data | Curve not loaded correctly.
2000-11-07 | Risk Controls |  | Liquids | UK | London | Energy Ops | 4 | Cash Flow Issues | J. Block data did not come across correctly. Clara is discussing with London. Note: Book has been changed to remove "take or pay" so cash flow would look different.
2000-11-07 | Risk Controls |  | Power | UK | London | IT/ Energy Ops | 3 | system problems | Books officialized by 5 AM but slow feed.
2000-11-06 | Risk Controls |  | Gas | UK | London | IT/ Energy Ops | 3 | system problems | MTM fell over so books re-run and curves were wrong. Problem on SQL server. No valuation 11/6 DPR had to be an estimate.
2000-11-06 | Risk Controls |  | Gas | UK | London | IT/ Energy Ops | 3 | system problems | Received London's 11/2 data again due to data in London was corrupted and London had to restart system.
2000-11-06 | Risk Controls |  | Liquids | US | Houston | Energy Ops | 1 | incorrect data | Rerun Liquids Var because PHYOil2-Index and PhyOil-Index (crude) book was in the ERMS but should not have been due to position was also captured in the RLL_Epx_Pos spreadsheet. Var needed to be re-run because numbers in credit are wrong and will need to be re-run
2000-11-06 | Risk Controls |  | Power | UK | London | IT/ Energy Ops | 3 | system problems | Books officialized by 3 AM but slow feed so books late coming across. Curves came in but no positions.
2000-11-06 | Risk Controls |  | Power | UK Nordic | London | IT/ Energy Ops | 3 | system problems | Macros and processors crashed so position files late.
2000-11-03 | IT |  | All | UK | London | IT/ Energy Ops | 3 | system problems | Feed problem all books officialized but not feed across.
2000-11-03 | IT |  | Liquids | UK | London | Energy Ops | 1 | curve pub code not tyed correctly | Liquids Var needed rerun because curve was not loaded correctly | yes
2000-11-03 | Risk Controls |  | Power | Canadian | Calgary | Energy Ops | 1 | book not officialized | Canada-Pwrwest-Prc book not officialized | yes
2000-11-02 | Risk Controls |  | Gas | US | Houston | Energy Ops | 1 | book not officialized | FT-CAND-EGSC-A-Prc book not officialized
2000-11-02 | Risk Controls |  | Gas | US | Houston | Energy Ops | 1 | book not officialized | FT-CAND-EGSC-A-Prc book not officialized
2000-11-02 | Risk Controls |  | Gas | UK | London | IT/ Energy Ops | 3 | system problems | data not in because feed is slow
2000-11-02 | Risk Controls | DABHOL-HO-AFF-IDX | Liquids | UK | London | Energy Ops | 1 | book not officialized | Affiliate book - BA did not know that book should be officialized
2000-11-02 | Risk Controls |  | merchant | US | Houston | IT/ Energy Ops | 3 | system problems | problem with Reuters Issues and the feed
2000-11-02 | Risk Controls |  | merchant | US | Houston | IT/ Energy Ops | 3 | system problems | CY-Explor-Bas book problem between medicalc and portcalc
2000-11-02 | Risk Controls |  | merchant | US | Houston | IT/ Energy Ops | 3 | system problems | CY-Explor-Prc book problem between medicalc and portcalc
2000-11-02 | Risk Controls |  | merchant | US | Houston | IT/ Energy Ops | 3 | system problems | EQ-Coal-East-Prc book problem between Metacalc and Portcalc
2000-11-02 | Risk Controls |  | merchant | US | Houston | IT/ Energy Ops | 3 | system problems | EQ-Coal-Jupiter-Prc book problem between Metacalc and Portcalc
2000-11-02 | Risk Controls |  | Merchant | US | Houston | IT/ Energy Ops | 3 | system problems | Equity-Cgas-Bas book problem between Metacalc and Portcalc
2000-11-02 | Risk Controls |  | Merchant | US | Houston | IT/ Energy Ops | 3 | system problems | Equity-CGAS-Prc book problem between Metacalc and Portcalc
2000-11-02 | Risk Controls |  | Merchant | US | Houston | IT/ Energy Ops | 3 | system problems | Equity-Mariner-Bas book problem between Metacalc and Portcalc
2000-11-02 | Risk Controls |  | Merchant | US | Houston | IT/ Energy Ops | 3 | system problems | Equity-Mariner-Prc book problem between Metacalc and Portcalc
2000-11-02 | Risk Controls |  | Power | UK | London | IT/ Energy Ops | 3 | system problems | data not in because feed is slow
2000-11-01 | Risk Controls |  | Gas | US | Houston | Energy Ops | 1 | book not officialized | FT-CAND-EGSC-A-Prc book not officialized
2000-11-01 | Risk Controls |  | Gas | US | Houston | Energy Ops | 1 | book not officialized | FT-CAND-EGSC-A-Prc book not officialized
2000-11-01 | Risk Controls |  | Liquids | US | Houston | IT/ Energy Ops | 3 | system problems | problem with Reuters Issues and the feed
2000-11-01 | Risk Controls |  | Power | UK | London | IT/ Energy Ops | 4 | system problems | EU-PWR-Bilateral book came across at 5 AM but JP received at 6 AM. WHY?
2000-11-01 | Risk Controls |  | Steel | US | Houston | Energy Ops | 1 | book not officialized | Steel-SCRC-Prc book not officialized - new BA | yes
2000-11-01 | IT |  | All | US | Houston | IT/ Energy Ops | 4 | system problems | Rerun of Var and Port Calc in morning is causing problems
Note on K1: shona: Ramesh runs VAR at 6 am
Note on M1: shona: Sheila's group needs this by 6:30 am - if they don't get it they use the cash flows from the prior day - find out - is this the same feed that is used for the VAR engine?

## Bridgeline
COB Date | Reported by: | Book | Class | Problem | Var Rerun? | Credit affected? | Impact cash flows?
2000-12-05 | Risk Controls | FT-Bridge-GD-GDL | 1 | book not officialized | yes | yes | no
2000-12-05 | Risk Controls | FT-Bridge-GDL | 1 | book not officialized | yes | yes | no
2000-12-05 | Risk Controls | FT-Bridge-Suba-GDL | 1 | book not officialized | yes | yes | no
2000-11-08 | Risk Controls | FT-Bridge-GD-GDL | 1 | book not officialized | yes | yes | no
2000-11-07 | Risk Controls | FT-Bridge-GD-GDL | 1 | book not officialized | yes | yes | no
2000-11-07 | Risk Controls | FT-Bridge-GDL | 1 | book not officialized | yes | yes | no
2000-11-07 | Risk Controls | FT-Bridge-Suba-GDL | 1 | book not officialized | yes | yes | no
2000-11-02 | Risk Controls | all books (so individual books not listed) | 1 | book not officialized | yes | yes | no
2000-11-02 | Risk Controls | all books (so individual books not listed) | 1 | book not officialized | yes | yes | no
2000-11-02 | Risk Controls | all books (so individual books not listed) | 1 | book not officialized | yes | yes | no
2000-11-02 | Risk Controls | all books (so individual books not listed) | 1 | book not officialized | yes | yes | no
2000-11-02 | Risk Controls | all books (so individual books not listed) | 1 | book not officialized | yes | yes | no
2000-11-02 | Risk Controls | all books (so individual books not listed) | 1 | book not officialized | yes | yes | no
2000-11-02 | Risk Controls | all books (so individual books not listed) | 1 | book not officialized | yes | yes | no
2000-11-02 | Risk Controls | all books (so individual books not listed) | 1 | book not officialized | yes | yes | no
2000-11-02 | Risk Controls | all books (so individual books not listed) | 1 | book not officialized | yes | yes | no
2000-11-02 | Risk Controls | all books (so individual books not listed) | 1 | book not officialized | yes | yes | no
2000-11-02 | Risk Controls | all books (so individual books not listed) | 1 | book not officialized | yes | yes | no
2000-11-02 | Risk Controls | all books (so individual books not listed) | 1 | book not officialized | yes | yes | no
2000-11-02 | Risk Controls | all books (so individual books not listed) | 1 | book not officialized | yes | yes | no
2000-11-02 | Risk Controls | all books (so individual books not listed) | 1 | book not officialized | yes | yes | no
2000-11-01 | Risk Controls | FT-Bridge-GDL | 1 | book not officialized | yes | yes | no