## Sheet1
Logistics Issue Log
Vol. Mgmt |  | Region | Pipe |  | Prod. |  |  |  | Estimated
Coordinator | Scheduler |  |  | Meter | date | Issue | Status | Date Notified | Completion
Antoinette Beale | Cora Pendergrass | Central | Michigan Consolidated | Deal 271751 | 2000-05-01 | Deal was killed on Great Lakes side and apparently not on MichCon | Contacted Cora and she is working on it. | 2001-08-08
Ryan Keith | Jessica White | Central | NGPL |  | 2000-11-01 | Select Point Usage was used resulting in an imbalance for Nov 2000 production of 2,329 mmbtu. | E-mailed information to Jessica. | 2001-08-27
Ryan Keith | Cora Pendergrass | Central | NGPL (Shipper: EMW) |  | 2001-06-01 | Have a cashout to process for NGPL EMW for an imbalance on K#117650 of 17 mmbtu. Contract is currently not in Unify so I am unable to process the cashout. | Contacted Cora. | 2001-08-16
Ryan Keith | Jessica White | Central | NGPL (Shipper: ENA Upstream) | 5449 | 2001-07-01 | Pipeline statement for NGPL shows gas flow of 398 mmbtu (199-7/30 & 199-7/31) at DEL POI 5449. Volume has not been pathed in Unify. | E-mailed information to Jessica. | 8/16/01 & 8/27/01
Marlo James | Tammy Gilmore | Central | PEPL | P9936 | 2001-08-01 | Requested volumes be repathed on correct contract since it is causing pool to be out of balance and can not tie to imbalance on #016918 | Have repathed some of the volumes after working with Richard Pinion. Will be getting w/ Tammy on Friday to fix the remainder of the paths. | 2001-09-17
Sherlyn Schumack | Mark Schrab | Central | TCPL | various | 99/01 | Transport usage tickets need to be created and pathed to clear interpipeline pools. |  | 2001-08-28
Marlo James | Tammy Gilmore | Central | TROK | Various | Various | Transok 4/99-12/99 needed repathing | 10/4/01 Lisa and Tammy will resume working on the reconciliation today. | 2000-11-01
Sherlyn Schumack | Mark Schrab | Central | UGL | various | 99/01 | Synthetic storage contracts need to be created and pathed so that imbalances can be tracked in unify |  | 2001-08-28
Sherlyn Schumack | Mark Schrab | Central | UGL | various | 99/01 | Transport usage tickets need to be created and pathed to clear interpipeline pools. |  | 2001-08-28
Gloria Barkowsky | Theresa Staab | Denver | PSCO | S116388 | 2000-05-01 | 06/00 Statement from Public Service is showing an imbalance delivery trade to Aurora Natural Gas. This is not in path manager and needs to be scheduled. |  | 2001-08-06
Alfonso Trabulsi | Dan Prudenti/Sabra | East | FGT | 25412/77777 | July 99, Sept 99, Oct 99 | Contract 5796 the delivery point was not pathed. | Have sent emails to scheduler with details | 2001-08-04
Alton Honore | Lia Halstead | East | Gulf South (Mitchell Marketing) | Imb Trade | 01/00 - 07/01 | Volume Management needs deal numbers for imbalance trades in order to path and actualize. |  | 10/3/01
Alton Honore | Kelly Loocke | East | Sea Robin |  | 2001-01-01 | On K#001077 for day 11 SeaRobin shows an injection of 991 mmbtu but no withdrawl from this point (pooling contract) | Kelly called her contact at SeaRobin for a corection in their system | 2001-08-23
Alton Honore | Kelly Loocke | East | Sea Robin |  | 2001-02-01 | On K#001077 for day 20 SeaRobin shows an injection of 360 mmbtu but no withdrawl from this point (pooling contract) | Kelly called her contact at SeaRobin for a corection in their system | 2001-08-23
Lee Ann Chance | Tamie Carter | East | Tenn | Various | 6/01 - 8/01 | Waiting on pathing on 3 contracts - k13274, k18314, k32748 | Talked with Tamie about paths; planning to get them in system 10/01 | 2001-09-05
Lee Ann Chance | Tamie Carter/Jesse Villereal | East/Upstream | Tenn | 001527 & 001447 | 2001-06-01 | Need pathing on Tenn for ENA k 36521 / brokered paths related to this contract needed from Upstream as well | Talked with both Tamie & Jesse 9/26 - deals entered in system; plans made to enter paths 10/2 10/3 | 9/6/01 & 9/26/01
Hakeem Ogunbunmi | Daniel Lisk | West | PGE | Various | 2001-08-01 | The following contracts are not scheduled in Unify for Aug. 2001: 0202PCG031, 0202LCG023, 0202LCG020, 020LCG033, 0202LCG034, 0202LCG037, & 0202LCG012
Marlo James | Jan Sutherland | West | SoCal |  | Various | Sent Jan a list of production periods that need to have the dailies sent from SoCal in order to cleanup the imbalances in Unify and provided Settlements with support. | Jan stated she would be contacting Socal 9/5 9/14 Received the dailies for the EES acct #2587. Jan said she would be calling SoCal back on 9/20 for the #2527 volumes. 9/28 Jan stated she would be calling SoCal again since we still have not received them. | 2001-08-22
Marlo James | Jan Sutherland | West | SoCal |  | 2001-07-01 | Requested missing volumes for EES be pathed |  | 2001-09-12
Marlo James | Jane Tholt/Matt Smith | West | SoCal | Imb Trade | Various | Missing Imbalance Trade tickets | Still missing 3/00 and 8/00 trades. Notified logistics and risk | 2001-09-06
|  | West | SoCal |  | 2001-08-01 | Needed a zero nom entered for 8/01 Harbor Cogen. |  | 2001-09-17
Stephen Swisher | Stacey Brewer | West | WFSC | L57 | 2001-04-01 | Day 27 gas is being pulled from imbalance account from WFSC. Waiting on Deal from Stacey Brewer. |  | 2001-06-15
Stephen Swisher | Stacey Brewer | West | WFSC | L57 | 2001-06-01 | Gas Day 3,4,5,6,22 missing deal (El Paso Merchant). Stacey is currently working with trader to get deals in unify. |  | 2001-09-18
Stephen Swisher | Wes Dempsey | West | WFSC | G470KS | Jan 00-Jun01 | Need to path gathering to pay gathering volume so that I can pay invoice thru Unify instead of manual payment. | Met on 8/27/01 with Lisa Kinsey, Patti Sullivan, and Wes Dempsey and we came to a conclusion that G470KS needed to be repathed in Unify. Projected to be completed Sept 17. | 2001-06-26