## Sheet1
Logistics Issue Log
Vol. Mgmt |  | Region | Pipe |  | Prod. |  |  |  | Estimated
Coordinator | Scheduler |  |  | Meter | date | Issue | Status | Date Notified | Completion
Antoinette Beale | Cora Pendergrass | Central | Michigan Consolidated | Deal 271751 | 2000-05-01 | Deal was killed on Great Lakes side and apparently not on MichCon | Contacted Cora and she is working on it. | 2001-08-08
Ryan Keith | Jessica White | Central | NGPL | 900325 | 2001-03-01 | Missing deal with Oxy USA for 2,717 on March 31 on the title transfer contract. |  | 6/27/01 & 7/05/01
Ryan Keith | Jessica White | Central | NGPL | 5433 | 2001-07-01 | Missing a purchase from ENA Upstream at REC POI 5433 of 15,000 mmbtu. Gas flowed from 7/27/01-7/29/01. | E-mailed information to Jessica. | 2001-08-27
Ryan Keith | Jessica White | Central | NGPL |  | 2000-11-01 | Select Point Usage was used resulting in an imbalance for Nov 2000 production of 2,329 mmbtu. | E-mailed information to Jessica. | 2001-08-27
Ryan Keith | Cora Pendergrass | Central | NGPL (Shipper: EMW) |  | 2001-06-01 | Have a cashout to process for NGPL EMW for an imbalance on K#117650 of 17 mmbtu. Contract is currently not in Unify so I am unable to process the cashout. | Contacted Cora. | 2001-08-16
Ryan Keith | Jessica White | Central | NGPL (Shipper: ENA Upstream) | 5449 | 2001-07-01 | Pipeline statement for NGPL shows gas flow of 398 mmbtu (199-7/30 & 199-7/31) at REC POI 5449 DEL POI 25085. Volume has not been pathed in Unify. | E-mailed information to Jessica. | 8/16/01 & 8/27/01
Marlo James | Tammy Gilmore | Central | PEPL | P9936 | 2001-04-01 | Requested volumes be repathed on correct contract since it is causing pool to be out of balance. |  | 2001-09-10
Marlo James | Tammy Gilmore | Central | TROK | Various | Various | 6/19 - Gave Lisa K. new copies of problem detail along w/ Transok statements to review and path lists. Will need to discuss further resolution solution after she has had time to review information. | 8/17 Lisa stated she wants to take one month at a time and will notify me when she gets started. | 2000-11-01
Gloria Barkowsky | Theresa Staab | Denver | PSCO | S116388 | 2000-05-01 | 06/00 Statement from Public Service is showing an imbalance delivery trade to Aurora Natural Gas. This is not in path manager and needs to be scheduled. |  | 2001-08-06
Sherry Anastas | Kevin Alvarado | East | CGAS | S1 | 2001-06-01 | Supply deal for Markwest Hydrocarbons missing for 13,775 mmbtu on contract 37147. | Kevin was going to call CGAS. | 2001-07-25
Sherry Anastas | Kevin Alvarado | East | CGAS | P10 | 2001-06-01 | Supply deal for Norse Pipeline missing for 1,620 mmbtu on contract 37147. | This gas was scheduled at another meter. Need to add P10 to deal and repath. | 2001-07-25
Sherry Anastas | Kevin Alvarado | East | CGAS | S1 | 2001-06-01 | Supply deal for Markwest Hydrocarbons missing for 183 mmbtu on contract 39149. | Kevin was going to call CGAS. | 2001-07-25
Sherry Anastas | Kevin Alvarado | East | CGAS | S1 | 2001-06-01 | Supply deal for Markwest Hydrocarbons missing for 7,432 mmbtu on contract 66917. | Kevin was going to call CGAS. | 2001-07-25
Sherry Anastas | Kevin Alvarado | East | CGAS | P10 | 2001-07-01 | Supply deal for Norse Pipeline missing for 2,634 mmbtu on contract 37147. | This gas was scheduled at another meter. Need to add P10 to deal and repath. | 2001-07-25
Alfonso Trabulsi | Dan Prudenti/Sabra | East | FGT | 25412/77777 | July 99, Sept 99, Oct 99 | Contract 5796 the delivery point was not pathed. | Have sent emails to scheduler with details | 2001-08-04
Alton Honore | Kelly Loocke | East | Sea Robin |  | 2001-01-01 | On K#001077 for day 11 SeaRobin shows an injection of 991 mmbtu but no withdrawl from this point (pooling contract) | Kelly called her contact at SeaRobin for a corection in their system | 2001-08-23
Alton Honore | Kelly Loocke | East | Sea Robin |  | 2001-02-01 | On K#001077 for day 20 SeaRobin shows an injection of 360 mmbtu but no withdrawl from this point (pooling contract) | Kelly called her contact at SeaRobin for a corection in their system | 2001-08-23
Alton Honore | Joe Casas | East | SONAT |  | 2000-01-01 | We need to repath contract PSNG2194 out of the Imbalance pool for PSNG2194 instead of the imbalance pool for FSNG11 (path ID344927) | Spoke with Joe about this issue and he requested statements | 2001-09-07
Stephen Swisher | Robert Ramirez | NE | VGS |  |  | Imbalance Trades for CY00 need to be pathed in Unify | Waiting til after bid week to complete | 2001-08-28
Eric Calub | Mike Olsen | Texas | EPGT/PGTT |  | Feb01-June01 | Move K#9135 from EPGT to PGTT | March thru June complete. February still outstanding | 2001-08-24
Hakeem Ogunbunmi | Daniel Lisk | West | PGE | Various | 2001-08-01 | The following contracts are not scheduled in Unify for Aug. 2001: 0202PCG031, 0202LCG023, 0202LCG020, 020LCG033, 0202LCG034, 0202LCG037, & 0202LCG012
Marlo James | Jan Sutherland | West | SoCal |  | Various | Sent Jan a list of production periods that need to have the dailies sent from SoCal in order to cleanup the imbalances in Unify and provided Settlements with support. | Jan stated she would be contacting Socal 9/5 9/14 Received the dailies for the EES acct #2587 | 2001-08-22
Marlo James | Jane Tholt/Matt Smith | West | SoCal | Imb Trade | Various | Unify is not tieing to the Socal statement on the Imbalance trades because there are missing tickets. Sent a compilation list to both traders with explanations and requested they be entered as soon as possible. | Still missing 3/00 , 8/00, and 7/01 trades. Notified logistics and risk | 2001-09-06
Stephen Swisher | Wes Dempsey | West | WFSC | G470KS | Jan 00-Jun01 | Need to path gathering to pay gathering volume so that I can pay invoice thru Unify instead of manual payment. | Met on 8/27/01 with Lisa Kinsey, Patti Sullivan, and Wes Dempsey and we came to a conclusion that G470KS needed to be repathed in Unify. Projected to be completed Sept 17. | 2001-06-26
Stephen Swisher | Stacey Brewer | West | WFSC | L57 | 2001-04-01 | Day 27 gas is being pulled from imbalance account from WFSC. Waiting on Deal from Stacey Brewer. |  | 2001-06-15