## Sheet1
Things to add to the issues / outstanding items list
North America list
Area responsible | Owner | Milestone |  | When
Commercial support | Al Pennisi, Marcelo Parra, Kevin Rhodes | Set up org chart for broker functions |  | 2000-10-06
Commercial support | Al Pennisi, Kevin Rhodes, Marcelo Parra, head of documentation (Paul Wallace), head of settlements | Assess Rolf & Nowlen |  | 2000-10-27
Commercial support | Marcelo Parra, Tim Poullain-Patterson | Determine & hire additional resource requirements MO & Fin Ops |  | 2000-10-13
Commercial support | Marcelo Parra, Louis Colarusso | Implement reorg
|  |  | Remote offices | 2000-10-16
|  |  | NY concentrates | 2000-11-10
|  |  | NY metals | 2000-10-27
|  |  | NY broker | 2000-10-27
Commercial support | Andy Cornfield, Lou Colarusso | Review current risk reporting and address gaps to Enron requirements |  | 2000-10-15
Legal | Alan Aronowitz | Review current contracts and confirmations and address gaps to Enron requirements |  | 2000-10-27
Commercial support | Documentation lead (Paul Wallace), Marcelo Parra | Coordinate with legal and determine appropriate confirmations/contracts to be sent out by each dept |  | 2000-10-27
Commercial support | Andy Cornfield, Lou Colarusso | Review book calcs |  | 2000-10-27
Commercial support | Andy Cornfield, Lou Colarusso | Review position capture |  | 2000-10-27
Credit, commercial support | Tim Davies, Marcelo Parra | Finalize reporting structure for prepaids |  | 2000-10-06
Commercial support | Marcelo Parra, Louis Colarusso | Change from Aquarius / Thunderball (Kevin Sweeny, Cindy Horn) or AS 400 |  | 2001-01-31
Cash management | Mary Perkins | Finalize cash management structure |  | 2000-10-30
Fin Ops | Naomi Connell, Lou Colarusso | Address gaps to current Enron reporting and implement changes (including SAP) |  | 2000-12-31
Credit | Tim Davies, Marcelo Parra | Hire Credit person and formalize structure |  | 2000-10-27