## 250 MM Exp West with SJ Lat
Mainline Expansion
San Juan (Bloomfield) to California (Topock)
Mainline Mid-Point Compression Only
Estimated Costs of Facilities
Dated 10-24-01
| CASE XI. | A. | 30" MAINLINE LOOP, AND HP
250 MMCF/D EXPANSION (1460 MMCF/D TOTAL)
[10 empty] | Vol. Incr. | Total Vol. | Int., O/H, etc
| From |  | To |  | Miles |  | Size (") |  | Est. Costs | MMcf/d | MMcf/d | Not Included
| BLFD CS |  | SJCT |  | 57.27 |  | 30 | " | 52917480 |  |  | 9621360
|  |  | Bloomfield Mods | [5 empty] | 1000000
|  |  | Bloomfield Compressor Mods | [5 empty] | 3000000
|  |  | Blanco Hub Mods | [5 empty] | 1700000
|  |  | Bisti CS Mods | [5 empty] | 2600000
|  |  | Standing Rock CS (9,500 Hp) | [5 empty] | 25346000
|  |  | Gallup CS HP Add | [5 empty] | 12000000
|  |  | Gallup CS Mods | [5 empty] | 6400000
|  |  |  | Total San Juan Expansion | 57.27 |  |  |  | 104963480 | 300 | 1150 | 9621360
|  |  | CS4 (25,000 Hp) | [5 empty] | 29660000
|  |  | CS3.5 (26,500 Hp) | [5 empty] | 29400000
|  |  | CS2.5 (26,500 Hp) | [5 empty] | 29400000
|  |  | CS1.5 (25,000 Hp) | [5 empty] | 29400000
|  |  | Kingman CS (25,000 Hp) | [5 empty] | 29400000
|  |  |  | Total Mainline Expansion | 0 |  |  |  | 117600000 | 250 | 1460 | 0
|  |  |  | Total Topock Lateral Expansion | 18.41 |  | 20 | " | 11340560 | 300 | 700 | 2061920
|  |  |  | Sub Total |  |  |  |  | 233904040
Extraordinary Detailed Line Items:
|  |  |  | Navajo land & labor costs |  |  |  |  | 46400000
|  |  |  | Gross receipt payments (AZ & NM) |  |  |  |  | 5262840.9
|  |  |  | River & stream crossings |  |  |  |  | 7600000
|  |  |  | Mountain terrain & |  |  |  |  | 4500000
BLM Double ditching
|  |  |  | Contingency on above |  |  |  |  | 6376284.09
|  |  |  | Total Project Excl. Int., O/H, etc. | 75.68 |  |  |  | 304043164.99 |  |  | 11683280
|  |  |  | Total Project Incl. Int., O/H, etc. |  |  |  |  | 315726444.99
| Note: | 1. | Interest and overheads identified separately.
|  | 2. | Station #4 Hp changeout included in this project.
|  | 3. | No escalation added to the above line items.
|  | 4. | The above is a + 30% cost estimate.

## 250 MM Exp West without SJ Lat
Mainline Expansion
San Juan (Bloomfield) to California (Topock)
Mainline Mid-Point Compression Only
Estimated Costs of Facilities
Dated 10-24-01
| CASE XI. | A. | 30" MAINLINE LOOP, AND HP
250 MMCF/D EXPANSION (1460 MMCF/D TOTAL)
[10 empty] | Vol. Incr. | Total Vol. | Int., O/H, etc
| From |  | To |  | Miles |  | Size (") |  | Est. Costs | MMcf/d | MMcf/d | Not Included
|  |  | CS4 (25,000 Hp) | [5 empty] | 29660000
|  |  | CS3.5 (26,500 Hp) | [5 empty] | 29400000
|  |  | CS2.5 (26,500 Hp) | [5 empty] | 29400000
|  |  | CS1.5 (25,000 Hp) | [5 empty] | 29400000
|  |  | Kingman CS (25,000 Hp) | [5 empty] | 29400000
|  |  |  | Total Mainline Expansion | 0 |  |  |  | 117600000 | 250 | 1460 | 0
|  |  |  | Total Topock Lateral Expansion | 18.41 |  | 20 | " | 11340560 | 300 | 700 | 2061920
|  |  |  | Sub Total |  |  |  |  | 128940560
Extraordinary Detailed Line Items:
|  |  |  | Navajo land & labor costs |  |  |  |  | 46400000
|  |  |  | Gross receipt payments (AZ & NM) |  |  |  |  | 2901162.6
|  |  |  | River & stream crossings |  |  |  |  | 0
|  |  |  | Mountain terrain & |  |  |  |  | 0
BLM Double ditching
|  |  |  | Contingency on above |  |  |  |  | 4930116.26
|  |  |  | Total Project Excl. Int., O/H, etc. | 18.41 |  |  |  | 183171838.86 |  |  | 2061920
|  |  |  | Total Project Incl. Int., O/H, etc. |  |  |  |  | 185233758.86
| Note: | 1. | Interest and overheads identified separately.
|  | 2. | Station #4 Hp changeout included in this project.
|  | 3. | No escalation added to the above line items.
|  | 4. | The above is a + 30% cost estimate.

## 300 MM Exp West with SJ Lat
Mainline Expansion
San Juan (Bloomfield) to California (Topock)
Pipe Loop and Compression
Estimated Costs of Facilities
Dated 10-24-01
| CASE XI. | B. | 30" MAINLINE LOOP, AND HP
330 MMCF/D EXPANSION (1740 MMCF/D TOTAL)
[10 empty] | Vol. Incr. | Total Vol. | Int., O/H, etc
| From |  | To |  | Miles |  | Size (") |  | Est. Costs | MMcf/d | MMcf/d | Not Included
| BLFD CS |  | SJCT |  | 57.27 |  | 30 | " | 52917480 |  |  | 9621360
|  |  | Bloomfield Mods | [5 empty] | 1000000
|  |  | Bloomfield Compressor Mods | [5 empty] | 3000000
|  |  | Blanco Hub Mods | [5 empty] | 1700000
|  |  | Bisti CS Mods | [5 empty] | 2600000
|  |  | Standing Rock CS (9,500 Hp) | [5 empty] | 25346000
|  |  | Gallup CS HP Add | [5 empty] | 12000000
|  |  | Gallup CS Mods | [5 empty] | 6400000
|  |  |  | Total San Juan Expansion | 57.27 |  |  |  | 104963480 | 300 | 1150 | 9621360
| SJCT | - | Sta. #4 |  | 43.9 |  | 30 | " | 40563600 |  |  | 7375200
| Sta. #4 | - | Sta. #3 |  | 85.5 |  | 30 | " | 79002000 |  |  | 14364000
| Sta. #3 | - | Sta. #2 |  | 59.11 |  | 30 | " | 54617640 |  |  | 9930480
| Sta. #2 |  | Sta. #1 |  | 0 |  | 30 | " | 0 |  |  | 0
| Sta. #1 |  | Needles |  | 0 |  | 30 | " | 0 |  |  | 0
|  |  | CS4 (25,000 Hp) | [5 empty] | 29660000
|  |  | CS1.5 (25,000 Hp) | [5 empty] | 29200000
|  |  | Kingman CS (25,000 Hp) | [5 empty] | 29400000
|  |  |  | Total Mainline Expansion | 188.51 |  |  |  | 262443240 | 330 | 1540 | 31669680
|  |  |  | Total Topock Lateral Expansion | 18.41 |  | 20 | " | 11340560 | 300 | 700 | 2061920
|  |  |  | Sub Total |  |  |  |  | 378747280
|  |  |  | Sub Total w/interest, etc |  |  |  |  | 410416960
Extraordinary Detailed Line Items:
|  |  |  | Navajo land & labor costs |  |  |  |  | 46400000
|  |  |  | Gross receipt payments (AZ & NM) |  |  |  |  | 8521813.8
|  |  |  | River & stream crossings |  |  |  |  | 7600000
|  |  |  | Mountain terrain & |  |  |  |  | 4500000
BLM Double ditching
|  |  |  | Contingency on above |  |  |  |  | 6702181.38
|  |  |  | Total Project Excl. Int., O/H, etc. | 264.19 |  |  |  | 452471275.18 |  |  | 43352960
|  |  |  | Total Project Incl. Int., O/H, etc. |  |  |  |  | 495824235.18
| Note: | 1. | Interest and overheads identified separately.
|  | 2. | Station #4 Hp changeout included in this project.
|  | 3. | No escalation added to the above line items.
|  | 4. | The above is a + 30% cost estimate.

## 300 MM Exp West without SJ Lat
Mainline Expansion
San Juan Junction to California (Topock)
Pipe Loop and Compression
Estimated Costs of Facilities
Dated 10-24-01
| CASE XI. | C. | 30" MAINLINE LOOP, AND HP
330 MMCF/D EXPANSION (1740 MMCF/D TOTAL)
[10 empty] | Vol. Incr. | Total Vol. | Int., O/H, etc
| From |  | To |  | Miles |  | Size (") |  | Est. Costs | MMcf/d | MMcf/d | Not Included
| SJCT | - | Sta. #4 |  | 43.9 |  | 30 | " | 40563600 |  |  | 7375200
| Sta. #4 | - | Sta. #3 |  | 85.5 |  | 30 | " | 79002000 |  |  | 14364000
| Sta. #3 | - | Sta. #2 |  | 59.11 |  | 30 | " | 54617640 |  |  | 9930480
| Sta. #2 |  | Sta. #1 |  | 0 |  | 30 | " | 0 |  |  | 0
| Sta. #1 |  | Needles |  | 0 |  | 30 | " | 0 |  |  | 0
|  |  | CS4 (25,000 Hp) | [5 empty] | 29660000
|  |  | CS1.5 (25,000 Hp) | [5 empty] | 29200000
|  |  | Kingman CS (25,000 Hp) | [5 empty] | 29400000
|  |  |  | Total Mainline Expansion | 188.51 |  |  |  | 262443240 | 330 | 1540 | 31669680
|  |  |  | Total Topock Lateral Expansion | 18.41 |  | 20 | " | 11340560 | 300 | 700 | 2061920
|  |  |  | Sub Total |  |  |  |  | 273783800
|  |  |  | Sub Total w/interest, etc |  |  |  |  | 305453480
Extraordinary Detailed Line Items:
|  |  |  | Navajo land & labor costs |  |  |  |  | 40400000
|  |  |  | Gross receipt payments (AZ & NM) |  |  |  |  | 6160135.5
|  |  |  | River & stream crossings |  |  |  |  | 5600000
|  |  |  | Mountain terrain & |  |  |  |  | 4500000
BLM Double ditching
|  |  |  | Contingency on above |  |  |  |  | 5666013.55
|  |  |  | Total Project Excl. Int., O/H, etc. | 206.92 |  |  |  | 336109949.05 |  |  | 33731600
|  |  |  | Total Project Incl. Int., O/H, etc. |  |  |  |  | 369841549.05
| Note: | 1. | Interest and overheads identified separately.
|  | 2. | Station #4 Hp changeout included in this project.
|  | 3. | No escalation added to the above line items.
|  | 4. | The above is a + 30% cost estimate.
|  | 5. | Project costs to expand east facilities (WTX or PH Laterals) not included in this study.