## M. Stringer
# | Category | Finding | Action Item | Responsible Person | Target Date | Confirm Reviewer | Completion Date | Comments
PSM
159 | ESMS | #399 Is good housekeeping being practiced? | Ensure good housekeeping is practiced throughout the facility as required per ETS Safety Procedure guidelines. | Mark Stringer | 2001-02-28 | Don Bishop
52 | GMP | No Equipment Readup records | Assure that operations logs are developed to capture the equipment's status and running conditions during shift rounds. | Mark Stringer | 2001-06-30 | Rick Suderman
56 | GMP | No Engine Crankcase Pressure Readings being taken. | Assure that crankcase pressures are captured on equipment readup sheets to be used for analyzing engine performance. | Mark Stringer | 2001-06-30 | Rick Suderman
101 | Operating Procedures | Start/ stop instructions missing from remote control panels. | Assure that start/stop instructions are posted at all remote start-up control panels, all equipment. | Mark Stringer | 2001-09-30 | Rick Suderman