## PROS
ET&S REVENUE MANAGEMENT PROJECT
Timeline Differences
High Level Timeline
| 1999-07-01 | 1999-08-01 | 1999-09-01 | 1999-10-01 | 1999-11-01 | 1999-12-01 | 2000-01-01 | 2000-02-01 | 2000-03-01 | 2000-04-01 | 2000-05-01 | 2000-06-01 | 2000-07-01 | 2000-08-01 | 2000-09-01 | 2000-10-01
| Stage 1 |  |  |  |  | 12/99
|  |  | Stage 2 |  |  | 12/99
[6 empty] | Stage 3 |  |  | 3/99
[7 empty] | Stage 4 |  |  |  |  | 6/00
[13 empty] | Stage 5 |  |  | 10/00
Project Plan Detailed Timeline
| 1999-07-01 | 1999-08-01 | 1999-09-01 | 1999-10-01 | 1999-11-01 | 1999-12-01 | 2000-01-01 | 2000-02-01 | 2000-03-01 | 2000-04-01 | 2000-05-01 | 2000-06-01 | 2000-07-01 | 2000-08-01 | 2000-09-01 | 2000-10-01 | 2000-11-01
| Pre-Launch 7/6/99 | 8/16/99
| Stage 1 7/6/99 |  |  |  |  | 12/16/99
|  | Stage 2 8/16/99 |  |  |  | 12/16/99 | 1/26/00
[6 empty] | Stage 3 12/16/99 |  |  |  | 4/13/00 |  |  | 7/26/00
[7 empty] | Stage 4 1/4/00 |  |  |  |  | 6/29/00 | 7/26/00
[12 empty] | Stage 5 6/29/00 |  |  |  | 10/27/00 | 11/2/00

## Zone EF Prototype
ET&S REVENUE Enhancement 2001 Goals / Objectives
High Level Timeline
Zone EF Prototype Model
| 2001-01-01 | 2001-02-01 | 2001-03-01 | 2001-04-01 | 2001-05-01 | 2001-06-01 | 2001-07-01 | 2001-08-01 | 2001-09-01 | 2001-10-01 | 2001-11-01 | 2001-12-01
High Level Technical Architecture Plan
Data Requirements (inputs, outputs) | 2001-01-01: Define Data/Req.
Technical Platform (database tools) | 2001-02-01: Design/Req
Development Tools | 2001-02-01: Design/Req
Zone EF Data Extraction Process
Executed Deals since 1994 | 2001-01-01: Contract Data; 2001-02-01: Analysis
Capacity Release Data since 1994 | 2001-01-01: Contract Data; 2001-02-01: Analysis
Variable Data Extraction | 2001-01-01: Price/Weather/Var. Data; 2001-03-01: Analysis
Business Problem Resolution / Model Design and Construction
Demand Forecast | 2001-02-01: Design/Construct; 2001-04-01: Constuct
Utilization Forecast | 2001-02-01: Design/Construct; 2001-04-01: Constuct
Customer Segmentation | 2001-02-01: Define/Develop tables
Volatility of Forward Prices | 2001-03-01: Evaluation of Applicability
Optimization Model | 2001-02-01: Design/Req; 2001-04-01: Constuct
Appropriate GUI for Proving Model | 2001-05-01: Design/Req
User Test
Proof of Model Viability | 2001-06-01: Analysis
|  |  |  | Training | Training
|  |  |  | Training | Design/Req
Design/Req
Design/Req
R & D
Design/Req

## TW Line Pack
ET&S REVENUE Enhancement 2001 Goals / Objectives
High Level Timeline
TW Line Pack
| 2001-01-01 | 2001-02-01 | 2001-03-01 | 2001-04-01 | 2001-05-01 | 2001-06-01 | 2001-07-01 | 2001-08-01 | 2001-09-01 | 2001-10-01 | 2001-11-01 | 2001-12-01
[13 empty] | Training | Training | Training
[13 empty] | Design/Req | Design/Req | Design/Req
[13 empty] | R & D | Design/Req. | Design/Req.
|  |  | Design/Req | Training | Design/Req
|  |  | Design/Req | Training
|  |  | Training | Design/Req

## Storage Model
ET&S REVENUE Enhancement 2001 Goals / Objectives
High Level Timeline
Storage Model
|  | 2001-01-01 | 2001-02-01 | 2001-03-01 | 2001-04-01 | 2001-05-01 | 2001-06-01 | 2001-07-01 | 2001-08-01 | 2001-09-01 | 2001-10-01 | 2001-11-01 | 2001-12-01
High Level Technical Architecture Plan
Data Requirements (inputs, outputs) |  | 2001-01-01: Design/Req.; 2001-05-01: Training
Technical Platform (database tools) |  | 2001-01-01: Design/Req.
Development Tools
Design/Req
R & D
Zone EF Data Extraction Process
Executed Deals since 1994 |  | 2001-03-01: Design/Req; 2001-06-01: Training
Capacity Release Data since 1994
Variable Data Extraction |  | 2001-04-01: Design/Req; 2001-07-01: Training
Business Problem Resolution / Model Design and Construction
Demand Forecast |  | 2001-06-01: Design/Req
Utilization Forecast
Customer Segmentation
Volatility of Forward Prices
Optimization Model |  | 2001-06-01: Design/Req; 2001-10-01: Training
Appropriate GUI for Proving Model
User Test |  | 2001-08-01: Design/Req; 2001-12-01: Training
Proof of Model Viability |  | 2001-08-01: Design/Req; 2001-12-01: Training
(New Group)
EDS
PROS

## Synthetic Storage
ET&S REVENUE Enhancement 2001 Goals / Objectives
High Level Timeline
Synthetic Storage
|  | 2001-01-01 | 2001-02-01 | 2001-03-01 | 2001-04-01 | 2001-05-01 | 2001-06-01 | 2001-07-01 | 2001-08-01 | 2001-09-01 | 2001-10-01 | 2001-11-01 | 2001-12-01
High Level Technical Architecture Plan
Data Requirements (inputs, outputs) |  | 2001-01-01: Design/Req.; 2001-05-01: Training
Technical Platform (database tools) |  | 2001-01-01: Design/Req.
Development Tools
Design/Req
R & D
Zone EF Data Extraction Process
Executed Deals since 1994 |  | 2001-03-01: Design/Req; 2001-06-01: Training
Capacity Release Data since 1994
Variable Data Extraction |  | 2001-04-01: Design/Req; 2001-07-01: Training
Business Problem Resolution / Model Design and Construction
Demand Forecast |  | 2001-06-01: Design/Req
Utilization Forecast
Customer Segmentation
Volatility of Forward Prices
Optimization Model |  | 2001-06-01: Design/Req; 2001-10-01: Training
Appropriate GUI for Proving Model
User Test |  | 2001-08-01: Design/Req; 2001-12-01: Training
Proof of Model Viability |  | 2001-08-01: Design/Req; 2001-12-01: Training
(New Group)
EDS
PROS

## MUD Project
ET&S REVENUE Enhancement 2001 Goals / Objectives
High Level Timeline
MUD Project
| 2001-01-01 | 2001-02-01 | 2001-03-01 | 2001-04-01 | 2001-05-01 | 2001-06-01 | 2001-07-01 | 2001-08-01 | 2001-09-01 | 2001-10-01 | 2001-11-01 | 2001-12-01
[13 empty] | Design/Req | Training | Training | Design/Req
[13 empty] | Design/Req | Training | Design/Req | Training
[13 empty] | Design/Req | Training | Design/Req | R & D
[13 empty] | Design/Req | Design/Req. | Training | Design/Req.