## Ready for Release
Product Types ready for release, pending GTC and External Customer Profile Upload
New Product Types: | 2000-08-25 | AUS Weather HDD and CDD Swaps
| 2000-08-25 | JPN Weather HDD and CDD Swaps
| 2000-09-01 | Financial Natural Gasoline
| 2000-09-01 | Physical Natural Gasoline
| 2000-09-01 | Financial Normal Butane
| 2000-09-01 | Physical Normal Butane

## Clean-up & Projects
Clean-up and Projects
Product Type |  | All West Power Product descriptions
| 2000-07-27 | Leslie Hansen sent new descriptions for the Spreads and all other non-Spread Product
Types. The system has a limitation that restricts the number of characters that can be put
into the Location Static Data element. Since we can't change the Location component,
we can't change the Product Type descriptions, as they must act in concert. Roll-out of
new language to occur post-Phase II. Ticker Item is ready.

## Work on Hold
Work on HOLD
New Product Type |  | US Nat Gas Financial Options
| 2000-08-10 | On hold until post-Phase II
New Product Type |  | AUS and JPN Weather Options
| 2000-08-10 | On hold until post-Phase II
New Product Type |  | Physical Steel
| 2000-08-03 | Spoke with Jayshree Desai. Enron owns a surplus of steel and would like to transact Online.
They have never done this OTC, have no Confirmations, no legal description, no GTC.
Jayshree was directed to the Legal area to start the legal review and processes.
New Product Type |  | Advertising Market (Bandwidth)
| 2000-08-09 | Work commenced earlier in the month with discussions with trading. When we followed
up with Cynthia Harkness (EBS Legal), Cynthia explained that they had not done this
product OTC, that they had no GTC, Legal Description, or Confirmation in place - and
that she was putting this on hold for EOL purposes until they could get the documentation
in order.

## Work in Progress
Work in Progress
New Product Type |  | Gas Transportation
| 2000-07-31 | Savita to follow-up with Steve Hotte on Product Long Descriptions and GTC's, an External Customer
list, and to determine whether or not the transactions will all be conducted by Enron Gas Pipeline
Group or by the different pipelines that make up EGP
New Product Type |  | US Nat Gas Financial Spread (Internal Use Only)
| 2000-08-10 | Peter Keavey wants a Spread Product to help him hedge between his closing Nymex position and
his GD HeHub position. Language drafted which he reviewed and approved with minor changes. Will
clean up the language and run by Legal, then start to build the Product Type. Appraised Pete of the
moratorium, he's okay with this.
| 2000-08-18 | David Forster spoke with Pete about his product and will be finalizing language.
New Product Type |  | US Phys Paper OCC Ex-works
| 2000-07-19 | New Product requested (OCC#11)
| 2000-08-10 | Request meeting to discuss Issues/Needs:
- Logistics is to validate product description with trader (movement of product is not usual practice)
- Logistics is to ascertain all possible types of movements for EOL OCC11 products. (Logistics has
identified a matrix of product movements, but movements do not conform to Legal's descriptions).
- Legal request to use Incoterms is contrary to P&P's domestic practice. Direction needed from Legal.
- P&P needs to identify delivery locations (potential hubs - not yet identified or defined by P&P)
- GTC's have been revised for Legal's approval (of Anti-Boycott Provisions). Awaiting approval.
| 2000-08-14 | Rob Cass is dedicated to supporting the Pulp and Paper desk and getting all related Products developed.
New Product |  | ANR ML7
| 2000-07-24 | This is a new Nat Gas Physical Location requested by Kevin Ruscetti. Stacey Dickson has turned
language development over to Bob Bowen. Bob is working with Kevin to draft new language.
New Product |  | US East Power Cinergy Peak Hour splits
| 2000-08-09 | Nicole La wants to transact on Cinergy using the Index "Internet Publishing Direct - Traders News"
and split the standard Peak hours in to four 4-hour periods. Language drafted and sent to Leslie Hansen.
Kenny Ha directed Nicole to provide an Index map.
| 2000-08-11 | Meeting scheduled for next Tuesday to review legal language with Nicole and Leslie.
| 2000-08-15 | Meeting held; Nicole and Leslie working together to finalize the Index and Loadshape descriptions.
| 2000-08-24 | Language finalized; going to Test.
New Product Type |  | Argentina Power and Gas
| 2000-08-11 | Follow-up conversations with Patrick Hansen. Checking with Brent Hendry on his review of the proposed
product type descriptions. Patrick to provide Risk Book Assignments, additional delivery Locations,
treatment for TRPs, legal names of transacting entities, and Regions. Spoke with Jason Althaus re:
Argentina Std time zone - to be created post-Phase II.
| 2000-08-14 | Risk Book assignment for Gas is done. Power will use Spreadsheet. Delivery Locations and their
related Products built in TEST.
| 2000-08-24 | Met with Legal; Argentina Legal has drafted a GTC in Spanish, and there has been no contemplation
of English defined terms in the product long descriptions. Per my conversation with Brent Hendry, I
will re-draft product long descriptions using established language and provide a copy of same along with
the GTC's so Agrentina counsel can incorpoaret same into their GTC.

## Pending Technology
Pending Technology
New Product Type |  | PJM Demand offered by the Weather Desk
| 2000-08-10 | The Product Type was originally set to Internal Use Only. Trading now wants to offer the
Product externally. This cannot be done until we have the ability to adjust/remove the
Weather-related attributes. We should, however, be able to use the existing Product Type.
New Product Type |  | US East Power Unplanned B
| 2000-08-08 | Product Type is built in Data Manager and has all approvals. Firmness needs to be
changed to Unplanned B, then we test.
| 2000-08-10 | Firmness has been changed, but we cannot test new power Product Types until the
test website is available.
Products |  | AUS and JPN Weather Products
| 2000-08-11 | The Maximum Trade Quantity on the Quote Details/Trading Hours tab cannot be adjusted in
the Product Manager once there are transactions against the Product.
New Product Types |  | Argentina Power and Gas
| 2000-08-11 | Need an Argentina Standard time zone created.
Products |  | All US-offered Products
| 2000-08-11 | Have technology set all Products that have 'blank' and 'No Region' in the REGION field
to 'None'.
Products |  | All US-offered Products
| 2000-08-15 | Test Next Month and Next Month + 1 Tokenized Reference Periods.
4615 and 4654 in TEST.
New Product Types |  | Physical Paper OCC #11
| 2000-08-16 | Need a Commodity/Deal Type-specific Product attribute for INCOterms.