## Sheet1
NEPCO PORTFOLIO
VAR BY MAJOR CATEGORY
$ x 1,000 | [22 empty] | DATA DATE: MAY 25, 2001
|  |  | REVENUES / FEES |  |  | MATL'S / EQUIPMENT |  |  | CONSTRUCTION |  |  | SCHED/PERF GUARANTEES |  |  | VAR (P95) |  |  |  | TOTAL | Warranty Guar.
|  |  | VAR (P95) |  |  | VAR (P95) |  |  | VAR (P95) |  |  | VAR (P95) |  |  | VAR (P95) |  |  |  | PROJECT VAR | VAR (P95)
| PROJECT NAME |  | DAILY |  | PROJECT LIFE | DAILY |  | PROJECT LIFE | DAILY |  | PROJECT LIFE | DAILY |  | PROJECT LIFE | Daily |  | Project Life |  |  | Daily |  | Project Life
| LS POWER, KENDALL |  | 37 | 474 | 805.547 | 18 | 474 | 391.8877 | 466 | 474 | 10145.5381 | 440 | 474 | 9579.4781 | 3 | 716 | 80.2745 | 474 | 13976 | 3 | 716 | 80.2745 |  |  | 474
| COGENTRIX, JENKS |  | 70 | 431 | 1524.0079 | 86 | 431 | 1872.3525 | 817 | 431 | 17787.349 | 71 | 431 | 1545.7794 | 9 | 612 | 222.6477 | 431 | 17185 | 9 | 612 | 222.6477 |  |  | 431
| DELL POWER |  | 100 | 736 | 2177.1541 | 404 | 736 | 8795.7026 | 338 | 736 | 7358.7809 | 175 | 736 | 3810.0197 | 32 | 736 | 868.1382 | 736 | 15333 | 32 | 736 | 868.1382 |  |  | 736
| MCADAMS POWER |  | 98 | 736 | 2133.611 | 402 | 736 | 8752.1595 | 330 | 736 | 7184.6085 | 168 | 736 | 3657.6189 | 32 | 736 | 868.1382 | 736 | 15106 | 32 | 736 | 868.1382 |  |  | 736
| AUSTIN PEAKERS |  | 12 | 187 | 261.2585 | 138 | 187 | 3004.4727 | 107 | 187 | 2329.5549 | 78 | 187 | 1698.1802 | 3 | 371 | 57.7841 | 187 | 2639 | 3 | 371 | 57.7841 |  |  | 187
| COYOTE SPRINGS |  | 42 | 644 | 914.4047 | 187 | 644 | 4071.2782 | 283 | 644 | 6161.3461 | 72 | 644 | 1567.551 | 1 | 828 | 28.775 | 644 | 8935 | 1 | 828 | 28.775 |  |  | 644
| LINDEN UNIT 6 |  | 22 | 361 | 478.9739 | 83 | 361 | 1807.0379 | 205 | 361 | 4463.1659 | 72 | 361 | 1567.551 | 11 | 543 | 256.326 | 361 | 4479 | 11 | 543 | 256.326 |  |  | 361
| WOLF HOLLOW POWER |  | 29 | 705 | 631.3747 | 21 | 705 | 457.2024 | 351 | 705 | 7641.8109 | 519 | 705 | 11299.4298 | 2 | 887 | 59.5651 | 705 | 16789 | 2 | 887 | 59.5651 |  |  | 705
| COGENTRIX, STERLINGTON |  | 95 | 187 | 2068.2964 | 117 | 187 | 2547.2703 | 154 | 187 | 3352.8173 | 188 | 187 | 4093.0497 | 3 | 371 | 57.7841 | 187 | 7219 | 3 | 371 | 57.7841 |  |  | 973
| COGENTRIX, SOUTHHAVEN |  | 136 | 644 | 2960.9296 | 200 | 644 | 4354.3082 | 502 | 644 | 10929.3136 | 183 | 644 | 3984.192 | 1 | 828 | 28.775 | 644 | 19204 | 1 | 828 | 28.775 |  |  | 1007
| PANDA, ARKANSAS |  | 313 | 361 | 6814.4924 | 461 | 361 | 10036.6804 | 798 | 361 | 17373.6898 | 630 | 361 | 13716.0709 | 11 | 543 | 256.326 | 361 | 36567 | 11 | 543 | 256.326 |  |  | 950
| PANDA, ARIZONA |  | 346 | 187 | 7532.9532 | 166 | 187 | 3614.0758 | 1149 | 187 | 25015.5007 | 631 | 187 | 13737.8424 | 3 | 371 | 57.7841 | 187 | 41784 | 3 | 371 | 57.7841 |  |  | 1043
| LS POWER, NELSON |  | 218 | 644 | 4746.196 | 553 | 644 | 12039.6622 | 684 | 644 | 14891.7341 | 196 | 644 | 4267.222 | 1 | 828 | 28.775 | 644 | 30267 | 1 | 828 | 28.775 |  |  | 1040
|  | TOTALS | 567.3059 |  | 12351.124 | 996.7236 |  | 21700.2095 | 2016.2177 |  | 43896.1674 | 1202.3365 |  | 26176.7179 | 49.1325 |  | 1307.9752 |  | 75912.5974 | 49.1325 |  | 1307.9752 |  | 91185.2845

## Sheet2
14.1421
| 1 | 2 | 3
Sigma | 10 | 20 | 14.1421
Var | 100 | 400 | 200