## Sheet1
NEPCO - Outstanding Projects
Percentage
Name | Capacity | Contract Amount | Completed* | Completion Date | Comments
Panda El Dorado (Arkansas) | 2,200 MW CCGT | $800.1MM | 49% | May 2003
Panda Gila River (Arizona) | 2,200 MW CCGT | $881.4MM | 27% | August 2003
LSP Nelson (Illinois) | 1,100 MW CCGT | $508.1MM | 26% | September 2003 | Joint Venture with PCL; 100% of revenues shown
LSP Kendall (Illinois) | 1,100 MW CCGT | $246.8MM | 74% | May 2002 | Joint Venture with Dick Corporation; only NEPCO's revenues shown
Cogentrix Green Power (Oklahoma) | 820 MW CCGT | 283.1MM | 98% | December 2001
Cogentrix Southhaven (Mississippi) | 820 MW CCGT | $327.0MM | 36% | July 2003
Cogentrix Sterlington (Louisiana) | 820 MW CCGT | $327.9MM | 80% | July 2002
AES Wolf Hollow (Texas) | 750MW CCGT | $298.9MM | 79% | August 2002
TPS Dell (Arkansas) | 600MW CCGT | $237.7MM | 65% | October 2002
TPS McAdams (Mississippi) | 600MW CCGT | $238.4MM | 65% | October 2002
Coyote Springs (Oregon) | 280MW CCGT | $122.7MM** | 76% | June 2002
Goldendale (Washington) | 248MW CCGT | $149.3MM | 73% | July 2002
Fountain Valley (Colorado) | 240MW Simple Cycle | $140.0MM | 100% | September 2001 | Expected completion in October 2001
Lake Worth (Florida) | 200MW CCGT Addition | $120.0MM | 32% | June 2003
Linden 6 (New Jersey) | 172MW Dual Fuel Cogen | $92.8MM | 97% | October 2001 | Expected completion December 2001
*As of September 30, 2001; includes procurement in percentage completed calculation
**Excludes Turbine
N.B. LSP Kendall, Cogentrix Green Power, and Linden 6 are projected to post aggregate losses of approximately $52MM; all other projects are projected to be profitable