## Sheet1
NETCO Integration testing on Friday 01/18.
Outstanding issues
| Area | Problem | Assigned | Status
| EnPower | PortCalc - when try to calc., connection refused. Connection is pointing to quark (estate hardware). This should be neptune (netco)! | David Poston | 4:00pm; In progress
| ERMS | Post Ids - (per Francis) - Ramesh said that numbers for post_id 1 is not right. This is a data problem. | Jeremy | Jemery will check where the data problem resides
| Gas | Known Balancing issue per Matt - | Matt Pena | Fri 5:15pm; In progress
| Global Replication | Contracts not going to Unify Gas - shadow tables not being populated | Jaikishore/ Sundar | Fri 5:15pm; In progress
| Global Replication | No Global replication info Unify financials | Jaikishore/ Sundar | Fri 5:15pm; In progress
| Power | EnPower deal replication to Unify - not able to load deals. CRD_Desk not populated in EnPower oracle table | Michael Berger/ David Poston | Fri 5:15pm; In progress
| Power Confirmations | TNS Server error 57541 | Schomer/ Kumaran | IT Fix in; not confirmed by user yet
| TAGG | Tagg web reports need to be checked to make sure it goes to the NETCO url | Sangeev Gupta | Open
Resolved Issues
| Area | Problem | Assigned | Status
| EnPower | Power Contract not showing in EnPower | D. Poston | Resolved
| EnPower | Curve managers do not launch | D. Poston | Resolved
| EOL bridge to EnPower | EOL Physical Deal Entry (ORA-03114 not connected to oracle) | D. Poston & EOL | Resolved
| Gas | Sitara to Unify - IM PB E 8 desk missing in Unify | Pena | Resolved
| Gas | FTP Server down for EDI (Cross roads) | M. Barber | Resolved
| Infrastructure | StartUp Script - (Tagg/ ERMS) RunM application needed to be added to startup script | Justin | Resolved
| Infrastructure | Terminal Server - not connecting to the NetCo platform. |  | Resolved
| Tagg/ Erms | Tagg settlement report - cannot connect to database (ORA-12154) | Francis Lim | Fri 5:15pm; In progress
| Tagg/ Erms | Tagg settlement report - does not run (error behind scene?) | Francis Lim
| Infrastructure | Our RisktRAC application does not recognize network IDs that are greater than 10 characters in length. | Champion, Andrew | Resolved
| Infrastructure | When she attempted to run the RisktRAC application (Start/Programs/Business Applications/RisktRAC) she ran into script error messages indicating access was denied to a folder or directory, which means her ID was missing a network group for a directory that the install script is dependent on | Champion, Andrew | Resolved
Request for next week
1) To activate both phones in room: 2521. We will need this for next week.