## Sheet1
NETCO Integration testing on Friday 01/22
Outstanding issues
| Area | Problem | Assigned | Status
1
2
3
4
Resolved Issues
| Area | Problem | Assigned | Status
1 | EnPower/ Canada | Kathy Reeves; Deal Entry; no access to deal leg seqment… Bug in deal entry? | David Poston/ Pete Davis | Resolved
2 | Global Data setup | Wade Price/ Unify Settlements - Missing Partner Bank Type for External Address Id 49863. This is needed to finalize the supply statement in Unify | Sundar | Resolved
3 | Global Data setup/ Replication | Unify Power - missing addresses |  | Resolved
4 | Infrastructure | Gas/ Canada/ Trading Cluster/ Tagg/ PortCalc. No Xterm login under Tagg Menu. This is needed for RunM unix connection. | Brian Larkin | IT Closed; Awaiting re-test from user.
5 | Infrastructure | Gas/ Canada/ Trading Cluster/ Tagg/ PortCalc. No Xterm login under CPR Menu. This is needed for RunM unix connection. | Brian Larkin | IT Closed; Awaiting re-test from user.
6 | Power Confirms/ Global Data setup | Power/ No address confirms for ENA Corp. | Sundar | IT Closed; Awaiting re-test from user.
7 | Tagg | Tagg Settlements report not working | Francis Lim; Brian Larkin | Resolved
8 | Tagg-Metacalc | Tagg-Metacalc-- Error Message: ORA-12154: TNS:could not resolve service name | Lim, Francis S. | IT Closed; Awaiting re-test from user.
9 | Unify (all) | Unable to xmit to SAP. Unify was executing older exe code (dated 1/10/02), when should have been executing revised (dated 01/18/02), that included the SAP changes. Infrastructure resolved migration script and repushed NetCo O:\ to W:\ for Unify EXE code. | Brian Larkin/ Jayanta | Resolved
10 | Unify Financial Settlements | Region Codes missing. Need CHIC and Financial. Cindy Clark will add. | DA group; Cindy Clark | Resolved
11 | Unify Financial Settlements/ Infrastructure | Need neptune directories added. Unify weblogic; missing to SQL Server drivers. | Cindy Clark/ Infrastructure | Resolved
12 | Unify Gas | Tammy Jacquet/ screen (stored procedure) permissions issue - scheduled quantity screen | Pena/ Ben | Resolved
13 | Unify Gas | Chris Spears; unable to see Tennessee Gas Pipeline (or any) under Service Verifications list screen. | Matt Pena | Resolved
14 | Unify Gas/ DBAs | Transport contract (20000057) not replicating to Unify | Pena/ Jaikishore | Resolved
15 | Unify Power | 1st error - Deal load Error: (%ls conflicted with %ls constraint) | Lori | Resolved
16 | Unify Power | 2nd error - DB error on EnPower deal load (%ls conflicted with %ls constraint) | Lori Boudreaux | Resolved