## TX Power Plants Master
[10 empty] | PEC | Planning, Engineering, and Construction |  |  | SGA | ERCOT Summery Genetation Additions
[10 empty] | MPS | Merchant Power Scoreboard |  |  | ERCOT | ERCOT Homepage
Map # | Operator | Name | County/City | Address | Zip | Parent Co. | Fuel | Turbine | Permit | Phase 1 Cap (MW) | Min | Max | Online Date | Cost $ Mil. | Status | Gas Supplier | Gas KTR Term | Stage | Connected Pipes | Distance to HPL | Comments | Developer/Engineer | Map | Phone # | Last updated | PEC | NewGen | MPS | SGA | ERCOT | POWERdat | Other
4 | Texas Independent Energy | Archer Power Partners | Wichita/Wichita Falls |  | 76301 |  | NATURAL GAS |  | Pending | 1000 | 144000 | 180000 | 2002-06-01 | 300 | Planned |  |  | E1 (20) |  |  | Construction kick-off Sep. '00 | Dick Camp | Y | 9724552980 | 2000-02-28 | X | X | X | X
6 | Lamar Power Partners, L.P. | Lamar Power Project | Lamar/Paris |  |  |  | NATURAL GAS | GE MS7001FA | Y | 1000 | 144000 | 180000 | 2000-06-01 | 150 | Under Constr | [7 empty] | Y |  | 2000-02-28 |  | X |  | X | X
7 | Garland Power & Light System | Ray Olinger | Collin/Nevada | 13835 Country Road 489 | 75173-6033 |  | NATURAL GAS | GE 7EA | Pending | 85 | 12240 | 15300 | 2000-06-01 | 20 | Planned |  |  | E2 (20) |  |  | Could possibly be operating | Tom Sheppard | N | 9138310833 | 2000-02-28 | X | X
8 | Ennis-Tractebel Power Co., Inc. | Ennis-Tractebel Power Project | Ellis/Ennis | US Hoghway 287 West | 75119 |  | NATURAL GAS, WASTE HEAT | Siemens 501-G | Y | 350 | 50400 | 63000 | 2001-12-01 | 200 | Planned |  |  | E2 (20) |  |  | Just broke ground | Jim Kemp | Y | 7135522000 | 2000-02-28 | X | X |  | X | X
9 | American National Power, Inc. | Midlothian Project | Ellis/Midlothian | 5000 V V Jones (Venus, TX) | 76084 |  | NATURAL GAS | ABB GT24 | Y | 1650 | 237600 | 297000 | 2000-06-01 | 350 | Under Constr |  |  | P2 (19) |  |  |  | Neal Parece | Y | 8047632000 | 2000-02-28 | X | X | 1100 MW | 1100 MW + 550 MW | 1000 MW
10 | Texas Independent Energy | Panda Guadalupe Power Plant | Guadalupe/Marion | 5740 Weil Road | 78124 |  | NATURAL GAS |  | Y | 1000 | 144000 | 180000 | 2001-12-01 | 200 | Under Constr |  |  | E2 (22) |  |  |  | Brad Frieson | Y | 9493492000 | 2000-02-28 | X | X | 740 MW | X
11 | San Antonio Public Service | Arthur van Rosenberg | Bexar/San Antonio |  |  |  | NATURAL GAS, WASTE HEAT | GE 7EA | Y | 539 | 77616 | 97020 | 2000-05-01 | 166 | Under Constr | [7 empty] | Y |  | 2000-02-28 |  | X |  | 540 MW | X
12 | Tenaska, Inc. | Frontier Generation Station | Grimes/Shiro |  |  |  | NATURAL GAS | GE MS7001FA | Y | 830 | 119520 | 149400 | 2000-06-01 | 380.7 | Under Constr | [7 empty] | N |  | 2000-02-28 |  | X | X | X | X |  | Web Page
13 | Reliant Energy Power Generation, Inc. | Equistar Channelview | Harris/Channelview | 9802 Fairmont Parkway | 77507 |  | NATURAL GAS |  | Pending | 750 | 108000 | 135000 | 2001-01-01 | 0 | Planned | [7 empty] | Y |  | 2000-02-28 |  | X |  | 820 MW
14 | Calpine Corp. | Pasadena Power Plant | Harris/Pasadena | 955 Phillips Rd. | 77505 |  | NATURAL GAS, WASTE HEAT | Siemens 501-F | Y | 240 | 34560 | 43200 | 1999-06-01 | 131 | Operating | [7 empty] | Y |  | 2000-02-28 |  | X | 510 MW (total 750) | X
14 | Calpine Corp. | Pasadena Power Plant II | Harris/Pasadena | 956 Phillips Rd. | 77506 |  | NATURAL GAS |  | N | 545 | 78480 | 98100 | 2000-06-01 |  | Under Constr | [7 empty] | Y |  | 2000-02-28 |  | X |  | 500 |  |  | Calpine Web Page
15 | Dynegy, Inc. | Lyondell | Harris/Houston | 10801 Choate Road | 77507 |  | NATURAL GAS | Siemens 501-F | Y | 155 | 22320 | 27900 | 2000-06-01 | 0 | Planned | [7 empty] | Y |  | 2000-02-28 |  | X | X | X
16 | BASF Corp. | Freeport | Brazoria/Freeport |  |  |  | NATURAL GAS | GE 7EA | Y | 92 | 13248 | 16560 | 1999-06-01 |  | Operating | [7 empty] | Y |  | 2000-02-28 |  | X
17 | Sweeny Cogeneration, L.P. | Sweeny Cogeneration Facility | Brazoria/Old Ocean |  |  |  | NATURAL GAS | Siemens 501D5A | Y | 390 | 56160 | 70200 | 1999-06-01 | 190 | Operating | [7 empty] | Y |  | 2000-02-28 |  | X
20 | Diamond Shamrock/Dynegy | Uds Project | Live Oak/Three Rivers | Leroy Street | 78071 |  | NATURAL GAS |  | Y | 750 | 108000 | 135000 | 2003-04-01 | 300 | Planned |  |  | P1 (02) |  |  |  | Doug Eagan | Y | 3012806800 | 2000-02-28 | X | X | X
22 | Gregory Power Partners, L.P. | Gregory Power Facility | San Patricio/Gregory |  |  |  | NATURAL GAS |  | Y | 336 | 48384 | 60480 | 2000-06-01 | 229 | Under Constr | [7 empty] | N |  | 2000-02-28 |  | X | 300-400 MW | 350 MW
24 | Duke | Hidalgo Energy Facility | Hidalgo/Edinburg |  |  |  | NATURAL GAS |  | Y | 510 | 73440 | 91800 | 2000-05-01 | 300 | Under Constr | [5 empty] | Ground broken 2/4/99 |  | Y |  | 2000-02-28 |  | X | 500 MW | 520 MW | X
25 | Calpine Corp. | Magic Valley Power Plant | Hildalgo/Edinburg |  |  |  | NATURAL GAS | Siemens 501G | Y | 730 | 105120 | 131400 | 2001-02-01 |  | Under Constr | [7 empty] | Y |  | 2000-02-28 |  | X |  | 700 | 700 |  | Calpine Web Page
26 | American National Power, Inc. | Edinburg Plant | Hildalgo/Edinburg |  |  |  | NATURAL GAS |  | Y | 1000 | 144000 | 180000 | 2001-06-01 | 450 | Planned | [7 empty] | N |  | 2000-02-28 |  | X | X | 815 MW
27 | CSW Energy, Inc. | Frontera Plant | Hildalgo/Mission |  |  |  | NATURAL GAS, WASTE HEAT | GE 7FA | Y | 330 | 47520 | 59400 | 1999-06-01 |  | Operating | [7 empty] | N |  | 2000-02-28 |  | X |  | 500 MW
28 | SkyGen Services | Corpus Christi Energy Center | Nueces/Corpus Christi | Nueces Boulevard | 78401 |  | NATURAL GAS |  | Pending | 500 | 72000 | 90000 | 2002-01-01 | 200 | Planned |  |  | E2 (20) |  |  |  | Dan Thompson | Y | 8475599800 | 2000-02-28 | X | X | 500 MW | 700 MW
29 | Texas Independent Energy | Odessa-Ector Power Partners | Ector/Odessa | Off IH 20 South Industrial Park | 79760 |  | NATURAL GAS |  | Y | 1000 | 144000 | 180000 | 2002-04-01 | 300 | Under Constr |  |  | E2 (25) |  |  |  | Rick Long | Y | 9493492000 | 2000-02-28 | X | X | X | X
30 | Constellation/Pace | Rio Nogales | Guadalupe/Seguin |  |  |  | NATURAL GAS, WASTE HEAT | GE 7FA | Pending | 750 | 108000 | 135000 | 2002-06-01 | 200 | Planned | [7 empty] | Y |  | 2000-02-28 |  | X | 750 MW | 800 MW
31 | Constellation/Pace | Gateway | Upshur/Gilmer | Highway 271 North | 75644 |  | NATURAL GAS | GE 7FA | Pending | 800 | 115200 | 144000 | 2001-12-01 | 400 | Planned |  |  | P2 (18) |  |  | Construction kick-off May '00 | Douglas Perry | Y | 4102304600 | 2000-02-28 | X |  |  | 800 MW
32 | Calpine Corp. | Lost Pines I | Bastrop/Bastrop |  |  |  | NATURAL GAS, WASTE HEAT | Siemens 501F-D | Y | 545 | 78480 | 98100 | 2001-06-01 | 225 | Under Constr | [7 empty] | N |  | 2000-02-28 |  | X | 500 | 500 | 500 |  | Calpine Web Page
33 | Donohue Paper | Sheldon | Harris/Houston | 11611 5th | 77044 |  | NATURAL GAS |  | Y | 200 | 28800 | 36000 | Unknown |  | Planned | [7 empty] | Y |  | 2000-02-28
34 | Calpine Corp. | Baytown Bayer Power Plant | Harris/Baytown | 8500 West Bay Road | 77521 |  | NATURAL GAS, WASTE HEAT | Siemens 501F | Pending | 800 | 115200 | 144000 | 2001-01-01 | 335 | Planned |  |  | E2 (21) |  |  | Construction kick-off Feb. '00 | Lloyd Huffman | Y | 7138302000 | 2000-02-28 | X | X | X | X
35 | Calpine/Mobil | Beaumont Refinery | Beaumont | 1795 Burt Street | 77701 |  | NATURAL GAS |  | N | 550 | 79200 | 99000 | Unknown |  | Planned | [7 empty] | Y |  | 2000-02-28
38 | American National Power, Inc. | San Marcos | Hays/San Marcos | 1601 Francis Harris Lane | 78666 |  | NATURAL GAS | ABB Alstom | Y | 1100 | 158400 | 198000 | 2001-06-01 |  | Under Constr | [7 empty] | Y |  | 2000-02-28 |  | X |  | X | X
39 | American National Power, Inc. | Beaumont | Jefferson/Beaumont | Industrial Road | 77705 |  | NATURAL GAS |  | N | 550 | 79200 | 99000 | 2003-06-01 | 250 | Planned |  |  | P1 (01) |  |  | Not ANP |  | N |  | 2000-02-28 | X
40 | American National Power, Inc. | Harris Co. Energy Facility | Harris/Houston | East Beltway 8 | 77001 |  | NATURAL GAS | ABB GT24 | Pending | 2200 | 316800 | 396000 | 2004-06-01 | 750 | Under Constr |  |  | P2 (18) |  |  | Kick-off in phases | Dave Sarles | N | 8047632000 | 2000-02-28 | X |  |  | 2200 MW
41 | American National Power, Inc. | El Paso | El Paso/El Paso | Stan Roberts Sr Avenue | 79936 |  | NATURAL GAS | ABB GT24 | Pending | 600 | 86400 | 108000 | 2002-06-01 | 400 | Planned |  |  | E2 (22) |  |  | Construction kick-off June '00 | Paul Wiecek | N | 8047632000 | 2000-02-28 | X
43 | Tenaska, Inc. | Gateway Generating Station | Rusk/Henderson | State Highway 315 & FM 840 | 75681 |  | NATURAL GAS | GE 7FA | Y | 845 | 121680 | 152100 | 2001-05-01 | 300 | Under Constr |  |  | E2 (26) |  |  | Started construction March '00 | Morgan Fagan | Y | 9134582000 | 2000-02-28 | X | X | 830 MW | 830 MW | X
44 | Conoco Global Power | Orange Sabine River | Orange/Orange | FM 1006 | 77630 |  | NATURAL GAS | GE 7FA | Y | 400 | 57600 | 72000 | 2001-03-01 | 200 | Planned |  |  | E2 (26) |  |  | Start construction April '00 | Chuck Foltyn | Y | 3014173000 | 2000-02-28 | X | X
48 | Calpine Corp. | Channel Energy Center | Harris/Houston | 12000 Lawndale Street | 77017 |  | NATURAL GAS |  | N | 560 | 80640 | 100800 | 2001-08-01 | 250 | Planned |  |  | P2 (18) |  |  | Construction kick-off Aprril '00 | Gary Devore | Y | 7138302000 | 2000-02-28 | X | X
49 | Calpine Corp. | Clear Lake Cogeneration LTD | Harris/Pasadena | 9602 Bayport Road | 77507 |  | NATURAL GAS |  | Y | 35 | 5040 | 6300 | 1999-06-01 | 0 | Operating | [7 empty] | Y |  | 2000-02-28 |  | X
50 | Cobisa Corp. | Forney | Kaufman/Forney | Forney Industrial Park | 75126 |  | NATURAL GAS |  | Y | 1500 | 216000 | 270000 | 2002-12-01 | 500 | Planned |  |  | P2 (18) |  |  | Construction kick-off Oct. '00 | Greg Platt | Y | 7139328070 | 2000-02-28 | X | X |  | 1680 MW
51 | CSW Energy, Inc. | Eastex Cogeneration Facility | Gregg/Longview |  |  |  | NATURAL GAS | GE 7F | Y | 440 | 63360 | 79200 | 2001-06-01 | 200 | Planned |  |  | E2 (25) |  |  | Construction kick-off Feb. '00 | Robert Riser | Y | 7139469040 | 2000-02-28 | X | X
52 | Duke | Mesquite | Dallas/Mesquite | Country Road 200 | 75149 |  | NATURAL GAS | GE 7FA | Pending | 440 | 63360 | 79200 | 2001-10-01 | 150 | Planned |  |  | P2 (18) |  |  | Construction kick-off May '00 | John Snyder | Y | 7044262000 | 2000-02-28 | X | X |  | 440 MW
53 | Entergy Gulf States, Inc. | Freestone | Freestone/Fairfield | Off Ranch Road 488 | 75840 |  | NATURAL GAS | GE 7FA | Pending | 800 | 115200 | 144000 | 2002-05-01 | 325 | Planned |  |  | E2 (22) |  |  | Construction kick-off Mar. '00 | Paul Lehning | Y | 7704477700 | 2000-02-28 | X | X |  | 500 + 600 MW | 1050 MW
54 | K N Power Co. | Decatur | Wise/Decator |  |  |  | NATURAL GAS |  | N | 510 | 73440 | 91800 | 2002-01-01 | 0 | Planned | [7 empty] | Y |  | 2000-02-28 |  | X | X | X | X
55 | LG&E Power, Inc. | Anderson | Anderson/Palestine | 1/4 Mile SW US ighway 79 & FM RD 2574 | 75801 |  | NATURAL GAS |  | Pending | 1600 | 230400 | 288000 | 2003-04-01 | 525 | Planned |  |  | P2 (18) |  |  | Construction kick-off Jan. '01 | Jim Frances | Y | 7142414700 | 2000-02-28 | X | X |  | X
59 | Duke | Jack | Jack/Jacksboro | Off Highway 281 | 76458 |  | NATURAL GAS | GE 7FA | Pending | 540 | 77760 | 97200 | 1/1/2002 | 250 | Planned |  |  | P1 (08) |  |  | Construction kick-off June '00 | John Snyder | Y | 7044262000 | 2000-02-28 | X | X | 250 MW | X
60 | Coastal/FP&L | Bastrop Clean Air Project | Bastrop/Bastrop | Bastrop Industrial Park | 78602 |  | NATURAL GAS |  | Pending | 550 | 79200 | 99000 | 12/1/2001 | 200 | Planned |  |  | P2 (19) |  |  | Construction kick-off Mar. '00 | Alan Rugh | Y | 71387776734 | 2000-02-28 | X |  |  | X
61 | American National Power, Inc. | Mont Belvieu | Chambers/Mont Belvieu |  |  |  | NATURAL GAS |  | N | 1100 | 158400 | 198000 | 2001/02 |  | Planned | [5 empty] | Development |  | N |  | 2000-02-28 |  |  |  | X
62 | Duke | Temple | Bell/Temple | Southeast Industrial Park | 76501 |  | NATURAL GAS |  | N | 520 | 74880 | 93600 | 12/1/2001 | 200 | Planned |  |  | P1 (16) |  |  | Construction kick-off June '00 | John Snyder | Y | 7044262000 | 2000-02-28 | X |  |  | X
64 | Southern Company | Weatherford | Parker/Weatherford | Weatherford Industrial Park | 76086 |  | NATURAL GAS |  | N | 650 | 93600 | 117000 | 4/1/2002 | 200 | Planned |  |  | P1 (04) |  |  | Construction kick-off Oct. '00 | Jack Bayer | Y | 7703797000 | 2000-02-28 | X |  |  | X
65 | Tractebel | Decatur | Wise/Decator | Off US Highway 380 | 76234 |  | NATURAL GAS |  | N | 800 | 115200 | 144000 | 6/1/2002 | 350 | Planned |  |  | P1 (08) |  |  | Construction kick-off July '00 | Bill Julian | N | 7135522000 | 2000-02-28 | X |  | 350 MW | 700 MW | X
66 | Southern Company | Clifton | Bosque/Clifton | Off FM Road 219 & Highway 22 | 76634 |  | NATURAL GAS |  | N | 525 | 75600 | 94500 | 2001-02-01 | 100 | Planned |  |  | E2 (22) |  |  | Construction kick-off Apr. '00 | Tim Berrigan | Y | 7703797000 | 2000-02-28 | X |  |  |  | X
67 | AES | Aurora | Granbury/Hood Co. |  |  |  | NATURAL GAS |  | N | 730 | 105120 | 131400 | 6/1/2002 | 400 | Planned |  |  | E1 (20) |  |  | Construction kick-off June '00 | Tim Libson | Y | 5123069068 | 2000-02-28 | X |  |  | X
68 | South Texas Electric Coop | Nusery Sam Rayburn | Victoria/Nersery | FM 447 | 77976 |  | NATURAL GAS |  | N | 80 | 11520 | 14400 | 6/1/2001 | 40 | Planned |  |  | P2 (19) |  |  | Construction kick-off Apr. '00 | Darrell Klimitchek | Y | 3615756491 | 2000-02-28 | X
69 | K N Power Co. | Harris Co. Merchant Power Plant | Harris/Humble | North Harris County off Hwy 59 North | 77338 |  | NATURAL GAS |  | N | 512 | 73728 | 92160 | 2002-12-01 | 200 | Planned |  |  | P1 (02) |  |  | Construction kick-off Jan. '01 | Paul Steinway | N | 3038573100 | 2000-02-28 | X
70 | Dynegy, Inc. | Mont Belvieu | Chambers/Mont Belvieu | 10319 Highway 146 | 77580 |  | NATURAL GAS |  | N | 250 | 36000 | 45000 | 6/1/2001 | 150 | Planned |  |  | P1 (06) |  |  | Construction kick-off Aug. '00 | Bob Taylor | Y | 7137354000 | 2000-02-28 | X
71 | LG&E Power, Inc. | Sulphur Springs | Hopkins/Sulphur Springs |  |  |  | NATURAL GAS |  | N | 800 | 115200 | 144000 | 2005-01-01 |  | Planned | [7 empty] | N |  | 2000-02-28 | [6 empty] | Talked with LG&E
72 | Reliant/Air Liquide | Sabine Cogeneration Facility | Orange/Orange | F.M. 1006 | 77631 |  | NATURAL GAS |  | N | 100 | 14400 | 18000 | 2000-02-01 |  | Under Constr | [7 empty] | Y |  | 2000-02-28 |  | X
[7 empty] | TOTAL |  |  | 36164 | 5207616 | 6509520
Note on A11: Not Exactly sure of location
Note on A34: This plant is not ANP. Not sure if it exists.
Note on A51: Map Estimated
Note on B40: Clear Lake Cogeneration, L.P.

## Weight
Map # | Operator | Name | Strength of Developer Parent | Permits (Stage) |  | Dispatchability | Degree of Captivity | Probable Online Timing | Capital Commitment to Date | Customer Relationship | ERCOT Approval | Ranking
Weight |  |  | 20 | 10 |  | 20 | 20 | 10 | 10 | 5 | 5
|  |  |  | Air | Water
4 | Texas Independent Energy | Archer Power Partners |  | Pending
6 | Lamar Power Partners, L.P. | Lamar Power Project |  | Y
7 | Garland Power & Light System | Ray Olinger |  | Pending
8 | Ennis-Tractebel Power Co., Inc. | Ennis-Tractebel Power Project |  | Y
9 | American National Power, Inc. | Midlothian Project |  | Y
10 | Texas Independent Energy | Panda Guadalupe Power Plant |  | Y
11 | San Antonio Public Service | Arthur van Rosenberg |  | Y
12 | Tenaska, Inc. | Frontier Generation Station |  | Y
13 | Reliant Energy Power Generation, Inc. | Equistar Channelview |  | Pending
14 | Calpine Corp. | Pasadena Power Plant |  | Y
14 | Calpine Corp. | Pasadena Power Plant II |  | N
15 | Dynegy, Inc. | Lyondell |  | Y
16 | BASF Corp. | Freeport |  | Y
17 | Sweeny Cogeneration, L.P. | Sweeny Cogeneration Facility |  | Y
20 | Diamond Shamrock/Dynegy | Uds Project |  | Y
22 | Gregory Power Partners, L.P. | Gregory Power Facility |  | Y
24 | Duke | Hidalgo Energy Facility |  | Y
25 | Calpine Corp. | Magic Valley Power Plant |  | Y
26 | American National Power, Inc. | Edinburg Plant |  | Y
27 | CSW Energy, Inc. | Frontera Plant |  | Y
28 | SkyGen Services | Corpus Christi Energy Center |  | Pending
29 | Texas Independent Energy | Odessa-Ector Power Partners |  | Y
30 | Constellation/Pace | Rio Nogales |  | Pending
31 | Constellation/Pace | Gateway |  | Pending
32 | Calpine Corp. | Lost Pines I |  | Y
33 | Donohue Paper | Sheldon |  | Y
34 | Calpine Corp. | Baytown Bayer Power Plant |  | Pending
35 | Calpine/Mobil | Beaumont Refinery |  | N
38 | American National Power, Inc. | San Marcos |  | Y
39 | American National Power, Inc. | Beaumont |  | N
40 | American National Power, Inc. | Harris Co. Energy Facility |  | Pending
41 | American National Power, Inc. | El Paso |  | Pending
43 | Tenaska, Inc. | Gateway Generating Station |  | Y
44 | Conoco Global Power | Orange Sabine River |  | Y
48 | Calpine Corp. | Channel Energy Center |  | N
49 | Calpine Corp. | Clear Lake Cogeneration LTD |  | Y
50 | Cobisa Corp. | Forney |  | Y
51 | CSW Energy, Inc. | Eastex Cogeneration Facility |  | Y
52 | Duke | Mesquite |  | Pending
53 | Entergy Gulf States, Inc. | Freestone |  | Pending
54 | K N Power Co. | Decatur |  | N
55 | LG&E Power, Inc. | Anderson |  | Pending
59 | Duke | Jack |  | Pending
60 | Coastal/FP&L | Bastrop Clean Air Project |  | Pending
61 | American National Power, Inc. | Mont Belvieu |  | N
62 | Duke | Temple |  | N
64 | Southern Company | Weatherford |  | N
65 | Tractebel | Decatur |  | N
66 | Southern Company | Clifton |  | N
67 | AES | Aurora |  | N
68 | South Texas Electric Coop | Nusery Sam Rayburn |  | N
69 | K N Power Co. | Harris Co. Merchant Power Plant |  | N
70 | Dynegy, Inc. | Mont Belvieu |  | N
71 | LG&E Power, Inc. | Sulphur Springs |  | N
72 | Reliant/Air Liquide | Sabine Cogeneration Facility |  | N

## Map
Proposed Texas IPPs 1999-2003
Map # | Operator | Name | County/City | Fuel | Phase 1 Cap (MW) | Min | Max | Online Date | Status | On HPL: 0 = No, 1 =- Yes | Likely: 0 = No, 1 = Yes
4 | Texas Independent Energy | Archer Power Partners | Wichita/Wichita Falls | NATURAL GAS | 1000 | 144000 | 180000 | 2002-06-01 | Planned | 0 | 0
6 | Lamar Power Partners, L.P. | Lamar Power Project | Lamar/Paris | NATURAL GAS | 1000 | 144000 | 180000 | 2000-06-01 | Under Constr | 1 | 1
7 | Garland Power & Light System | Ray Olinger | Collin/Nevada | NATURAL GAS | 85 | 12240 | 15300 | 2000-06-01 | Planned | 0 | 0
8 | Ennis-Tractebel Power Co., Inc. | Ennis-Tractebel Power Project | Ellis/Ennis | NATURAL GAS, WASTE HEAT | 350 | 50400 | 63000 | 2001-12-01 | Planned | 0 | 0
9 | American National Power, Inc. | Midlothian Project | Ellis/Midlothian | NATURAL GAS | 1650 | 237600 | 297000 | 2000-06-01 | Under Constr | 0 | 0
10 | Texas Independent Energy | Panda Guadalupe Power Plant | Guadalupe/Marion | NATURAL GAS | 1000 | 144000 | 180000 | 2001-12-01 | Under Constr | 1 | 0
11 | San Antonio Public Service | Arthur van Rosenberg | Bexar/San Antonio | NATURAL GAS, WASTE HEAT | 539 | 77616 | 97020 | 2000-05-01 | Under Constr | 1 | 1
12 | Tenaska, Inc. | Frontier Generation Station | Grimes/Shiro | NATURAL GAS | 830 | 119520 | 149400 | 2000-06-01 | Under Constr | 1 | 1
13 | Reliant Energy Power Generation, Inc. | Equistar Channelview | Harris/Channelview | NATURAL GAS | 750 | 108000 | 135000 | 2001-01-01 | Planned | 1 | 1
14 | Calpine Corp. | Pasadena Power Plant | Harris/Pasadena | NATURAL GAS, WASTE HEAT | 240 | 34560 | 43200 | 1999-06-01 | Operating | 1 | 1
14 | Calpine Corp. | Pasadena Power Plant II | Harris/Pasadena | NATURAL GAS | 545 | 78480 | 98100 | 2000-06-01 | Under Constr | 1 | 1
15 | Dynegy, Inc. | Lyondell | Harris/Houston | NATURAL GAS | 155 | 22320 | 27900 | 2000-06-01 | Planned | 1 | 1
16 | BASF Corp. | Freeport | Brazoria/Freeport | NATURAL GAS | 92 | 13248 | 16560 | 1999-06-01 | Operating | 1 | 1
17 | Sweeny Cogeneration, L.P. | Sweeny Cogeneration Facility | Brazoria/Old Ocean | NATURAL GAS | 390 | 56160 | 70200 | 1999-06-01 | Operating | 1 | 1
20 | Diamond Shamrock/Dynegy | Uds Project | Live Oak/Three Rivers | NATURAL GAS | 750 | 108000 | 135000 | 2003-04-01 | Planned | 1 | 1
22 | Gregory Power Partners, L.P. | Gregory Power Facility | San Patricio/Gregory | NATURAL GAS | 336 | 48384 | 60480 | 2000-06-01 | Under Constr | 1 | 1
24 | Duke | Hidalgo Energy Facility | Hidalgo/Edinburg | NATURAL GAS | 510 | 73440 | 91800 | 2000-05-01 | Under Constr | 0 | 0
25 | Calpine Corp. | Magic Valley Power Plant | Hildalgo/Edinburg | NATURAL GAS | 730 | 105120 | 131400 | 2001-02-01 | Under Constr | 0 | 0
26 | American National Power, Inc. | Edinburg Plant | Hildalgo/Edinburg | NATURAL GAS | 1000 | 144000 | 180000 | 2001-06-01 | Planned | 0 | 1
27 | CSW Energy, Inc. | Frontera Plant | Hildalgo/Mission | NATURAL GAS, WASTE HEAT | 330 | 47520 | 59400 | 1999-06-01 | Operating | 0 | 0
28 | SkyGen Services | Corpus Christi Energy Center | Nueces/Corpus Christi | NATURAL GAS | 500 | 72000 | 90000 | 2002-01-01 | Planned | 1 | 1
29 | Texas Independent Energy | Odessa-Ector Power Partners | Ector/Odessa | NATURAL GAS | 1000 | 144000 | 180000 | 2002-04-01 | Under Constr | 0 | 0
30 | Constellation/Pace | Rio Nogales | Guadalupe/Seguin | NATURAL GAS, WASTE HEAT | 750 | 108000 | 135000 | 2002-06-01 | Planned | 1 | 1
31 | Constellation/Pace | Gateway | Upshur/Gilmer | NATURAL GAS | 800 | 115200 | 144000 | 2001-12-01 | Planned | 1 | 1
32 | Calpine Corp. | Lost Pines I | Bastrop/Bastrop | NATURAL GAS, WASTE HEAT | 545 | 78480 | 98100 | 2001-06-01 | Under Constr | 1 | 0
33 | Donohue Paper | Sheldon | Harris/Houston | NATURAL GAS | 200 | 28800 | 36000 | Unknown | Planned | 1 | 1
34 | Calpine Corp. | Baytown Bayer Power Plant | Harris/Baytown | NATURAL GAS, WASTE HEAT | 800 | 115200 | 144000 | 2001-01-01 | Planned | 1 | 1
35 | Calpine/Mobil | Beaumont Refinery | Beaumont | NATURAL GAS | 550 | 79200 | 99000 | Unknown | Planned | 1 | 1
38 | American National Power, Inc. | San Marcos | Hays/San Marcos | NATURAL GAS | 1100 | 158400 | 198000 | 2001-06-01 | Under Constr | 1 | 0
39 | American National Power, Inc. | Beaumont | Jefferson/Beaumont | NATURAL GAS | 550 | 79200 | 99000 | 2003-06-01 | Planned | 1 | 1
40 | American National Power, Inc. | Harris Co. Energy Facility | Harris/Houston | NATURAL GAS | 2200 | 316800 | 396000 | 2004-06-01 | Under Constr | 1 | 1
41 | American National Power, Inc. | El Paso | El Paso/El Paso | NATURAL GAS | 600 | 86400 | 108000 | 2002-06-01 | Planned | 0 | 0
43 | Tenaska, Inc. | Gateway Generating Station | Rusk/Henderson | NATURAL GAS | 845 | 121680 | 152100 | 2001-05-01 | Under Constr | 1 | 0
44 | Conoco Global Power | Orange Sabine River | Orange/Orange | NATURAL GAS | 400 | 57600 | 72000 | 2001-03-01 | Planned | 1 | 1
48 | Calpine Corp. | Channel Energy Center | Harris/Houston | NATURAL GAS | 560 | 80640 | 100800 | 2001-08-01 | Planned | 1 | 1
49 | Calpine Corp. | Clear Lake Cogeneration LTD | Harris/Pasadena | NATURAL GAS | 35 | 5040 | 6300 | 1999-06-01 | Operating | 1 | 1
50 | Cobisa Corp. | Forney | Kaufman/Forney | NATURAL GAS | 1500 | 216000 | 270000 | 2002-12-01 | Planned | 0 | 0
51 | CSW Energy, Inc. | Eastex Cogeneration Facility | Gregg/Longview | NATURAL GAS | 440 | 63360 | 79200 | 2001-06-01 | Planned | 1 | 1
52 | Duke | Mesquite | Dallas/Mesquite | NATURAL GAS | 440 | 63360 | 79200 | 2001-10-01 | Planned | 0 | 0
53 | Entergy Gulf States, Inc. | Freestone | Freestone/Fairfield | NATURAL GAS | 800 | 115200 | 144000 | 2002-05-01 | Planned | 0 | 0
54 | K N Power Co. | Decatur | Wise/Decator | NATURAL GAS | 510 | 73440 | 91800 | 2002-01-01 | Planned | 0 | 0
55 | LG&E Power, Inc. | Anderson | Anderson/Palestine | NATURAL GAS | 1600 | 230400 | 288000 | 2003-04-01 | Planned | 0 | 0
59 | Duke | Jack | Jack/Jacksboro | NATURAL GAS | 540 | 77760 | 97200 | 1/1/2002 | Planned | 0 | 0
60 | Coastal/FP&L | Bastrop Clean Air Project | Bastrop/Bastrop | NATURAL GAS | 550 | 79200 | 99000 | 12/1/2001 | Planned | 1 | 1
61 | American National Power, Inc. | Mont Belvieu | Chambers/Mont Belvieu | NATURAL GAS | 1100 | 158400 | 198000 | 2001/02 | Planned | 1 | 1
62 | Duke | Temple | Bell/Temple | NATURAL GAS | 520 | 74880 | 93600 | 12/1/2001 | Planned | 0 | 0
64 | Southern Company | Weatherford | Parker/Weatherford | NATURAL GAS | 650 | 93600 | 117000 | 4/1/2002 | Planned | 0 | 0
65 | Tractebel | Decatur | Wise/Decator | NATURAL GAS | 800 | 115200 | 144000 | 6/1/2002 | Planned | 0 | 0
66 | Southern Company | Clifton | Bosque/Clifton | NATURAL GAS | 525 | 75600 | 94500 | 2001-02-01 | Planned | 0 | 0
67 | AES | Aurora | Granbury/Hood Co. | NATURAL GAS | 730 | 105120 | 131400 | 6/1/2002 | Planned | 0 | 0
68 | South Texas Electric Coop | Nusery Sam Rayburn | Victoria/Nersery | NATURAL GAS | 80 | 11520 | 14400 | 6/1/2001 | Planned | 1 | 1
69 | K N Power Co. | Harris Co. Merchant Power Plant | Harris/Humble | NATURAL GAS | 512 | 73728 | 92160 | 2002-12-01 | Planned | 1 | 1
70 | Dynegy, Inc. | Mont Belvieu | Chambers/Mont Belvieu | NATURAL GAS | 250 | 36000 | 45000 | 6/1/2001 | Planned | 1 | 1
71 | LG&E Power, Inc. | Sulphur Springs | Hopkins/Sulphur Springs | NATURAL GAS | 800 | 115200 | 144000 | 2005-01-01 | Planned
72 | Reliant/Air Liquide | Sabine Cogeneration Facility | Orange/Orange | NATURAL GAS | 100 | 14400 | 18000 | 2000-02-01 | Under Constr
|  |  |  | TOTAL | 36164 | 5207616 | 6509520

## On HPL
IPPs on HPL
Map # | Operator | Name | County/City | Fuel | Phase 1 Cap (MW) | Min | Max | Online Date | Status
6 | Lamar Power Partners, L.P. | Lamar Power Project | Lamar/Paris | NATURAL GAS | 1000 | 144000 | 180000 | 2000-06-01 | Under Constr
10 | Texas Independent Energy | Panda Guadalupe Power Plant | Guadalupe/Marion | NATURAL GAS | 1000 | 144000 | 180000 | 2001-12-01 | Under Constr
11 | San Antonio Public Service | Arthur van Rosenberg | Bexar/San Antonio | NATURAL GAS, WASTE HEAT | 539 | 77616 | 97020 | 2000-05-01 | Under Constr
12 | Tenaska, Inc. | Frontier Generation Station | Grimes/Shiro | NATURAL GAS | 830 | 119520 | 149400 | 2000-06-01 | Under Constr
13 | Reliant Energy Power Generation, Inc. | Equistar Channelview | Harris/Channelview | NATURAL GAS | 750 | 108000 | 135000 | 2001-01-01 | Planned
14 | Calpine Corp. | Pasadena Power Plant | Harris/Pasadena | NATURAL GAS, WASTE HEAT | 240 | 34560 | 43200 | 1999-06-01 | Operating
14 | Calpine Corp. | Pasadena Power Plant II | Harris/Pasadena | NATURAL GAS | 545 | 78480 | 98100 | 2000-06-01 | Under Constr
15 | Dynegy, Inc. | Lyondell | Harris/Houston | NATURAL GAS | 155 | 22320 | 27900 | 2000-06-01 | Planned
16 | BASF Corp. | Freeport | Brazoria/Freeport | NATURAL GAS | 92 | 13248 | 16560 | 1999-06-01 | Operating
17 | Sweeny Cogeneration, L.P. | Sweeny Cogeneration Facility | Brazoria/Old Ocean | NATURAL GAS | 390 | 56160 | 70200 | 1999-06-01 | Operating
20 | Diamond Shamrock/Dynegy | Uds Project | Live Oak/Three Rivers | NATURAL GAS | 750 | 108000 | 135000 | 2003-04-01 | Planned
22 | Gregory Power Partners, L.P. | Gregory Power Facility | San Patricio/Gregory | NATURAL GAS | 336 | 48384 | 60480 | 2000-06-01 | Under Constr
28 | SkyGen Services | Corpus Christi Energy Center | Nueces/Corpus Christi | NATURAL GAS | 500 | 72000 | 90000 | 2002-01-01 | Planned
30 | Constellation/Pace | Rio Nogales | Guadalupe/Seguin | NATURAL GAS, WASTE HEAT | 1000 | 144000 | 180000 | 37408 | Planned
31 | Constellation/Pace | Gateway | Upshur/Gilmer | NATURAL GAS | 750 | 108000 | 135000 | 37226 | Planned
32 | Calpine Corp. | Lost Pines I | Bastrop/Bastrop | NATURAL GAS, WASTE HEAT | 800 | 115200 | 144000 | 37043 | Under Constr
33 | Donohue Paper | Sheldon | Harris/Houston | NATURAL GAS | 545 | 78480 | 98100 | Unknown | Planned
34 | Calpine Corp. | Baytown Bayer Power Plant | Harris/Baytown | NATURAL GAS, WASTE HEAT | 200 | 28800 | 36000 | 36892 | Planned
35 | Calpine/Mobil | Beaumont Refinery | Beaumont | NATURAL GAS | 800 | 115200 | 144000 | Unknown | Planned
38 | American National Power, Inc. | San Marcos | Hays/San Marcos | NATURAL GAS | 550 | 79200 | 99000 | 2001-06-01 | Under Constr
39 | American National Power, Inc. | Beaumont | Jefferson/Beaumont | NATURAL GAS | 1100 | 158400 | 198000 | 2003-06-01 | Planned
40 | American National Power, Inc. | Harris Co. Energy Facility | Harris/Houston | NATURAL GAS | 550 | 79200 | 99000 | 2004-06-01 | Under Constr
43 | Tenaska, Inc. | Gateway Generating Station | Rusk/Henderson | NATURAL GAS | 845 | 121680 | 152100 | 2002-06-01 | Under Constr
44 | Conoco Global Power | Orange Sabine River | Orange/Orange | NATURAL GAS | 400 | 57600 | 72000 | 2001-05-01 | Planned
48 | Calpine Corp. | Channel Energy Center | Harris/Houston | NATURAL GAS | 560 | 80640 | 100800 | 2001-03-01 | Planned
49 | Calpine Corp. | Clear Lake Cogeneration LTD | Harris/Pasadena | NATURAL GAS | 35 | 5040 | 6300 | 2001-08-01 | Operating
51 | CSW Energy, Inc. | Eastex Cogeneration Facility | Gregg/Longview | NATURAL GAS | 440 | 63360 | 79200 | 2001-06-01 | Planned
60 | Coastal/FP&L | Bastrop Clean Air Project | Bastrop/Bastrop | NATURAL GAS | 550 | 72000 | 90000 | ='TX Power Plants Master'!L51 | Planned
61 | American National Power, Inc. | Mont Belvieu | Chambers/Mont Belvieu | NATURAL GAS | 1100 | 158400 | 198000 | ='TX Power Plants Master'!L52 | Planned
68 | South Texas Electric Coop | Nusery Sam Rayburn | Victoria/Nersery | NATURAL GAS | 80 | 11520 | 14400 | ='TX Power Plants Master'!L58 | Planned
69 | K N Power Co. | Harris Co. Merchant Power Plant | Harris/Humble | NATURAL GAS | 512 | 73728 | 92160 | 2002-12-01 | Planned
70 | Dynegy, Inc. | Mont Belvieu | Chambers/Mont Belvieu | NATURAL GAS | 250 | 36000 | 45000 | 6/1/2001 | Planned
|  |  |  | TOTAL | 18194 | 2612736 | 3265920

## Off HPL
North Central/Dallas Area Plants
Map # | Operator | Name | County/City | Fuel | Phase 1 Cap (MW) | Min | Max | Online Date | Status
4 | Texas Independent Energy | Archer Power Partners | Wichita/Wichita Falls | NATURAL GAS | 1000 | 144000 | 180000 | 2002-06-01 | Planned
7 | Garland Power & Light System | Ray Olinger | Collin/Nevada | NATURAL GAS | 85 | 12240 | 15300 | 2000-06-01 | Planned
8 | Ennis-Tractebel Power Co., Inc. | Ennis-Tractebel Power Project | Ellis/Ennis | NATURAL GAS, WASTE HEAT | 350 | 50400 | 63000 | 2001-12-01 | Planned
9 | American National Power, Inc. | Midlothian Project | Ellis/Midlothian | NATURAL GAS | 1650 | 237600 | 297000 | 2000-06-01 | Under Constr
50 | Cobisa Corp. | Forney | Kaufman/Forney | NATURAL GAS | 1500 | 216000 | 270000 | 2002-12-01 | Planned
52 | Duke | Mesquite | Dallas/Mesquite | NATURAL GAS | 440 | 63360 | 79200 | 2001-10-01 | Planned
53 | Entergy Gulf States, Inc. | Freestone | Freestone/Fairfield | NATURAL GAS | 800 | 115200 | 144000 | 2002-05-01 | Planned
54 | K N Power Co. | Decatur | Wise/Decator | NATURAL GAS | 510 | 73440 | 91800 | 2002-01-01 | Planned
55 | LG&E Power, Inc. | Anderson | Anderson/Palestine | NATURAL GAS | 1600 | 230400 | 288000 | 2003-04-01 | Planned
59 | Duke | Jack | Jack/Jacksboro | NATURAL GAS | 540 | 77760 | 97200 | 1/1/2002 | Planned
62 | Duke | Temple | Bell/Temple | NATURAL GAS | 520 | 74880 | 93600 | 12/1/2001 | Planned
64 | Southern Company | Weatherford | Parker/Weatherford | NATURAL GAS | 650 | 93600 | 117000 | 4/1/2002 | Planned
65 | Tractebel | Decatur | Wise/Decator | NATURAL GAS | 800 | 115200 | 144000 | 6/1/2002 | Planned
66 | Southern Company | Clifton | Bosque/Clifton | NATURAL GAS | 525 | 75600 | 94500 | 2001-02-01 | Planned
67 | AES | Aurora | Granbury/Hood Co. | NATURAL GAS | 730 | 105120 | 131400 | 6/1/2002 | Planned
71 | LG&E Power, Inc. | Sulphur Springs | Hopkins/Sulphur Springs | NATURAL GAS | 800 | 115200 | 144000 | 2005-01-01 | Planned
|  |  |  | TOTAL | 12500 | 1684800 | 2106000
South Texas Plants
Map # | Operator | Name | County/City | Fuel | Phase 1 Cap (MW) | Min | Max | Online Date | Status
24 | Duke | Hidalgo Energy Facility | Edinburg | NATURAL GAS | 510 | 73440 | 91800 | 2000-05-01 | Under Constr
25 | Calpine Corp. | Magic Valley Power Plant | Hildalgo/Edinburg | NATURAL GAS | 730 | 105120 | 131400 | 2001-02-01 | Under Constr
26 | American National Power, Inc. | Edinburg Plant | Hildalgo/Edinburg | NATURAL GAS | 1000 | 144000 | 180000 | 2001-06-01 | Planned
27 | CSW Energy, Inc. | Frontera Plant | Mission | NATURAL GAS, WASTE HEAT | 330 | 47520 | 59400 | 1999-06-01 | Operating
|  |  |  | TOTAL | 2570 | 370080 | 462600
Other
Map # | Operator | Name | County/City | Fuel | Phase 1 Cap (MW) | Min | Max | Online Date | Status
29 | Texas Independent Energy | Odessa-Ector Power Partners | Ector/Odessa | NATURAL GAS | 1000 | 144000 | 180000 | 2002-04-01 | Under Constr
41 | American National Power, Inc. | El Paso | El Paso/El Paso | NATURAL GAS | 600 | 86400 | 108000 | 2002-06-01 | Planned
|  |  |  | TOTAL | 1600 | 230400 | 288000
|  |  |  | GRAND TOTAL | 16670 | 2285280 | 2856600

## Outline
|  | Competitive Look At Pipeline Characteristics | [16 empty] | Competition
|  | County/City | Turbine | Phase 1 Cap (MW) | HPL Diameter | Distance, Miles | Pipeline # | Pipeline ID | Account # | HPL Pressure Range |  |  | HPL Available Capacity | HPL 1999 Average Use |  | HPL Spec Issues | Wet or Dry | Comments | Competitor | Competitor Diameter | Distance, Miles | Pressure Range |  |  | Available Capacity | 1999 Average Use |  | Spec Issues | Wet or Dry | Comments
Map Number | Power Plant | [8 empty] | Average | High | Low |  | Flow | PSI | [6 empty] | Average | High | Low |  | Flow | PSI
4 | Texas Independent Energy | Wichita/Wichita Falls | 0 | 1000 | N/A | [13 empty] | Lone Star | 10 | 4.03
[19 empty] | CLUPL | 6 | 8.23
6 | Lamar Power Partners, L.P. | Lamar/Paris | GE MS7001FA | 1000 | 30 | 7.73 | 4 | 10005 | 3080 | 764 | 947 | 672 | 550 mmcfd | 0-15mmcfd (winter) 15-60 mmcfd (summer) | 764 | None | Dry |  | Lone Star | 12 | 0.22
|  | *Black Marlin | [7 empty] | Bennington #6594 | [8 empty] | Natural Gas Pipeline of America | 30 | 5.3
[19 empty] | Black Marlin* | 30 | 5.3
7 | Garland Power & Light System | Collin/Nevada | GE 7EA | 85
8 | Ennis-Tractebel Power Co., Inc. | Ellis/Ennis | Siemens 501-G | 350 | N/A | [13 empty] | Lone Star | 30 | 2.04
[19 empty] | Valero | 36 | 3.05
9 | American National Power, Inc. | Ellis/Midlothian | ABB GT24 | 1650 | N/A | [13 empty] | Lone Star | 24 | 0.55
10 | Texas Independent Energy | Guadalupe/Marion |  | 1000 | 30 | 21.85 | 1161 | 11162 | 3017 | 876 | 969 | 719 | 70 mmcfd | 30 mmcfd | 876 |  | Dry | If the gas is sourced from Thompsonville, all IPP's downstream of Nueces Compressor station are compteting for the same 70 mmcfd of capacity south of Prairie Lea or 40 mmcfd north of Prairie Lea. | PG&E | 30 | 0.47 | [5 empty] | 650 |  | Dry
[10 empty] | Austin Cross Over Upstream #8662 |  |  | 770 nmmcfd | 30 mmcfd | 876 |  | Dry | If gas is sourced from Oasis and/or Mid Texas, a total of 770 mmcfd can flow to IPP's south of Prairie Lea or 150 mmcfd to IPP's north of Prairie Lea. | Valero | 20 | 2.78
11 | San Antonio Public Service | Bexar/San Antonio | GE 7EA | 539 | N/A | [7 empty] | 70 mmcfd | 220 mmcfd | 925 |  | Dry | If the gas is sourced from Thompsonville, all IPP's downstream of Nueces Compressor station are compteting for the same 70 mmcfd of capacity south of Prairie Lea or 40 mmcfd north of Prairie Lea. | Valero | 20 | 0.4 | [5 empty] | 650 |  | Dry
[13 empty] | 770 mmcfd | 220 mmcfd | 925 |  | Dry | If gas is sourced from Oasis and/or Mid Texas, a total of 770 mmcfd can flow to IPP's south of Prairie Lea or 150 mmcfd to IPP's north of Prairie Lea. | Coastal | 4 | 4.9
12 | Tenaska, Inc. | Grimes/Shiro | GE MS7001FA | 830
13 | Reliant Energy Power Generation, Inc. | Harris/Channelview |  | 750 | 16 | connected | 1015 | 11016 | 0104 | 550 | 630 | 350 | 65 mmcfd |  | 550 |  | Dry | Source of gas is Bammel | Texas Eastern | 30 | 1.6 | [8 empty] | Not close to the Equistar Channelview plant
| Wrong Location shown on map 13 | [8 empty] | Equistar Channelview #1373 | [8 empty] | Dow | N/A | 0.56 | [8 empty] | Not close to the Equistar Channelview plant
[19 empty] | Amoco | 20 | 0.96 | [8 empty] | Amoco is now Tejas (Coral)
[19 empty] | Valero | 16 | 0.45 | [8 empty] | Now El Paso, should be a direct connect from the A/S line
[19 empty] | Midcon | 12 | 0.8 | [8 empty] | Weak part of Midcon Texas' system
[19 empty] | Seagull | 8 | 4.28 | [8 empty] | Not close to the Equistar Channelview plant
[19 empty] | Exxon | 10 | 5.7 | [8 empty] | Amoco and Exxon are now Tejas (Coral)
[19 empty] | TPCC | 30 | 0.82 | [8 empty] | Not close to the Equistar Channelview plant
[19 empty] | Channel Industires | 20 | [9 empty] | Valero and Channel Industries are now both owned by El Paso
[19 empty] | PG&E | 16 | 3.16 | [5 empty] | 650 |  | Dry | PG&E assets (Valero) bought by El Paso
14 | Calpine Corp. | Harris/Pasadena | Siemens 501-F | 240 | 30 | Connected | 1015 | 11016 | 3053 | 583 | 659 | 496 | See Comment |  | 583 | None | Dry | Available capacity depends on the A/S scheduling. HPL is limited to 300 mmcfd on A/S 30". | Texas Eastern | 30 | 3.21 | [8 empty] | I doubt if they are real competition
14 | Calpine Corp. | Harris/Pasadena |  | 545 | [5 empty] | Clear Lake Cogen #1424 | [8 empty] | Dow | N/A | 1.8 | [8 empty] | This line has been converted to liquies service
[19 empty] | Amoco | 20 | 1.8 | [8 empty] | Amoco and Tejas are the same
[19 empty] | Valero | 16 | 0.67
[19 empty] | Midcon | 12 | 0.1
[19 empty] | Seagull | 8 | 7.67
[19 empty] | Exxon | 10 | 4.37 | [8 empty] | Amoco and Exxon are now Tejas (Coral)
[19 empty] | TPCC | 30 | 2.55
[19 empty] | Channel Industires | 20 | 3.95
[19 empty] | PG&E | 16 | 5.28 | [5 empty] | 650 |  | Dry
15 | Dynegy, Inc. | Harris/Houston | Siemens 501-F | 155 | [14 empty] | Texas Eastern | 30 | 4.57
[19 empty] | Dow | N/A | 3.16
[19 empty] | Amoco | 20 | 0.47 | [8 empty] | Amoco is now Tejas (Coral)
[19 empty] | Valero | 16 | 1.3 | [5 empty] | 650 |  | Dry
[19 empty] | Midcon | 12 | 0.2
[19 empty] | Seagull | 8 | 1.25
[19 empty] | Exxon | 10 | 3.1 | [8 empty] | Amoco and Exxon are now Tejas (Coral)
[19 empty] | TPCC | 30 | 3.81
[19 empty] | Channel Industires | 20 | 4.17
[19 empty] | PG&E | 16 | 6.05
16 | BASF Corp. | Brazoria/Freeport | GE 7EA | 92 | 12 | connected | 1426 | 11427 | 3013 | 368 | 397 | 335 | 30 mmcfd | 30 mmcfd | 368 |  |  | Gas sourced from Texas City Loop. Freeport system is a closed system. | Blue Dolphin | 20 | 0.48 | [8 empty] | Has no acess to any customer other than Dow.
[10 empty] | BASF Freeport #1437 | [8 empty] | Dow | N/A | 0.32
[19 empty] | TPCC | 12 | 1.64
[19 empty] | Midcon | 20 | 0.86
17 | Sweeny Cogeneration, L.P. | Brazoria/Old Ocean | Siemens 501D5A | 390 | 30 | 6.54 | 1372 | 11373 | 3053 | 809 | 918 | 564 | See Comment |  | 809 |  |  | Source A/S. HPL can not supply gas to Philips through the New Gkulf system without using the Caney compressor at 7 cents/mcf. | Valero | 20 | 0.45 | [5 empty] | 700 |  | Dry
New Gulf #3555
[5 empty] | 16 | connected | 1381 | 11382 | 1809 | 570 | 830 | 498 | 0 |  |  |  | Wet | Hilcorp project will eliminate capacity. | Phillips | 10 | 0.49
[5 empty] | 12 | 1.75 | 1389 | 11390 | 1808 | 570 | 830 | 498 | 0 | [5 empty] | Dow | 12 | 0.63
[10 empty] | Philips Sweeny #1517 | [8 empty] | Natural Gas Pipeline of America | 24 | 1.1
[19 empty] | Amoco | 20 | 1 | [8 empty] | Amoco is now Tejas (Coral)
[19 empty] | Lone Star | 24 | 1.4
[19 empty] | Texas Eastern | 30 | 3.85
[19 empty] | Channel Industires | 12 | 1.25
20 | Diamond Shamrock/Dynegy | Live Oak/Three Rivers | 0 | 750 | 30 | 6.05 | 1868 | 11872 | 3017 | 935 | 1051 | 600 | 70 mmcfd | 220 mmcfd | 935 |  | Dry | If the gas is sourced from Thompsonville, all IPP's downstream of Nueces Compressor station are compteting for the same 70 mmcfd of capacity south of Prairie Lea or 40 mmcfd north of Prairie Lea. | Lone Star | 10 | 2.94
[10 empty] | Nueces Discharge |  |  | 770 mmcfd | 220 mmcfd | 935 |  | Dry | If gas is sourced from Oasis and/or Mid Texas, a total of 770 mmcfd can flow to IPP's south of Prairie Lea or 150 mmcfd to IPP's north of Prairie Lea. | Transco | 24 | 4
[10 empty] | 625 | 905 | 500 | 70 mmcfd | 220 mmcfd | 625 |  | Dry | If the gas is sourced from Thompsonville, all IPP's downstream of Nueces Compressor station are compteting for the same 70 mmcfd of capacity south of Prairie Lea or 40 mmcfd north of Prairie Lea. | Midcon | 30 | 4.14
[10 empty] | Nueces Suction |  |  | 770 mmcfd | 220 mmcfd | 625 |  | Dry | If gas is sourced from Oasis and/or Mid Texas, a total of 770 mmcfd can flow to IPP's south of Prairie Lea or 150 mmcfd to IPP's north of Prairie Lea. | Valero | 20 | 4.14 | [5 empty] | 900 |  | Wet
22 | Gregory Power Partners, L.P. | San Patricio/Gregory | 0 | 336
24 | Duke | Hidalgo/Edinburg | 0 | 510 | 24 | 10.33 | 2476 | 12481 | 3025 | 843 | 1029 | 578 | 120 mmcfd | 0 mmcfd | 579 | See Comment | Dry | Gas sourced from King Ranch. Remove all rich gas from system bet2ween Edinburg and King Ranch. Take King Ranch residue down to Edinburg. | Valero | 8 | 4.36 | [5 empty] | 500-600 |  | Dry
[10 empty] | Texaco Mc Allen #6593 | [8 empty] | Texas Eastern | 30 | 5.42
[19 empty] | CMSTG | 10 | 0.8
[19 empty] | TPCC | N/A | 1.4
[19 empty] | Florida Gas | 8 | 6.15
[19 empty] | Tennessee | 16 | 4.2
[19 empty] | Aquila | 12 | 6.8
25 | Calpine Corp. | Hildalgo/Edinburg | Siemens 501G | 730 | 24 | 10.16 | 2476 | 12481 | 3025 | 843 | 1029 | 578 | 120 mmcfd | 0 mmcfd | 579 | See Comment |  | Gas sourced from King Ranch. Remove all rich gas from system bet2ween Edinburg and King Ranch. Take King Ranch residue down to Edinburg. | CMSTG | 20 | 0.05
[10 empty] | Texaco Mc Allen #6593 | [8 empty] | TPCC | N/A | 1.3
[19 empty] | Valero | 14 | 5.6 | [5 empty] | 500-600 |  | Dry
[19 empty] | Tennessee | 16 | 4.65
[19 empty] | Texas Eastern | 30 | 5.8
[19 empty] | Aquila | 12 | 7.2
26 | American National Power, Inc. | Hildalgo/Edinburg | 0 | 1000 | [8 empty] | 120 mmcfd | 0 mmcfd | 579 | See Comment |  | Gas sourced from King Ranch. Remove all rich gas from system bet2ween Edinburg and King Ranch. Take King Ranch residue down to Edinburg.
27 | CSW Energy, Inc. | Hildalgo/Mission | GE 7FA | 330 | [8 empty] | 120 mmcfd | 0 mmcfd | 579 | See Comment |  | Gas sourced from King Ranch. Remove all rich gas from system bet2ween Edinburg and King Ranch. Take King Ranch residue down to Edinburg.
28 | SkyGen Services | Nueces/Corpus Christi | 0 | 500 | [14 empty] | Davis | 6 | 0.2
[19 empty] | John Pursley | 16 | 0.25
[19 empty] | Tejas | 12 | 0.87
[19 empty] | TEJENE | 12 | 1.03
[19 empty] | Texas Eastern | 30 | 4.33
[19 empty] | Koch Gateway | 6 | 4.42
[19 empty] | Florida Gas | 12 | 3.95
[19 empty] | Channel Industries | 6 | 4.8
[19 empty] | Transco | 10 | 7.2
[19 empty] | Valero | 16 | 0.05 | [5 empty] | 500 |  | Dry
[19 empty] | Coastal | 4 | 0.93
[19 empty] | TPCC | 16 | 6.2
29 | Texas Independent Energy | Ector/Odessa | 0 | 1000 | N/A | [13 empty] | Westar | 20 | 2.72
[19 empty] | BROG | 10 | 1.8
[19 empty] | El Paso | 20 | 2.7
[19 empty] | GPM Gas Corp. | 6 | 2.4
[19 empty] | Red River | 24 | 9.75
30 | Constellation/Pace | Guadalupe/Seguin | GE 7FA | 750 | 30 | 10.7 | 1161 | 11162 | 3017 | 876 | 969 | 719 | 70 mmcfd | 30 mmcfd | 876 |  | Dry | If the gas is sourced from Thompsonville, all IPP's downstream of Nueces Compressor station are compteting for the same 70 mmcfd of capacity south of Prairie Lea or 40 mmcfd north of Prairie Lea. | Valero | 6 | 2.2 | [5 empty] | 300 |  | Dry
[10 empty] | Austin Cross Over Upstream #8662 |  |  | 770 mmcfd | 30 mmcfd | 876 |  | Dry | If gas is sourced from Oasis and/or Mid Texas, a total of 770 mmcfd can flow to IPP's south of Prairie Lea or 150 mmcfd to IPP's north of Prairie Lea. | Valero | 30 | 10.5 | [5 empty] | 650 |  | Dry
[19 empty] | Oasis | 36 | 6.2
[19 empty] | TECO | 30 | 6
31 | Constellation/Pace | Upshur/Gilmer | GE 7FA | 800 | 30 | 4.18 | 7 | 10008 | 3080 | 752 | 856 | 676 | 0 mmcfd | 55-90 mmcfd | 752 | High BTU | Wet | Sourced from Bennington and no gathered volumes | Tejas | 8 | 1.52
[10 empty] | Goldston #9603 |  |  | 15 mmcfd |  |  |  |  | 150 mmcfd from Valero and 80 mmcfd from gathering | KOMDST | 12 | 1.32
[13 empty] | 75 mmcfd |  |  |  |  | 150 mmcfd from Valero, 80 mmcfd from gathering, and 60 mmcfd from Bennington | RELANT | 6 | 1.3
[13 empty] | 150 mmcfd |  |  |  |  | Sourced from Bennington and Valero | Western Gas Resources | 4 | 3.5
32 | Calpine Corp. | Bastrop/Bastrop | Siemens 501F-D | 545 | [8 empty] | 40 mmcfd | 30 mmcfd |  |  | Dry | If the gas is sourced from Thompsonville, all IPP's downstream of Nueces Compressor station are compteting for the same 70 mmcfd of capacity south of Prairie Lea or 40 mmcfd north of Prairie Lea.
[13 empty] | 150 mmcfd | 30 mmcfd |  |  | Dry | If gas is sourced from Oasis and/or Mid Texas, a total of 770 mmcfd can flow to IPP's south of Prairie Lea or 150 mmcfd to IPP's north of Prairie Lea.
33 | Donohue Paper | Harris/Houston | 0 | 200 | 12 | 1 | 526 | 10527 | 3016 | 450 | 450 | 450 | See Comment |  | 450 |  |  | MAOP of the 12" (3016) line is limited to 467 psig. Available capacity depends on the necessary delivery pressure. | TPCC | 30 | 0.15
[19 empty] | Midcon | N/A | 0.15
[19 empty] | Valero | 12 | 3.7
[19 empty] | Mobil | 14 | 2.62
[19 empty] | Gulf Coast Natural Gas | 8 | 1.6
34 | Calpine Corp. | Harris/Baytown | Siemens 501F | 800 | 30 | Connected | 810 | 10811 | 3053 |  |  |  | See Comment |  |  |  | Dry | Available capacity depends on the A/S scheduling. HPL is limited to 300 mmcfd on A/S 30". | Exxon | 8 | 0.7
[19 empty] | Midcon | 24 | 0.42
[19 empty] | Channel | 8 | 1.73
[19 empty] | Texas Eastern | 30 | 3.11
[19 empty] | Tejas | 26 | 0.9
35 | Calpine/Mobil | Beaumont | 0 | 550 | 24 | 2.3 | 240 | 10241 | 3032 | 552 | 679 | 478 | 0 mmcfd |  | 552 |  |  |  | Mobil | 16 | 0.17
[10 empty] | Dupont #1428 |  |  | 50 mmcfd |  |  |  |  | If Mobil Florida St. firm term could be reduced from 150 mmcfd to 100 mmcfd and bring additional 50 mmcfd on through A/S. | Midcon | 12 | 0.47
[13 empty] | 100 mmcfd |  |  |  |  | If Mobil Florida St. firm term could be reduced from 150 mmcfd to 100 mmcfd and additional firm term could be reduced by 50 mmcfd and bring 100 mmcfd on through A/S. | Centana Intrastate | 16 | 1.25
[19 empty] | TPCC | 12 | 1.7
[19 empty] | Florida Gas | 24 | 4.17
[19 empty] | KOMDST | 10 | 0.7
38 | American National Power, Inc. | Hays/San Marcos | ABB Alstom | 1100 | 20 | 15.6 | 813 | 10841 | 3103 | 876 | 969 | 719 | 40 mmcfd | 30 mmcfd | 876 |  | Dry | If the gas is sourced from Thompsonville, all IPP's downstream of Nueces Compressor station are compteting for the same 70 mmcfd of capacity south of Prairie Lea or 40 mmcfd north of Prairie Lea. | Valero | 30 | 1.8 | [5 empty] | 600 |  | Dry
[10 empty] | Austin Cross Over Upstream #8662 |  |  | 150 mmcfd | 30 mmcfd |  |  | Dry | If gas is sourced from Oasis and/or Mid Texas, a total of 770 mmcfd can flow to IPP's south of Prairie Lea or 150 mmcfd to IPP's north of Prairie Lea. | Oasis | 36 | 4 | [7 empty] | Dry
[19 empty] | Southern Union Gas | 4 | 16.6
39 | American National Power, Inc. | Jefferson/Beaumont | 0 | 550 | [8 empty] | 0 mmcfd
[13 empty] | 50 mmcfd |  |  |  |  | If Mobil Florida St. firm term could be reduced from 150 mmcfd to 100 mmcfd and bring additional 50 mmcfd on through A/S.
[13 empty] | 100 mmcfd |  |  |  |  | If Mobil Florida St. firm term could be reduced from 150 mmcfd to 100 mmcfd and additional firm term could be reduced by 50 mmcfd and bring 100 mmcfd on through A/S.
40 | American National Power, Inc. | Harris/Houston | ABB GT24 | 2200 | [8 empty] | See Comment |  |  |  |  | Will compete for HPL capaciy with Reliant Enkergy Channelview (IPP #13)
41 | American National Power, Inc. | El Paso/El Paso | ABB GT24 | 600
43 | Tenaska, Inc. | Rusk/Henderson | GE 7FA | 845 | 30 | 7.47 | 19 | 10020 | 3080 | 714 | 750 | 695 | 0 mmcfd | 70-100 mmcfd | 714 | High BTU | Wet | Sourced from Bennington and no gathered volumes | KOMDST | 12 | 1.33
[10 empty] | Valero Henderson Del. #695 |  |  | 15 mmcfd |  |  |  |  | 150 mmcfd from Valero and 80 mmcfd from gathering | Lone Star | 4 | 2.7
[13 empty] | 75 mmcfd |  |  |  |  | 150 mmcfd from Valero, 80 mmcfd from gathering, and 60 mmcfd from Bennington | Natural Gas Pipeline Co. | 36 | 7.44
[13 empty] | 150 mmcfd |  |  |  |  | Sourced from Bennington and Valero | Enjet | 2 | 7.11
44 | Conoco Global Power | Orange/Orange | GE 7FA | 400 | 30 | 12.44 | 148 | 10149 | 3053 | 584 | 691 | 533 | 0 mmcfd |  | 584 |  |  |  | Midcon | N/A | Connected?
[10 empty] | Texoma Beaumont Upstream |  |  | 100 mmcfd |  |  |  |  | Lay new pipe and reduce firm term in Beaumont
[5 empty] | 18 | 10.5 | 185 | 10186 | 4225 | 581 | 691 | 530 |  |  | 581 |  |  |  | Sabine | 18 | 0.88
[10 empty] | Texoma Beaumont Downstream | [8 empty] | Transco | 10 | 1.05
[19 empty] | Centana | 26 | 2.17
[19 empty] | KOMDST | 12 | 2.28
[19 empty] | Florida Gas Trans. | 24 | 5.53
48 | Calpine Corp. | Harris/Houston | 0 | 560 | 24 | 0.9 | 974 | 10975 | 3026 | [9 empty] | Valero | 20 | Connected? | [5 empty] | 650 |  | Dry
[19 empty] | PG&E | 16 | 6.46
[19 empty] | Amoco | 10 | 0.34
[19 empty] | Midcon | 16 | Connected?
[19 empty] | Texas Petrochemicals | 10 | 0.93
[19 empty] | Mobil | 8 | 2.1 | [8 empty] | This line is in liquids service.
49 | Calpine Corp. | Harris/Pasadena | 0 | 35 | [5 empty] | 583 | 659 | 496 | See Comment |  | 583 | None | Dry | Available capacity depends on the A/S scheduling. HPL is limited to 300 mmcfd on A/S 30". | Texas Eastern | 30 | 3.21
[10 empty] | Clear Lake Cogen #1424 | [8 empty] | Dow | N/A | 1.8
[18 empty] | What is the difference between IPP #49 and IPP #14? | Amoco | 20 | 1.8
[19 empty] | Valero | 16 | 0.67 | [5 empty] | 650 |  | Dry
[19 empty] | Midcon | 12 | 0.1
[19 empty] | Seagull | 8 | 7.67
[19 empty] | Exxon | 10 | 4.37
[19 empty] | TPCC | 30 | 2.55
[19 empty] | Channel Industires | 20 | 3.95
[19 empty] | PG&E | 16 | 5.28
50 | Cobisa Corp. | Kaufman/Forney | 0 | 1500 | N/A | [13 empty] | Koch | 18 | 1.43
[19 empty] | Lone Star | N/A | 1.07
[19 empty] | Lone Star | 20 | 3.81
51 | CSW Energy, Inc. | Gregg/Longview | GE 7F | 440 | 30 | 5.6 | 7 | 10008 | 3080 | 730 | 812 | 625 | 0 mmcfd | 70-100 mmcfd | 730 | High BTU | Wet | Sourced from Bennington and no gathered volumes | Western Gas Resources | N/A | 0.23
[10 empty] | Trident #6772 |  |  | 15 mmcfd |  |  |  |  | 150 mmcfd from Valero and 80 mmcfd from gathering | Koch Gateway | 8 | 0.92
[13 empty] | 75 mmcfd |  |  |  |  | 150 mmcfd from Valero, 80 mmcfd from gathering, and 60 mmcfd from Bennington | TPCC | 20 | 0.3
[13 empty] | 150 mmcfd |  |  |  |  | Sourced from Bennington and Valero | KOMDST | 12 | 1.43
[19 empty] | RELANT | 8 | 0.9
[19 empty] | Texas Eastern | 20 | 1.17
[19 empty] | Lone Star | 8 | 0.68
52 | Duke | Dallas/Mesquite | GE 7FA | 440
53 | Entergy Gulf States, Inc. | Freestone/Fairfield | GE 7FA | 800 | [8 empty] | N/A | N/A |  |  |  |  | KOMDST | N/A | 0.42
[19 empty] | Lone Star | N/A | 1.44
[19 empty] | Lone Star | 8 | 2.35
[19 empty] | TPCC | 12 | 3.6
54 | K N Power Co. | Wise/Decator | 0 | 510 | N/A | [13 empty] | Ryder Scott Oil Co. | 4 | 0.42
[19 empty] | Lone Star | 24 | 2.16
[19 empty] | CLUPL | 8 | 1.84
[19 empty] | KOMDST | 6 | 4.72
55 | LG&E Power, Inc. | Anderson/Palestine | 0 | 1600 | 30 | 47-50 | 19 | 10020 | 3080 | 673 | 780 | 476 |  |  | 673 |  |  |  | Lone Star | N/A | 0.8
[5 empty] | 8 | 32-35 | 20 | 10021 | 1556 | 673 | 780 | 476 |  |  | 673 |  |  |  | Koch Gateway | 6 | 3.44
[10 empty] | Tufco Reklaw #1590 | [8 empty] | KOMDST | 6 | 3.1
[19 empty] | Duke Energy | 4 | 7.05
59 | Duke | Jack/Jacksboro | GE 7FA | 540
60 | Coastal/FP&L | Bastrop/Bastrop | 0 | 550 | 16 | 14.7 | 243 | 10244 | 3103 | 686 | 790 | 351 | 40 mmcfd | 30 mmcfd | 686 |  | Dry | If the gas is sourced from Thompsonville, all IPP's downstream of Nueces Compressor station are compteting for the same 70 mmcfd of capacity south of Prairie Lea or 40 mmcfd north of Prairie Lea. | Valero | 20 | 4.4 | [5 empty] | 500-600 |  | Dry
|  | HPL?? |  |  | 18 | 7 |  |  |  | Colorado River #8663 |  |  | 150 mmcfd | 30 mmcfd |  |  | Dry | If gas is sourced from Oasis and/or Mid Texas, a total of 770 mmcfd can flow to IPP's south of Prairie Lea or 150 mmcfd to IPP's north of Prairie Lea. | Valero | 16 | 4.4 | [5 empty] | 500-600 |  | Dry
[19 empty] | Lone Star | 20 | 11.3
61 | American National Power, Inc. | Chambers/Mont Belvieu | 0 | 1100
62 | Duke | Bell/Temple | 0 | 520
64 | Southern Company | Parker/Weatherford | 0 | 650 | N/A | [13 empty] | CLUPL | 10 | 0.68
[19 empty] | Lone Star | 12 | 9.42
65 | Tractebel | Wise/Decator | 0 | 800
66 | Southern Company | Bosque/Clifton | 0 | 525
67 | AES | Granbury/Hood Co. | 0 | 730 | N/A | [13 empty] | Lone Star | N/A | 2.56
[19 empty] | Lone Star | 4 | 1.42
[19 empty] | Valero | 14 | 1.48 | [5 empty] | 700-900 |  | Dry
68 | South Texas Electric Coop | Victoria/Nersery | 0 | 80 | 12 | 3.5 | 1495 | 11496 | 3048 | 635 | 733 | 533 |  |  | 635 |  |  |  | Transco | 24 | 0.46
[10 empty] | Dubose #3355 | [8 empty] | Transco | 6 | 0.28693
[19 empty] | Valero | 8 | 1.7867 | [5 empty] | 800-900 |  | Wet
[19 empty] | Gulf Coast | 14 | 1.1093
[19 empty] | CMSTG | 20 | 7.2443
[19 empty] | Texas Eastern | 16 | 7.0744
69 | K N Power Co. | Harris/Humble | 0 | 512 | [8 empty] | See Comment |  |  |  |  | HPL has no pipelines in this area. Sever congestion will not allow HPL to install any new pipelines. | Midcon | [10 empty] | This is the only pipeline in the area, and it is affilieated with KN.
70 | Dynegy, Inc. | Chambers/Mont Belvieu | 0 | 250 | 12 | 0.34129 | 620 | 10621 | 1204 | [9 empty] | Midcon | 30 | 0.60739
[19 empty] | Midcon | 30 | 1.7366
[19 empty] | Texas Eastern | 30 | 2.3875
[19 empty] | Valero | 4 | 1.8337 | [5 empty] | 600 |  | Dry
[19 empty] | Gulf Coast | N/A | 9.8341
[19 empty] | Exxon | 8 | 2.0318
[19 empty] | Enron?? | 12 | 3.2174
71 | LG&E Power, Inc. | Hopkins/Sulphur Springs | 0 | 800 |  |  |  | Bennington #6594 |  | 764 | 947 | 672 | N/A | 0-60 mmcfd | 764 | None | Dry
72 | Reliant/Air Liquide | Orange/Orange | 0 | 100 | 12 | 8.69 | 395 | 10396 | 4748 | 577 | 687 | 518 | 0 mmcfd |  | 577 |  |  |  | Sabine | 18 | 0.47
[10 empty] | Sabine #1507, Requires Crossing River |  |  | 100 mmcfd |  |  |  |  | Lay new pipe and reduce firm term in Beaumont | KOMDST | 12 | 0.92
[5 empty] | 30 | 12.22 | 246 | 10247 | 3080 | 584 | 691 | 533 | ????? |  | 584 |  |  |  | CIPC | 6 | 1.4
[10 empty] | Texoma Beaumont Upstream | [8 empty] | Midcon | N/A | 1.18
[19 empty] | TPCC | 26 | 1.34
[19 empty] | Florida Gas | 24 | 7.8
[19 empty] | Texas Eastern | 30 | 9.9
| Calpine | Clear Lake |  |  | 12 | Connected? | 1011 | 11012 | 4079 | [9 empty] | Valero | 6 | Connected? | [5 empty] | 650 |  | Dry
[19 empty] | Midcon | 12 | 0.4
[19 empty] | Amoco | 8 | 0.67
[19 empty] | Dow | N/A | 2.16
[19 empty] | Tejas | 30 | 2.5
[19 empty] | Tejas | 14 | 2.5
[19 empty] | Texas Eastern | 30 | 3.33
| Calpine | Lyondell |  |  | 16 | Connected | 896 | 10897 | 4352 | [9 empty] | Tejas | 10 | Connected?
[19 empty] | Midcon | 14 | Connected?
[19 empty] | Valero | 12 | Connected? | [5 empty] | 650 |  | Dry
[19 empty] | Amoco | 10 | 0.4
| Calpine | Texas City |  |  | 18 | Connected | 1172 | 11173 | 3375 | [9 empty] | Amoco | 16 | Connected?
[19 empty] | Valero | 16 | Connected? | [5 empty] | 700 |  | Dry
| LG & E | Ingleside |  |  | 6 | Connected? | 2120 | 12125 | 1113 | [9 empty] | Tennessee | 12 | 0.3
[19 empty] | CCNG | 12 | 0.42
[19 empty] | Valero | 10 | 0.47 | [5 empty] | 800 |  | Wet
| SkyGen | Corpus Christi |  |  | 12 | 0.65303 | 2305 | 12310 | 3075 | [9 empty] | Valero | 16 | 1.4763 | [5 empty] | 500 |  | Dry
[19 empty] | Davis | 4 | 4.1807
[19 empty] | Florida Gas | 8 | 4.8807
[19 empty] | Texas Eastern | 12 | 4.5653
[19 empty] | Corpus Christi Trans. | 16 | 5.1415
Robert Morgan added | LG&E Power, Inc. | Anderson |  |  | 30 |  |  |  | 3080 | 714 | 750 | 695 | 0 mmcfd | 70-100 mmcfd | 714 | High BTU | Wet | Sourced from Bennington and no gathered volumes
[13 empty] | 15 mmcfd |  |  |  |  | 150 mmcfd from Valero and 80 mmcfd from gathering
[13 empty] | 75 mmcfd |  |  |  |  | 150 mmcfd from Valero, 80 mmcfd from gathering, and 60 mmcfd from Bennington
[13 empty] | 150 mmcfd |  |  |  |  | Sourced from Bennington and Valero
Note on A99: Need to check the accuracy of the map