## Permit Matrix
Edgecombe Energy Facility (Revised August 23, 2000)
Permit/Approval | Date of Application |  | Date of Approval |  | Restrictions/Conditions
| Actual | Expected | Actual | Expected
US Federal Aviation Administration
Notice of Proposed Construction |  | 2000-10-01 |  | 2000-11-01 | Submit 30 days prior to construction
Federal Energy Regulatory Commission
Certification of Exempt Wholesale Generator Status |  | 2001-02-01 |  | 2001-04-01
Power Marketer Certification |  | 2001-02-01 |  | 2001-04-15
US Department of Energy
Exemption to burn natural gas and No. 2 fuel oil |  |  |  |  | Only applies to base load plants.
US Army Corps of Engineers
Wetlands (Letter of Concurrence) | 2000-08-15 |  |  | 2000-09-15 | No restriction anticipated.
US Fish and Wildlife Service
Threatened and endangered species (Letter of Concurrence) | 2000-08-15 |  |  | 2000-09-15 | No restriction anticipated.
North Carolina Public Utilities Commission
Certificate of Public Convenience and Necessity |  | 2000-08-25 |  | 2000-10-15 | Submit staff data request by August 25
North Carolina Department of Environment, Health and Natural Resources
Authority to Construct Permit (Air Permit) |  | 2000-09-01 |  | 2000-12-01 | No restrictions to construction are anticipated. Continuous emissions monitoring against the 250 ton per year limit. Facility operations will be managed such that this limit is not exceeded (approx. 2000 hours)
Title IV Operating Permit (Air Permit) |  | 2000-10-01 |  | 2001-02-01 | Recordkeeping, reporting, and purchase sulfur allowances.
Title V Operating Permit (Air Permit) |  | 2002-05-01 |  | 2003-05-01 | Apply within 12 months of starting operations, recordkeeping, reporting.
NPDES Stormwater Construction Permit |  | 2000-10-01 |  | 2000-10-08 | Notification and implementation of stormwater pollution prevention plan prior to construction.
Sedimentation Control Plan Approval |  | 2000-10-01 |  | 2000-11-01 | Requires expediting.
SPCC Plan |  | 2000-12-01 |  |  | Completed and implemented by 11/01/00, recordkeeping, reporting, training. Filing not necessary.
Department of Transportation
Driveway Permit |  | 2000-09-01 |  | 2000-09-15 | Necessary to complete curb cut during construction site preparation.
Department of Cultural Resources
Archaeological survey approval (Letter of Concurrence) | 2000-08-15 |  |  | 2000-09-15 | No restriction anticipated.
North Carolina Secretary of State
Certificate of Authority (Business License) |  | 2001-03-01 |  | 2001-03-15
County of Edgecombe, City of Rocky Mount
Annexation |  |  |  |  | Following purchase of property, deed property to City of Rocky Mount. City of Rocky Mount can complete annexation process within 30 days.
Conditional Use Permit |  |  |  |  | Function of annexation.
Water service |  | 2000-06-21 |  | 2000-11-01
Local Construction Permit |  | 2000-10-15 |  | 2000-11-01
Certificate of Occupancy |  | 2001-05-01 |  | 2001-06-01
Fire Safety Approval |  | 2000-10-15 |  | 2000-11-01