## Sheet1
NORTHERN CALIFORNIA POWER PLANTS
| Plant | Region | Status | Probability | Graph | Capacity | Applicant | Online Date | Permit Date | Location | State | County
| SMUD McClellan Upgrade (COMPLETE) | NP15 | 1 | High | 1 | 22 | SMUD | 2001-05-01 |  |  | CA | Sacramento
| Procter & Gamble (Phase 2) (COMPLETED) | NP15 | 1 | High | 1 | 44 | SMUD | 2001-05-10 |  | Sacramento | CA | Sacramento
| CEC June Renewables Estimate (COMPLETED) | NP15 | 1 | High | 1 | 42.8 |  | 2001-06-01 |  |  | CA
| Chowchilla Peaker (COMPLETED) | NP15 | 1 | High | 1 | 48.6 | NRG Energy, Inc. | 2001-06-14 |  | Chowchilla | CA | Madera
| CEC July Renewables Estimate (COMPLETED) | NP15 | 1 | High | 1 | 12 |  | 2001-07-01 |  |  | CA
| Madera Biomass (COMPLETED) | NP15 | 1 | High | 1 | 25 | El Paso Corp. | 2001-07-01 |  |  | CA | Madera
| Sutter (COMPLETED) | NP15 | 1 | High | 1 | 500 | Calpine Corp. | 2001-07-02 | 1999-04-14 | Yuba City | CA | Sutter
| Los Medanos (Pittsburg) Facility (COMPLETED) | NP15 | 1 | High | 1 | 555 | Calpine Corp. | 2001-07-09 | 1999-08-17 | Pittsburg | CA | Contra Costa
| CEC August Renewables Estimate (COMPLETED) | NP15 | 1 | High | 1 | 16.5 |  | 2001-08-01 |  |  | CA
| Red Bluff Peaker | NP15 | 1 | High | 1 | 48.6 | NRG Energy, Inc. | 2001-09-30 |  | Red Bluff | CA | Tehama
| Gilroy (Phase 1) | NP15 | 1 | High | 1 | 135 | Calpine Corp. | 2001-09-01 | 2001-05-21 | Gilroy | CA | Santa Clara
| King City Peaker | NP15 | 1 | High | 1 | 50 | Calpine Corp. | 2001-09-01 | 2001-05-02 | King City | CA | Monterey
| Delta Energy Center | NP15 | 1 | High | 1 | 880 | Calpine Corp. / Bechtel Generating Co. | 2002-07-01 | 2000-02-09 | Pittsburg | CA | Contra Costa
| Moss Landing | NP15 | 1 | High | 1 | 1060 | Duke Energy Corp. | 2002-07-01 | 36824 | Moss Landing | CA | Monterey
| Evergreen Concord | NP15 | 2 | Medium-High | N | 50 | Evergreen Power | 2001-10-01 |  | Martinez | CA | Contra Costa
| Contra Costa | NP15 | 1 | High | N | 530 | Mirant Corp. | 2003-05-01 | 36982 | Antioch | CA | Contra Costa
| United Golden Gate (Phase 1) | NP15 | 1 | High | N | 51 | El Paso Corp. | 2001-10-01 | 2001-03-07 | San Francisco | CA | San Mateo
| Four Mile Hill Project | NP15 | 2 | Medium-High | 2 | 49.9 | Calpine Corp. | 2003-12-01 |  | Modoc National Forest | CA | Siskiyou
| Three Mountain Power | NP15 | 2 | Medium-High | 2 | 500 | Ogden Pacific | 2003-12-01 | 2001-05-16 | Burney | CA | Shasta
| Benicia Refinery Cogen | NP15 | 2 | Medium-High | 2 | 51 | Valero Energy Corp. | 2002-06-01 |  | Benicia | CA | Solano