## Sheet1
Matrix Power Process - Outstanding Issues
| Issue | Who will be involved in resolving? | Timeframe | Comments/ Status
1 | Where should Product Dev get load profiles to develop Matrix products? Site Profile? If so, need reasonable turnaround time. | JD Burrows, Erling Brakke | By 8/09/01 | JD and Erling are currently working on sharing information.
2 | How does the Prospect List work with OMS? | Scott Wohlander, Jennifer Rudolph, Nicole Schwartz | 2001-08-01 | Done - Prospect database will be queried given certain channel criteria. Resulting opportunities will be loaded into OMS for Origination to pursue.
3 | How does the Prospect List work with Credit? Is credit pre-screened? | Scott Wohlander, Jennifer Rudolph, Nicole Schwartz, Molly Harris | 2001-08-01 | Done - Criteria has been established. Most opportunities with exposure < $500,000 will be pre-screened and pre-approved for credit. Those with exposure > $500,000 will be pre-screened with approval pending financial statement analysis and deal structure.
4 | We need to automate credit reserve updates to Matrix prices. | JD Burrows, Molly Harris, IT | ? | NY ConEd will be updated by 8/6/01. Further automation will be developed.
5 | We need to automate overall Matrix price updates. | JD Burrows, Scott Yeargain, IT | ? | In progress - The NY market is currently automated. Awaiting cost and time proposal from IT for extending the automation to other markets.
6 | Can we go to real-time pricing? | JD Burrows, Scott Yeargain, IT | ?
7 | Integrate OMS into overall process. | Michelle Juden | By 8/15/2001 | In-progress
8 | Define rules of use for Legal contracts. | Jennifer Hillegonds, Mike Smith | 2001-08-01 | Mini Contract - agent sales only; New Master Contract - all other power transactions
9 | Streamline process for getting contracts from Legal. | Jennifer Hillegonds, Mike Smith, Michelle Juden | By 8/15/01 | Memo on process went out on 8/7/01. Still need to work on streamlining or automating
10 | Too many uses of the term "Deal Ticket" - needs definition. | Karen Cutler, JD Burrows, Mark Kiddle | By 8/15/01
11 | Legal name wrong on contract? Can GCP, D&B help? Needs to be fixed in X number of days. | Molly Harris, Mark Kiddle, Eric Letke | By 8/15/01 | The D&B Prospect Database should help this somewhat. Eventually this will be tied to GCP for name verification. In the meantime, need a process for an exception to work - how will the name be fixed and how will it flow back to Prospect Database.
12 | Integrate Global Counterparty into process. | Molly Harris, Mark Kiddle, Michelle Juden | 2001-08-06 | Credit sends request to GCP. Future state is that RPS and RGS will be integrated with GCP. Need to get status from IT.
13 | Streamline process for credit to get notified of matrix deals closed. | JD Burrows, Nicole Schwartz, Michelle Juden, Molly Harris | By 8/15/01 | Need 1 report sent to credit daily. Suggestions made, need to be implemented.
14 | Define parameters around requesting collateral from matrix customers. | Molly Harris, Scott Gahn | 2001-08-01 | According to Molly Harris, already defined: for deals approved after-the-fact, no collateral - only Yes or No.
15 | Identify roles and processes for unwinding deals. | Mark Kiddle, Molly Harris, Michelle Juden | By 8/10/2001 | Deal Capture will be responsible - awaiting flow chart from Molly Harris.
16 | Who should be booking matrix deals? | JD Burrows, Deal Mgmt | By 8/15/01 | Transaction Economics and initiating booking will reside in Deal Structuring. JD and Deb Merril are working our transition of responsibilities
17 | Should we use a Deal Ticket that Originators fill out (like gas process)? | Michelle Juden, JD Burrows, Mark Kiddle, Scott Gahn/Eric Letke | By 8/15/01
18 | Define timelines for routing of contract - how long does it take? | Mark Kiddle, Jennifer Hillegonds | 2001-08-01 | 1 day to 1 week depending on who can sign it. Deal Capture takes contract to Legal, legal initials and forward to mgmt to sign, mgmt return to Deal Capture once signed.
19 | Need process for dealing with bankruptcies and past-due amounts (during fulfillment). | Molly Harris, Jay Bhatty, Scott Mills | ? | Process development is in progress - Molly Harris is the point person from the Power Task Force.
20 | Integrate Credit worksheet into process | Molly Harris, Michelle Juden, Eric Letke | By 8/15/2001 | Worksheet has been developed.