## Sheet1
NNG WEEKLY OUTAGE REPORT
NORTHERN NATURAL GAS
| Location | Date | Scope | Comments
NNG | Garner | 12/04/01 to 04/30/02 | Refrigerant compressor is being shipped to York International for repairs. | Est. Flow affect - Not able to to liquifey and gas during this outage. The tank is about 80% full going into January.
NNG | Waterloo Unit 6 | 02/11/02 to 02/27/02 | Packing and compressor rings. | Flow affect = 0 mmcfd.
NNG | Bushton 31 | 02/27/02 to 02/29/02 | Replace a section of the exhaust header. (We will try and wait until north flows drop off). | Flow affect = 0 mmcfd.
NNG | Burdett | 02/27/02 to 02/27/02 | Replace valve. 4 to 5 hrs | Flow affect = 0 mmcfd.
NNG | Finney 4 Unit 3 | 03/11/02 to 04/05/02 | Overhaul | Flow affect = 3 mmcfd.
NNG | Canadian 1&3 | 03/12/02 to 03/12/02 | Relief valve testing. 8 hrs. | Flow affect = 3 mmcfd.
NNG | Northrup 1&2 | 03/19/02 to 03/19/02 | Relief valve testing. 8 hrs. | Flow affect = 15 mmcfd.
NNG | Perryton Barlow 1-3 | 03/18/02 to 03/18/02 | Relief valve testing. 8 hrs. | Flow affect = 7 mmcfd.
NNG | Plains Turbine | 03/19/02 to 03/20/02 | Annual ESD 32 hrs. (We will see if EL Paso can work with us during this outage). | Flow affect = 100 mmcfd.