## Sheet1
NNG WEEKLY OUTAGE REPORT
NORTHERN NATURAL GAS
| Location | Date | Scope | Comments
NNG | Chatfield | 03/06/02 to 03/22/02 | Re-enforce the rear outboard bearing support. Part needs to be machined. | Flow affect = 0 mmcfd if temps stay mild..
NNG | Garner | 12/04/01 to 04/30/02 | Refrigerant compressor is being shipped to York International for repairs. | Est. Flow affect - Not able to liquefy and gas during this outage. The tank is about 80% full going into January.
NNG | Waterloo Piping Transitions | 03/18/02 to 04/26/02 | Piping in the yard will be hand dug inspected and recoated with some sort of protection. (This will be done on each unit. One at a time). Check DesMoines Region outage report for the schedule. | Flow affect = 0 mmcfd
NNG | Cunningham Unit 5 | 02/25/02 to 03/25/02 | Overhaul and repair cracked manifold. (The actual overhaul started 03/04). | Flow affect = 50 mmcfd from our max wdl. effort.
NNG | Sublette Unit 24 | 03/25/02 to 03/25/02 | Perform coupling alignment and base deflection. (10 hour outage). | Flow affect = 3 mmcfd
NNG | Finney 4 Unit 3 | 04/02/02 to 04/11/02 | Need to pull #1 compressor piston. (Unit #3 will be down due to #1 being down). | Flow affect = 4.5 mmcfd
NNG | Finney 4 Unit 4 | 04/15/02 to 05/10/02 | Overhaul (possible unit exchange). | Flow affect = 3 mmcfd
NNG | Beaver 7 Unit 1 | 03/10/02 to 03/22/02 | Knock in the compressor. | Flow affect = 2 mmcfd
NNG | Kermit | 03/26/02 to 03/26/02 | Test relief valves on #1 and #2 turbines at the station.(Seminole would be available to run if needed). | Flow affect = 0 mmcfd.
NNG | Sprayberry Unit 4 | 03/12/02 to 03/28/02 | Complete inspection on #4 unit. Inspect bearings. Web deflections, and torque anchor bolts. (There will be a flow affect, if noms get above 80 mmcfd). | Flow affect = 0 mmcfd at the present time.
NNG | Jal 1&2 | 03/19/02 to 03/21/02 | Repair operator for fuel gas ESD. | Flow affect = 0 mmcfd. No gas noms at the present time.