## Page 1
ENRON TRANSPORTATION SERVICES | [9 empty] | ORIGINAL |  | REVISION NO. |  | CANCEL |  |  | PAGE 1 of 2
PROJECT AUTHORIZATION | [9 empty] | X
| Project Definition |  |  |  |  | Title (20) | Agave WT I/C |  |  |  | WBS | .01 |  |  |  | Install
76
Related Project Number |  |  | Related Project Number(2) |  |  |  | PCF Number | PDB Number |  |  | Estimated Start Date |  |  | Estimated Finish Date
[11 empty] | 2001-10-01 |  |  | 2001-12-15
Company Code and Name |  |  |  | Profit Center |  |  | Region | Team |  | Responsible Cost Center |  | Requesting Cost Center |  |  | Project Type
0060 Transwestern Pipeline Co. |  |  |  | 10802 |  |  | ALB | ARTESIA |  | 111519 |  | 111138
Location (Legal Description) |  |  |  | County/Parish |  |  | Zip Code | State | Line No./Station No. |  |  |  | Plant Number |  |  | Farmtaps?
S2 T17S R29E |  |  |  | EDDY |  |  | 88264 | NM | NMBW219
AFUDC | OH |  |  | City Name
Y or N | Yor N |  |  | MALJAMAR |  |  | Project in city | NM
Please check one: |  |  |  | New facility | X |  | Existing facility | [5 empty] | Removing facility from service
Detailed Description of Work:
SCOPE: INSTALL A 12" HOT TAP AND SIDE VALVE ON TRANSWESTERN'S 24" LOOP LINE LOCATED IN EDDY COUNTY NEW MEXICO
Install riser from side valve and leave one (1) 12" 600# ser. RF Flange for Agave to install insulation kit and tie in point.
Tie in is for interconnect with Agave and volume to be from 35 mmcfd to 100 mmcfd.
Tie in point will be on the discharge pressure side of Station WT-1 (High Pressure Side) with a MAOP of 1008#
Agave to install all measurement facilities and gas quality instrumentation and retain ownership and Transwestern is to operate interconnect.
Interconnect to be built to Enron standards.
This work order includes inspection cost for the measurement facility being built by Agave to meet Enron Standards.
Tap and side valve = $75,000
Inspection Extra = $10,000
Benefit/Reason for Change:
Marketing: volumes into the TW system
PROJECT REVIEW/CONTACT INFORMATION | [8 empty] | REGULATORY APPROVAL SECTION
Responsible Person |  |  | Environmental |  |  |  | Reg Affairs |  | Approval Required |  |  | Yes |  |  | No
Earl Chanley |  |  | Larry Campbell | [5 empty] | Approval Received |  |  | Yes |  |  | No
Marketing Rep/Sponsor |  |  | ROW Agent |  |  |  | Facility Planner |  | Authorization: | [6 empty] | Date:
Kim Watson |  |  | Cecil Gutierrez |  |  |  | Mansor Abdmoulaie |  | REGULATORY STAMP
Team Contact |  |  | Prepared By |  |  |  | Construction Coordinator
Terry Youngren |  |  | Earl Chanley |  |  |  | Mike McCracken
ESTIMATED WORK ORDER COST
Project Reimbusable? |  |  | Total Estimated Cost |  |  |  | 85000
No |  |  | Less Credit |  |  |  | (0)
|  |  | Net Cost |  |  |  | 85000
Reimbusable Amount |  |  | Less: Previous W/O Cost |  |  |  | 0 |  | APPROVALS
$___________________ |  | -or- | Increase(Decrease) | [5 empty] | Signature:
| __________% | [5 empty] | 85000 |  | Earl Chanley | [6 empty] | Date:092501
Signature:
ADMIN BUDGET CONTROL | [15 empty] | Date:
Project in Plan? | [5 empty] | Capital Budget Code |  |  | Signature:
If not in Plan, Where are the funds coming from? | [15 empty] | Date:
________________________________________ | [8 empty] | Signature:
Project in Current Estimate? | [5 empty] | MW _ TWP | [9 empty] | Date:
Project Discretionary? | [5 empty] | Budget Category |  |  | Signature:
Budget Balance Available | [5 empty] | Exective Pool | [9 empty] | Date:
Less: Net Project Cost or | [5 empty] | Budget Responsibility |  |  | Signature:
Revision Increase (Decreased) | [5 empty] | Mktg - E&C | [9 empty] | Date:
Budget Balance Remaining | [8 empty] | IM Releaser:
Functional Coordinator Signature: | [5 empty] | Date: | [9 empty] | Date:
Financial Control Signature: | [8 empty] | Property Accounting:
[6 empty] | Date: | [9 empty] | Date:
Project Authorization.xlt Revision: 1/10/2001
DO NOT DELETE THE FOLLOWING INFORMATION. IT IS NEEDED FOR THE FORM TO OPERATE.
1
Project Types: Drop Down Box
Install
Removal
Study
|  | 1 | 01 Intangible Plant
|  | 2 | 02 Storage
|  | 3 | 03 Extraction Plant
|  | 4 | 04 Gathering Plant
|  | 5 | 05 Transmission-Compression
|  | 6 | 06 Transmission-Lateral Comp/TW La
|  | 7 | 07 Transmission-Plant
|  | 8 | 08 Transmission-Right of Way
|  | 9 | 09 Transmission-Sales
|  | 10 | 10 Transmission-Offshore Gathering
|  | 11 | 11 Transmission-Offshore Trans Plant
|  | 12 | 12 Blanket Operations

## Page 2
PROJECT AUTHORIZATION |  |  |  | X | ORIGINAL | [5 empty] | PAGE 2 of 2
Project Definition |  | Project Title |  |  | REVISION NO.
0 |  | Agave WT I/C |  |  | CANCEL
Project WBS |  |  |  | 2 | AFUDC
.01 |  | Install |  | 2.75 | Overhead Rate
WBS | Cost | PS | Materials |  | Qty | Unit | AFUDC | OH | Item | Current | Previous
Element | Element | Asset | [6 empty] | Cost | Cost | Cost
.06 | 53500500 |  | Meter Station: |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 08 | 08 Flare System |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 12 | 12 Buildings |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 13 | 13 Cathodic Protection Equipment |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 14 | 14 Communication Equipment |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 16 | 16 Computer Equipment |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 18 | 18 Control Equipment |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 20 | 20 Dehydrator |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 21 | 21 Detection Equipment |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 31 | 31 Gas Loss |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 33 | 33 Pipe Coating |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 38 | 38 Land & Land Rights |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 39 | 39 Metering Equipment |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 40 | 40 Odorizers |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 45 | 45 Regulators |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 47 | 47 Separators, Scrubbers, Gas Cleaners |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 49 | 49 Station Service Lines |  | 1 | lt | 10.5556 | 68.75 | 2500 | 2580 | 0
.06 |  | 50 | 50 Tanks |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  | 51 | 51 Valves - 2" inches and over |  | 1 | lt | 42.2222 | 275 | 10000 | 10318 | 0
.06 |  | 54 | 54 Gas Pipe |  | 1 | lt | 21.1111 | 137.5 | 5000 | 5159 | 0
.06 |  | 99 | 99 Allocated materials |  | 1 | lt | 3.5171 | 22.9075 | 833 | 860 | 0
.06 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
.06 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
[9 empty] | TOTAL MATERIALS | 18917 | 0
[9 empty] | FREIGHT | 1800 | 0
[9 empty] | SALES TAX | 1350 | 0
[9 empty] | GRAND TOTAL MATERIALS + AFUDC + OH | 22067 | 0
ENVIRONMENTAL |  |  |  | Overhead |  | Interest |  |  | Planned Total | SAP Total
.01 | .01 |  | ENVR-GENERAL EXPENSE | 13.75 |  | 2.1111 |  |  | 500 | 516 | 0
.01 | .02 |  | ENVR-PERMITS/AUTH. | 0 |  | 0 |  |  | 0 | 0 | 0
.01 | .03 |  | ENVR.CONST.MONITOR | 0 |  | 0 |  |  | 0 | 0 | 0
[8 empty] | TOTAL | 500 | 516 | 0
CONSTRUCTION SUPPORT
.02 | .01 |  | COMPANY LABOR | 33 |  | 5.0667 |  |  | 1200 | 1239 | 0
.02 | .02 |  | CONTRACT LABOR | 0 |  | 0 |  |  | 0 | 0 | 0
.02 | .03 |  | XRAY (NDT) | 27.5 |  | 4.2222 |  |  | 1000 | 1032 | 0
.02 | .05 |  | 3RD PARTY INSPECT-ADD | 266.53 |  | 40.9218 |  |  | 9692 | 10000 | 0
.02 | .05 |  | 3RD PARTY INSPECT | 96.25 |  | 14.7778 |  |  | 3500 | 3612 | 0
.02 | .06 |  | TEST | 0 |  | 0 |  |  | 0 | 0 | 0
[8 empty] | TOTAL | 15392 | 15883 | 0
DISTRICT LABOR AND EQUIPMENT
.03 |  |  | COMPANY LABOR | 132 |  | 20.2667 |  |  | 4800 | 4953 | 0
ENGINEERING
.04 | .01 |  | COMPANY LABOR | 132 |  | 20.2667 |  |  | 4800 | 4953 | 0
.04 | .02 |  | CONTRACT LABOR | 0 |  | 0 |  |  | 0 | 0 | 0
.04 | .03 |  | AS-BUILTS | 68.75 |  | 10.5556 |  |  | 2500 | 2580 | 0
[8 empty] | TOTAL | 7300 | 7533 | 0
CONTRACT INSTALLATION
.05 |  |  | CONTRACT LABOR | 687.5 |  | 105.5556 |  |  | 25000 | 25794 | 0
ROW AND OTHER
.06 | .38 | 53102200 | Real Property Purchase | 0 |  | 0 |  |  | 0 | 0 | 0
.06 | .38 | 53102000 | Right-of-Way | 13.75 |  | 2.1111 |  |  | 500 | 516 | 0
.07 |  | 53102100 | Damages, Services, & Other | 0 |  | 0 |  |  | 0 | 0 | 0
[8 empty] | TOTAL | 500 | 516 | 0
CONTINGENCY
.08 |  |  | CONTINGENCY | 206.25 |  | 31.6667 |  | TOTAL | 7500 | 7738 | 0
OTHER
.09 | .01 |  | OTHER GENERAL | 0 |  | 0 |  |  | 0 | 0 | 0
.09 | .02 |  | GAS LOSS | 0 |  | 0 |  |  | 0 | 0 | 0
.09 | .03 |  | QUALITY INSPECTION | 0 |  | 0 |  |  | 0 | 0 | 0
[8 empty] | TOTAL | 0 | 0 | 0
|  | Total Estimated Cost | [6 empty] | 83059 | 85000 | 0
Less Credits (Reimbursements/Contr.-in-aid) -- Needs to be planned on WBS C.XXXXXX.04 | [8 empty] | 0 | 0 | 0
|  | Net Cost | [6 empty] | 83059 | 85000 | 0

## Assets
SAP FIXED ASSETS SYSTEM
Project Systems Asset Determination Table.
PS Asset # | DESCRIPTION | PS Asset # | DESCRIPTION
01 | ABSORBERS / ADSORBERS | 28 | ISOM UNITS
02 | STATIONARY AIR BLOWERS | 29 | CATALYST
03 | AIR CLEANERS | 30 | GAS LINE PACK
04 | AIR COMPRESSORS | 31 | GAS LOSS
05 | AUXILLARY POWER SUPPLY EQUIPMENT | 32 | GAS UNDERGROUND-NON-RECOVERABLE
06 | BUTANE ISOMERIZATION | 33 | PIPE COATING
07 | OLEFLEX | 34 | STORAGE GAS WELLS
08 | FLARE SYSTEM | 35 | HEAT EXCHANGE EQUIPMENT
09 | LOADING FACILITIES | 36 | HOISTING SYSTEM - YARD
10 | BOILERS | 37 | LAND IMPROVEMENTS
11 | BRIDGES - AERIAL XING STRUCTURE | 38 | LAND AND LAND RIGHTS
12 | BUILDINGS | 39 | METERING EQUIPMENT
13 | CATHODIC PROTECTION EQUIPMENT | 40 | ODERIZERS
14 | COMMUNICATIONS EQUIPMENT | 41 | OIL CHARGING SYSTEM
15 | COMPRESSORS AND DRIVERS | 42 | PIPELINE LAUNCHERS & RECEIVERS
16 | COMPUTER | 43 | PLATFORMS - OFFSHORE
17 | CONDENSERS | 44 | PUMPS
18 | CONTROL EQUIPMENT | 45 | REGULATORS
19 | COOLING SYSTEMS - PACKAGED UNITS | 46 | REVETMENTS
20 | DEHYDRATOR | 47 | SEPERATORS, SCRUBBERS, GAS CLEANERS
21 | DETECTION EQUIPMENT | 48
22 | DISPOSAL TREATMENT - EQUIP / FACILITY | 49 | GENERAL PLANT ADDITIONS
23 | DRAINAGE AND SEWERAGE SYSTEMS | 50 | TANKS, RESERVIORS, & VESSLES
24 | ELECTRICAL | 51 | VALVES - 2 INCH AND OVER
25 | FRACTIONATION TOWER | 52 | VAPORIZERS
26 | GAS PROCESSING UNIT | 53 | WATER SUPPLY TREATMENT SYSTEMS
27 | GAS TREATING UNITS / SYSTEMS | 54 | GAS PIPE
|  | 99 | ALLOCABLE MATERIALS (BOLTS, GASKETS, ECT)

## Assets per Project Type
Recommended PS Asset WBS Structure
| Pipeline: | Meter Station: | Valves Tap | Storage Tank Battery: | Scrubber/ Separator Station: | Regulator Stations:
1 | 08 Flare System | 08 Flare System | 31 Gas Loss | 08 Flare System | 13 Cathodic Protection Equipment | 12 Buildings
2 | 11 Bridges - Aerial Crossing Structure | 12 Buildings | 33 Pipe Coating | 13 Cathodic Protection Equipment | 18 Control Equipment | 13 Cathodic Protection Equipment
3 | 13 Cathodic Protection Equipment | 13 Cathodic Protection Equipment | 38 Land & Land Rights | 14 Communication Equipment | 21 Detection Equipment | 14 Communication Equipment
4 | 18 Control Equipment | 14 Communication Equipment | 51 Valves - 2" inches and over | 18 Control Equipment | 31 Gas Loss | 16 Computer Equipment
5 | 20 Dehydrator | 16 Computer Equipment | 54 Gas Pipe | 21 Detection Equipment | 33 Pipe Coating | 18 Control Equipment
6 | 21 Detection Equipment | 18 Control Equipment |  | 33 Pipe Coating | 38 Land & Land Rights | 21 Detection Equipment
7 | 31 Gas Loss | 20 Dehydrator |  | 38 Land & Land Rights | 39 Metering Equipment | 31 Gas Loss
8 | 33 Pipe Coating | 21 Detection Equipment |  | 50 Tanks | 47 Separators, Scrubbers, Gas Cleaners | 33 Pipe Coating
9 | 38 Land & Land Rights | 31 Gas Loss |  | 51 Valves - 2" inches and over | 50 Tanks | 38 Land & Land Rights
10 | 42 Pipeline Launchers and Receivers | 33 Pipe Coating |  | 54 Gas Pipe | 51 Valves - 2" inches and over | 39 Metering Equipment
11 | 47 Separators, Scrubbers, Gas Cleaners | 38 Land & Land Rights |  |  | 54 Gas Pipe | 45 Regulators
12 | 48 Farm Taps | 39 Metering Equipment |  |  |  | 47 Separators, Scrubbers, Gas Cleaners
13 | 49 Station Service Lines | 40 Odorizers |  |  |  | 49 Station Service Lines
14 | 50 Tanks | 45 Regulators |  |  |  | 51 Valves - 2" inches and over
15 | 51 Valves - 2" inches and over | 47 Separators, Scrubbers, Gas Cleaners |  |  |  | 54 Gas Pipe
16 | 54 Gas Pipe | 49 Station Service Lines
17 |  | 50 Tanks
18 |  | 51 Valves - 2" inches and over
19 |  | 54 Gas Pipe
| Compressor Station: | Dehydrator Station: | Pigging Facilities: | Secondary Containment Facility: | Gas Storage Facility:
1 | 04 Air Compression Equipment | 08 Flare System | 42 Pipeline Launchers and Receivers | 38 Land & Land Rights | 04 Air Compression Equipment
2 | 05 Auxiliary Power Supply Equipment | 13 Cathodic Protection Equipment | 31 Gas Loss | 50 Tanks | 05 Auxiliary Power Supply Equipment
3 | 08 Flare System | 14 Communication Equipment | 33 Pipe Coating | 51 Valves - 2" inches and over | 08 Flare System
4 | 12 Buildings | 16 Computer Equipment | 38 Land & Land Rights | 54 Gas Pipe | 11 Bridges - Aerial Crossing Structure
5 | 13 Cathodic Protection Equipment | 18 Control Equipment | 51 Valves - 2" inches and over |  | 12 Buildings
6 | 14 Communication Equipment | 20 Dehydrator | 54 Gas Pipe |  | 13 Cathodic Protection Equipment
7 | 15 Compressors and Drivers | 21 Detection Equipment |  |  | 14 Communication Equipment
8 | 16 Computer Equipment | 31 Gas Loss |  |  | 15 Compressors and Drivers
9 | 18 Control Equipment | 33 Pipe Coating |  |  | 18 Control Equipment
10 | 19 Cooling Systems | 38 Land & Land Rights |  |  | 19 Cooling Systems
11 | 20 Dehydrator | 47 Separators, Scrubbers, Gas Cleaners |  |  | 20 Dehydrator
12 | 21 Detection Equipment | 50 Tanks |  |  | 21 Detection Equipment
13 | 23 Drainage and Sewer Systems | 51 Valves - 2" inches and over |  |  | 24 Electrical Systems
14 | 24 Electrical Systems | 54 Gas Pipe |  |  | 30 Gas Line Pack
15 | 31 Gas Loss |  |  |  | 31 Gas Loss
16 | 33 Pipe Coating |  |  |  | 32 Gas Underground- Non-Recoverable
17 | 36 Hoisting System |  |  |  | 33 Pipe Coating
18 | 38 Land & Land Rights |  |  |  | 38 Land & Land Rights
19 | 39 Metering Equipment |  |  |  | 39 Metering Equipment
20 | 44 Pumps |  |  |  | 42 Pipeline Launchers and Receivers
21 | 45 Regulators |  |  |  | 44 Pumps
22 | 47 Separators, Scrubbers, Gas Cleaners |  |  |  | 45 Regulators
23 | 49 Station Service Lines |  |  |  | 47 Separators, Scrubbers, Gas Cleaners
24 | 50 Tanks |  |  |  | 48 Farm Taps
25 | 51 Valves - 2" inches and over |  |  |  | 49 Station Service Lines
26 | 54 Gas Pipe |  |  |  | 50 Tanks
51 Valves - 2" inches and over
54 Gas Pipe

## Settlement Rule Percentage
PROJECT AUTHORIZATION
Project Definition |  | Project Title
0 |  | Agave WT I/C
Project WBS
.01 |  | Install
WBS | Cost | PS |  | Current | Settlement
Element | Element | Asset | Materials | Cost | Percentage
.06 | 53500500 | 0 | Meter Station: | 0 | 0%
.06 |  | 08 | 08 Flare System | 0 | 0%
.06 |  | 12 | 12 Buildings | 0 | 0%
.06 |  | 13 | 13 Cathodic Protection Equipment | 0 | 0%
.06 |  | 14 | 14 Communication Equipment | 0 | 0%
.06 |  | 16 | 16 Computer Equipment | 0 | 0%
.06 |  | 18 | 18 Control Equipment | 0 | 0%
.06 |  | 20 | 20 Dehydrator | 0 | 0%
.06 |  | 21 | 21 Detection Equipment | 0 | 0%
.06 |  | 31 | 31 Gas Loss | 0 | 0%
.06 |  | 33 | 33 Pipe Coating | 0 | 0%
.06 |  | 38 | 38 Land & Land Rights | 0 | 0%
.06 |  | 39 | 39 Metering Equipment | 0 | 0%
.06 |  | 40 | 40 Odorizers | 0 | 0%
.06 |  | 45 | 45 Regulators | 0 | 0%
.06 |  | 47 | 47 Separators, Scrubbers, Gas Cleaners | 0 | 0%
.06 |  | 49 | 49 Station Service Lines | 2580 | 13.64%
.06 |  | 50 | 50 Tanks | 0 | 0%
.06 |  | 51 | 51 Valves - 2" inches and over | 10318 | 54.54%
.06 |  | 54 | 54 Gas Pipe | 5159 | 27.27%
.06 |  | 99 | 99 Allocated materials | 860 | 4.546%
.06 |  | 0 | 0 | 0 | 0%
.06 |  | 0 | 0 | 0 | 0%
.06 |  |  |  | 0 | 0%
|  |  |  | 18917 | 100%