## PS#5
(e)
Summary of EST, EFT, LST, LFT, slack and critical activities for Problem 15.9 (Creations store move)
| Activity | Description | Time | EST | EFT | LST | LFT | Slack | Critical Activity?
| A | install new plumbing | 10 | 0 | 10 | 4 | 14 | 4 | no
| B | order and receive furniture | 20 | 0 | 20 | 0 | 20 | 0 | yes
| C | order and receive flooring | 15 | 0 | 15 | 4 | 19 | 4 | no
| D | construct partitions | 5 | 0 | 5 | 9 | 14 | 9 | no
| E | paint and wallpaper | 5 | 10 | 15 | 14 | 19 | 4 | no
| F | install furniture | 3 | 20 | 23 | 20 | 23 | 0 | yes
| G | install flooring | 4 | 15 | 19 | 19 | 23 | 4 | no
| H | move inventory and records | 2 | 23 | 25 | 23 | 25 | 0 | yes
| I | clean old shop | 2 | 25 | 27 | 25 | 27 | 0 | yes