## Deal List (hidden)
PROJECT PHOENIX STATUS REPORT
AS OF AUGUST 17, 2001
| CUSTOMER | PHOENIX LEAD | PHOENIX SECOND | PORTFOLIO ORIGINATION | SERVICE MGMT | ACCOUNT MGMT | RISK MODELS | DEAL MGMT | DSM | SITE PROFILE | LEGAL | TRANSACTION SUPPORT | CONTRACT REVIEW % | REVIEW START | TARGET END | ORIG TARGET | MTM EXPOSURE (6/01)
[17 empty] | GAS | POWER | DSM | TOTAL
Priority
| American National Can/Rexam | - | - | Craig Childers | Becky Brakke | Javier Gallo | Ken Lee | Gerri Gobbi | - | Erling Brakke | Jim Keller | Nina Nguyen | 100% | 2001-06-15 | 2001-08-31 |  | -163711.9496 | -7976763 | 0 | -8140474.9496
| Chase | Scott Vonderheide | Chris Watts | Mike Harris | Cindy Stephens | Dag Joraholmen | Ken Lee | Roger Persson | - | Mary Sapilio | Mike Smith | - | 60% | 2001-07-30 | 2001-09-07 | Q3 | 0 | 5069473 | 0 | 5069473
| Molded Fiber Glass | Catherine Simoes | - | Charlene Jackson | Terry Lacy | Peter Johnston | Mike Kim | Gerri Gobbi | Rajesh Dhir | Murli Nagwani | - | David Saindon | 45% | 2001-08-13 | 2001-09-14 |  | 1465571.5732 | 5584887 | 2772983.2745 | 9823441.8477
| Owens Illinois | Saji John | Stephanie Segura | Maureen Palmer | Lisa Polk | Tony Valenzuela | Dickson Koo | Gerri Gobbi | - | Murli Nagwani | Jim Keller | David Saindon | 45% | 2001-08-06 | 2001-09-07 | Q3 | -2868929.1933 | -18474512 | 0 | -21343441.1933
| Quebecor | Oliver Jones | Chris Watts | Maureen Palmer | Whitney Fox | Bob Clifford | Ken Lee | Gerri Gobbi | Chad Corbit | Murli Nagwani | Michelle Maynard | David Saindon | 75% | 2001-07-18 | 2001-08-31 | Q3 | 19680375.7344 | 25017854 | 54940255.8585 | 99638485.593
| Simon Property Group (EMA/OA) | Terry Donovan | Chris Ahn | Mike Harris | Ben Smith | J Paul Oxer | Mike Kim | Gerri Gobbi | Chad Corbit | Murli Nagwani | Michelle Maynard | John Mackel | 25% | 2001-07-15 | 2001-09-30 | Q4 | -14925718.1557 | 28534667 | 21965938.5713 | 35574887.4155
| Springs Industries | Andy Chen | - | Charlene Jackson | Debra Blake | Kristin Griffin | Ken Lee | Roger Persson | Pedro Man | Mary Sapilio | Bill Rapp | Nina Nguyen | 95% | 2001-06-15 | 2001-08-24 | Q4 | 209933.5185 | 6862573 | 2714290.1101 | 9786796.6286
| Starwood | Saji John | Chris Ahn | Mike Harris | Kevin Boudreaux | Kevin Covack | Dickson Koo | Roger Persson | Rajesh Dhir | Murli Nagwani | - | Nina Nguyen | 100% | 2001-07-16 | 2001-08-24 | Q3 | 65735.797 | 5818212 | 0 | 5883947.797
| Suiza Foods | Terry Donovan | Rusty Parks | Richard Zdunkewicz | Kevin Boudreaux | C Allured | Joe Capasso | Gerri Gobbi | Andre Gibson | Mary Sapilio | Michelle Maynard | Nina Nguyen | 100% | 2001-06-01 | 2001-08-24 | Q4 | 32599318.6699 | -40991019 | 27628612.872 | 19236912.5419
| Tyco | Terry Donovan | Rusty Parks | Craig Childers | Florence Zoes | Scott Layne | Ken Lee | Gerri Gobbi | Pedro Man | Mary Sapilio | Debbie Asmus | Nina Nguyen | 85% | 2001-06-15 | 2001-08-31 | Q3 | 5113966.6395 | 1628446.73 | 15282357.1445 | 22024770.514
Tier Two
| ArchDiocese of Chicago | Saji John | Stephanie Segura | - | Rob Smith | Tim Novacyk | Mike Kim | - | Andre Gibson |  | Mike Smith | Nina Nguyen | 0% |  |  |  | 3265807.8305 | 2867733 | 0 | 6133540.8305
| BICCGeneral/General Cable | Saji John | Andy Chen | Charlene Jackson | Rhonda Short | Steve Swerdloff | Mike Kim | - | Franco Cuminato |  | - | - | 0% |  |  |  | 3043245.8074 |  | 4184499.9778 | 7227745.7853
| Eli Lilly | Edith Cross | Andy Chen | Craig Childers | Whitney Fox | Peter D'Lassandro | Dickson Koo | Steve Nguyen | Tarek Dou-Saada |  | Jim Keller | David Saindon | 25% | 2001-06-01 |  | Q4 | 6008507.8024 | 50585492 | 0 | 56593999.8024
| GGP | Oliver Jones | Stephanie Segura | Mike Harris | Becky Brakke | Victor Chael | Dickson Koo | Jeff Cobb | - |  | - | - | 0% |  |  | Q3 | 0 | -19719895 | 0 | -19719895
| IBM | Todd Perry | Chris Ahn | Richard Zdunkewicz | Ben Smith | Jeff Nieland | Ken Lee | Steve Nguyen | - |  | Mike Smith | Nina Nguyen | 5% |  |  | Q4 | 0 | -31851958 | 0 | -31851958
| Infomart | Scott Vonderheide | Chris Ahn | - | Nikita Harris | Peter Johnston | Mike Kim | - | Franco Cuminato |  | - | Nina Nguyen | 0% |  |  |  | 0 | 0 | 976484.9432 | 976484.9432
| JC Penney | Catherine Simoes | Chris Ahn | Mike Harris | Chris Copass | Bill Douglass | Mike Kim | Humberto Cubillos | Andre Gibson |  | - | Nina Nguyen | 0% |  |  |  | 18676.4338 | 37813691 | 0 | 37832367.4338
| Kaiser Healthcare | Scott Vonderheide | Chris Ahn | George Waidelich | - | - | Ken Lee | - | - |  | - | - | 0% |  |  |  | 87699.7922 | 0 | 0 | 87699.7922
| Lucent | Oliver Jones | Andy Chen | Tony Barnhart | - | Michael O Brown | Ken Lee | Matt Guin | - |  | - | - | 0% |  |  |  | 0 | -2905414 | 0 | -2905414
| Macerich | Catherine Simoes | Chris Watts | Mike Harris | Brent Edwards | - | Dickson Koo | Catherine Simoes | Chad Corbit |  | - | David Saindon | 0% |  |  |  | -16437.3314 | 412264 | 174175.4893 | 570002.1579
| Ocean Spray Cranberries, Inc. | Terry Donovan | Andy Chen | Richard Zdunkewicz | Nikita Harris | Chris Wheeler | Mike Kim | - | Franco Cuminato |  | - | - | 0% |  |  |  | 2638915.6081 | 0 | 2379268.6969 | 5018184.305
| Owens (includes Canada) | Catherine Simoes | Chris Ahn | Maureen Palmer | Lisa Polk | B Kortes | Ken Lee | - | Rajesh Dhir |  | Jim Keller | David Saindon | 10% | 2001-08-20 |  |  | 0 | 7873905 | 0 | 7873905
| Packaged Ice | Scott Vonderheide | Stephanie Segura | - | Ben Smith | Michell Faust | Mike Kim | - | Tim Sundel |  | Rich Freed | Nina Nguyen | 50% | 2001-06-15 | 2001-08-31 |  | 0 | -5696587 | 3018097.9451 | -2678489.0549
| Pilkington (includes Rossford, OH) | Oliver Jones | Chris Watts | Maureen Palmer | Lisa Polk | Barbara Kortes | Dickson Koo | Steve Nguyen | Andre Gibson |  | Ed Essandoh | Nina Nguyen | 0% |  |  |  | 34652335.3611 | 13704468.78 | 4591434.7378 | 52948238.879
| Polaroid | Saji John | Stephanie Segura | Richard Zdunkewicz | Debra Blake | Chris Wheeler | Mike Kim | - | Rajesh Dhir |  | Marianne Castano | Nina Nguyen | 0% |  |  |  | -166541.4905 | 0 | 4478915.6767 | 4312374.1861
| Prudential | Oliver Jones | Chris Watts | Tom Prisk | Nikita Harris | - | Dickson Koo | Jeff Cobb | - |  | - | David Saindon | 0% |  |  |  | 0 | 11184671 | 0 | 11184671
| Quaker | Saji John | Andy Chen | Charlene Jackson | Rob Krotee | John Tickell | Jerald Surface | Steve Nguyen | Rajesh Dhir |  | - | Nina Nguyen | 0% |  |  |  | 9413609.6532 | 12480057.89 | 9099397.7099 | 30993065.2531
| Rich Product | Scott Vonderheide | Chris Ahn | Richard Zdunkewicz | Richard Hannum | John Nanof | Jerald Surface | Jodi Thrasher | - |  | - | David Saindon | 0% |  |  |  | 1521984.4077 | -6826068 | 0 | -5304083.5923
| Ridge Tool | Scott Vonderheide | Stephanie Segura | - | Nikita Harris | Steve Beck | Mike Kim | Nat MacAdams | Andre Gibson |  | - | - | 0% |  |  |  | -86960.1048 | 0 | 1905055.231 | 1818095.1262
| Rite Aid | Catherine Simoes | Chris Watts | Lamar Frazier | - | - | - | - | - |  | - | - | 0%
| Saks | Terry Donovan | Stephanie Segura | Mike Harris | Whitney Fox | Bryan Gee | Mike Kim | Jeff Cobb | - |  | - | David Saindon | 0% |  |  |  | 2279682.5717 | -2661879 | 0 | -382196.4283
| Sonoco | Terry Donovan | Andy Chen | - | Debra Blake | Bryan Gee | Dickson Koo | Chris Riley | - |  | - | David Saindon | 0% |  |  |  | 0 | -9265142 | 0 | -9265142
| UC/CSU | Catherine Simoes | Chris Watts | Lamar Frazier | - | Tom Riley | Joe Capasso | - | Chad Corbit |  | Andy Wu | - | 0%
| READY FOR REBOOK | REBOOK TARGET
Starwood
Suiza Foods
| COMPLETE | DATE
American National Can/Rexam
PERCENT COMPLETE (simple avg)
TOTAL PROJECT COMPLETENESS
| FZ | Florence Zoes - Lead
| SW | Steve Watson - Lead
| DB | Don Black

## Orig (hidden)
PROJECT PHOENIX STATUS REPORT
| CUSTOMER | PHOENIX LEAD | PHOENIX SECOND | PORTFOLIO ORIGINATION | SERVICE MGMT | ACCOUNT MGMT | RISK MODELS | DEAL MGMT | DSM | LEGAL | TRANSACTION SUPPORT | ORIG TARGET | CONTRACT REVIEW % | TARGET END | MTM EXPOSURE (6/01)
[15 empty] | GAS | POWER | DSM | TOTAL | DSM | TOTAL
Priority
| American National Can/Rexam | - | - | Craig Childers | Becky Brakke | Javier Gallo | Ken Lee | Gerri Gobbi | - | Jim Keller | Nina Nguyen | - | - | 'Deal List'!Q8) | 2001-08-31 | #REF! | -163711.9496 | -7976763 | 0 | -8140474.9496
| Chase | Scott Vonderheide | Chris Watts | Mike Harris | Cindy Stephens | Dag Joraholmen | Ken Lee | Roger Persson | - | Mike Smith | - | Q3 | 60% | 37102 | 37141 | #REF! | 0 | 5069473 | 0 | 5069473
| Molded Fiber Glass | Catherine Simoes | - | Charlene Jackson | Terry Lacy | Peter Johnston | Mike Kim | Gerri Gobbi | Rajesh Dhir | - | David Saindon | - | 45% | 2001-08-13 | 2001-09-14 | #REF! | 1465571.5732 | 5584887 | 2772983.2745 | 9823441.8477
| Owens Illinois | Saji John | Stephanie Segura | Maureen Palmer | Lisa Polk | Tony Valenzuela | Dickson Koo | Gerri Gobbi | - | Jim Keller | David Saindon | Q3 | 45% | 2001-08-06 | 2001-09-07 | #REF! | -2868929.1933 | -18474512 | 0 | -21343441.1933
| Quebecor | Oliver Jones | Chris Watts | Maureen Palmer | Whitney Fox | Bob Clifford | Ken Lee | Gerri Gobbi | Chad Corbit | Michelle Maynard | David Saindon | Q3 | 75% | 2001-07-18 | 2001-08-31 | #REF! | 19680375.7344 | 25017854 | 54940255.8585 | 99638485.593
| Simon Property Group (EMA/OA) | Terry Donovan | Chris Ahn | Mike Harris | Ben Smith | J Paul Oxer | Mike Kim | Gerri Gobbi | Chad Corbit | Michelle Maynard | John Mackel | Q4 | 25% | 2001-07-15 | 2001-09-30 | #REF! | -14925718.1557 | 28534667 | 21965938.5713 | 35574887.4155
| Springs Industries | Andy Chen | - | Charlene Jackson | Debra Blake | Kristin Griffin | Ken Lee | Roger Persson | Pedro Man | Bill Rapp | Nina Nguyen | Q4 | 95% | 2001-06-15 | 37127 | #REF! | 209933.5185 | 6862573 | 2714290.1101 | 9786796.6286
| Starwood | Saji John | Chris Ahn | Mike Harris | Kevin Boudreaux | Kevin Covack | Dickson Koo | Roger Persson | Rajesh Dhir | - | Nina Nguyen | Q3 | 100% | 2001-07-16 | 37127 | #REF! | 65735.797 | 5818212 | 0 | 5883947.797
| Suiza Foods | Terry Donovan | Rusty Parks | Richard Zdunkewicz | Kevin Boudreaux | C Allured | Joe Capasso | Gerri Gobbi | Andre Gibson | Michelle Maynard | Nina Nguyen | Q4 | 100% | 2001-06-01 | 37127 | #REF! | 32599318.6699 | -40991019 | 27628612.872 | 19236912.5419
| Tyco | Terry Donovan | Rusty Parks | Craig Childers | Florence Zoes | Scott Layne | Ken Lee | Gerri Gobbi | Pedro Man | Debbie Asmus | Nina Nguyen | Q3 | 85% | 2001-06-15 | 37134 | #REF! | 5113966.6395 | 1628446.73 | 15282357.1445 | 22024770.514
Tier Two
| ArchDiocese of Chicago | Saji John | Stephanie Segura | - | Rob Smith | Tim Novacyk | Mike Kim | - | Andre Gibson | Mike Smith | Nina Nguyen | - | 0% | 0 | 0 | #REF! | 3265807.8305 | 2867733 | 0 | 6133540.8305
| BICCGeneral/General Cable | Saji John | Andy Chen | Charlene Jackson | Rhonda Short | Steve Swerdloff | Mike Kim | - | Franco Cuminato | - | - | - | 0% | 0 | 0 | #REF! | 3043245.8074 | 0 | 4184499.9778 | 7227745.7853
| Eli Lilly | Edith Cross | Andy Chen | Craig Childers | Whitney Fox | Peter D'Lassandro | Dickson Koo | Steve Nguyen | Tarek Dou-Saada | Jim Keller | David Saindon | - | 25% | 37043 | 0 | #REF! | 6008507.8024 | 50585492 | 0 | 56593999.8024
| GGP | Oliver Jones | Stephanie Segura | Mike Harris | Becky Brakke | Victor Chael | Dickson Koo | Jeff Cobb | - | - | - | Q4 | 0% | 0 | 0 | #REF! | 0 | -19719895 | 0 | -19719895
| IBM | Todd Perry | Chris Ahn | Richard Zdunkewicz | Ben Smith | Jeff Nieland | Ken Lee | Steve Nguyen | - | Mike Smith | Nina Nguyen | Q3 | 5% | 0 | 0 | #REF! | 0 | -31851958 | 0 | -31851958
| Infomart | Scott Vonderheide | Chris Ahn | - | Nikita Harris | Peter Johnston | Mike Kim | - | Franco Cuminato | - | Nina Nguyen | Q4 | 0% | 0 | 0 | #REF! | 0 | 0 | 976484.9432 | 976484.9432
| JC Penney | Catherine Simoes | Chris Ahn | Mike Harris | Chris Copass | Bill Douglass | Mike Kim | Humberto Cubillos | Andre Gibson | - | Nina Nguyen | - | 0% | 0 | 0 | #REF! | 18676.4338 | 37813691 | 0 | 37832367.4338
| Kaiser Healthcare | Scott Vonderheide | Chris Ahn | George Waidelich | - | - | Ken Lee | - | - | - | - | - | 0% | 0 | 0 | #REF! | 87699.7922 | 0 | 0 | 87699.7922
| Lucent | Oliver Jones | Andy Chen | Tony Barnhart | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | - | 0% | #REF! | #REF! | #REF! | 0 | -2905414 | 0 | -2905414
| Macerich | Catherine Simoes | Chris Watts | Mike Harris | Brent Edwards | - | Dickson Koo | Catherine Simoes | Chad Corbit | - | David Saindon | - | 0% | 0 | 0 | #REF! | -16437.3314 | 412264 | 174175.4893 | 570002.1579
| Ocean Spray Cranberries, Inc. | Terry Donovan | Andy Chen | Richard Zdunkewicz | Nikita Harris | Chris Wheeler | Mike Kim | - | Franco Cuminato | - | - | - | 0% | 0 | 0 | #REF! | 2638915.6081 | 0 | 2379268.6969 | 5018184.305
| Owens (includes Canada) | Catherine Simoes | Chris Ahn | Maureen Palmer | Lisa Polk | B Kortes | Ken Lee | - | Rajesh Dhir | Jim Keller | David Saindon | - | 10% | 37123 | 0 | #REF! | 0 | 7873905 | 0 | 7873905
| Packaged Ice | Scott Vonderheide | Stephanie Segura | - | Ben Smith | Michell Faust | Mike Kim | - | Tim Sundel | Rich Freed | Nina Nguyen | - | 50% | 37057 | 37134 | #REF! | 0 | -5696587 | 3018097.9451 | -2678489.0549
| Pilkington (includes Rossford, OH) | Oliver Jones | Chris Watts | Maureen Palmer | Lisa Polk | Barbara Kortes | Dickson Koo | Steve Nguyen | Andre Gibson | Ed Essandoh | Nina Nguyen | - | 0% | 0 | 0 | #REF! | 34652335.3611 | 13704468.78 | 4591434.7378 | 52948238.879
| Polaroid | Saji John | Stephanie Segura | Richard Zdunkewicz | Debra Blake | Chris Wheeler | Mike Kim | - | Rajesh Dhir | Marianne Castano | Nina Nguyen | - | 0% | 0 | 0 | #REF! | -166541.4905 | 0 | 4478915.6767 | 4312374.1861
| Prudential | Oliver Jones | Chris Watts | Tom Prisk | Nikita Harris | - | Dickson Koo | Jeff Cobb | - | - | David Saindon | - | 0% | 0 | 0 | #REF! | 0 | 11184671 | 0 | 11184671
| Quaker | Saji John | Andy Chen | Charlene Jackson | Rob Krotee | John Tickell | Jerald Surface | Steve Nguyen | Rajesh Dhir | - | Nina Nguyen | - | 0% | 0 | 0 | #REF! | 9413609.6532 | 12480057.89 | 9099397.7099 | 30993065.2531
| Rich Product | Scott Vonderheide | Chris Ahn | Richard Zdunkewicz | - | Michael O Brown | Ken Lee | Matt Guin | - | - | - | - | 0% | 0 | 0 | #REF! | 1521984.4077 | -6826068 | 0 | -5304083.5923
| Ridge Tool | Scott Vonderheide | Stephanie Segura | - | Richard Hannum | John Nanof | Jerald Surface | Jodi Thrasher | - | - | David Saindon | - | 0% | 0 | 0 | #REF! | -86960.1048 | 0 | 1905055.231 | 1818095.1262
| Rite Aid | Catherine Simoes | Chris Watts | Lamar Frazier | Nikita Harris | Steve Beck | Mike Kim | Nat MacAdams | Andre Gibson | - | - | - | 0% | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| Saks | Terry Donovan | Stephanie Segura | Mike Harris | - | - | - | - | - | - | - | - | 0% | 0 | 0 | #REF! | 2279682.5717 | -2661879 | 0 | -382196.4283
| Sonoco | Terry Donovan | Andy Chen | - | Whitney Fox | Bryan Gee | Mike Kim | Jeff Cobb | - | - | David Saindon | - | 0% | 0 | 0 | #REF! | 0 | -9265142 | 0 | -9265142
| UC/CSU | Catherine Simoes | Chris Watts | Lamar Frazier | - | Tom Riley | Joe Capasso | - | Chad Corbit | Andy Wu | - | - | 0% | 0 | 0 | #REF! | 0 | 0 | 0 | 0
| READY FOR REBOOK | REBOOK TARGET
| Starwood | 0
| Suiza Foods | 0
| COMPLETE | DATE
| American National Can/Rexam | 0
PERCENT COMPLETE (simple avg)
TOTAL PROJECT COMPLETENESS
| FZ | Florence Zoes - Lead
| SW | Steve Watson - Lead
| DB | Don Black

## Mgmt (hidden)
PROJECT PHOENIX STATUS REPORT
| CUSTOMER | PHOENIX LEAD | PHOENIX SECOND | PORTFOLIO ORIGINATION | SERVICE MGMT | ACCOUNT MGMT | RISK MODELS | DEAL MGMT | DSM | LEGAL | TRANSACTION SUPPORT | CONTRACT REVIEW % | REVIEW START | TARGET END | ORIG TARGET
Priority
| American National Can/Rexam | - | - | Craig Childers | Becky Brakke | Javier Gallo | Ken Lee | Gerri Gobbi | - | Jim Keller | Nina Nguyen | 100% | 2001-06-15 | 2001-08-31 | -
| Chase | Scott Vonderheide | Chris Watts | Mike Harris | Cindy Stephens | Dag Joraholmen | Ken Lee | Roger Persson | - | Mike Smith | - | 60% | 2001-07-30 | 2001-09-07 | Q3
| Molded Fiber Glass | Catherine Simoes | - | Charlene Jackson | Terry Lacy | Peter Johnston | Mike Kim | Gerri Gobbi | Rajesh Dhir | - | David Saindon | 45% | 2001-08-13 | 2001-09-14 | -
| Owens Illinois | Saji John | Stephanie Segura | Maureen Palmer | Lisa Polk | Tony Valenzuela | Dickson Koo | Gerri Gobbi | - | Jim Keller | David Saindon | 45% | 2001-08-06 | 2001-09-07 | Q3
| Quebecor | Oliver Jones | Chris Watts | Maureen Palmer | Whitney Fox | Bob Clifford | Ken Lee | Gerri Gobbi | Chad Corbit | Michelle Maynard | David Saindon | 75% | 2001-07-18 | 2001-08-31 | Q3
| Simon Property Group (EMA/OA) | Terry Donovan | Chris Ahn | Mike Harris | Ben Smith | J Paul Oxer | Mike Kim | Gerri Gobbi | Chad Corbit | Michelle Maynard | John Mackel | 25% | 2001-07-15 | 2001-09-30 | Q4
| Springs Industries | Andy Chen | - | Charlene Jackson | Debra Blake | Kristin Griffin | Ken Lee | Roger Persson | Pedro Man | Bill Rapp | Nina Nguyen | 95% | 2001-06-15 | 2001-08-24 | Q4
| Starwood | Saji John | Chris Ahn | Mike Harris | Kevin Boudreaux | Kevin Covack | Dickson Koo | Roger Persson | Rajesh Dhir | - | Nina Nguyen | 100% | 2001-07-16 | 2001-08-24 | Q3
| Suiza Foods | Terry Donovan | Rusty Parks | Richard Zdunkewicz | Kevin Boudreaux | C Allured | Joe Capasso | Gerri Gobbi | Andre Gibson | Michelle Maynard | Nina Nguyen | 100% | 2001-06-01 | 2001-08-24 | Q4
| Tyco | Terry Donovan | Rusty Parks | Craig Childers | Florence Zoes | Scott Layne | Ken Lee | Gerri Gobbi | Pedro Man | Debbie Asmus | Nina Nguyen | 85% | 2001-06-15 | 2001-08-31 | Q3
Tier Two
| ArchDiocese of Chicago | Saji John | Stephanie Segura | - | Rob Smith | Tim Novacyk | Mike Kim | - | Andre Gibson | Mike Smith | Nina Nguyen | 0% | 0 | 0 | -
| BICCGeneral/General Cable | Saji John | Andy Chen | Charlene Jackson | Rhonda Short | Steve Swerdloff | Mike Kim | - | Franco Cuminato | - | - | 0% | 0 | 0 | -
| Eli Lilly | Edith Cross | Andy Chen | Craig Childers | Whitney Fox | Peter D'Lassandro | Dickson Koo | Steve Nguyen | Tarek Dou-Saada | Jim Keller | David Saindon | 0% | 0 | 0 | -
| GGP | Oliver Jones | Stephanie Segura | Mike Harris | Becky Brakke | Victor Chael | Dickson Koo | Jeff Cobb | - | - | - | 25% | 2001-06-01 | 0 | Q4
| IBM | Todd Perry | Chris Ahn | Richard Zdunkewicz | Ben Smith | Jeff Nieland | Ken Lee | Steve Nguyen | - | Mike Smith | Nina Nguyen | 0% | 0 | 0 | Q3
| Infomart | Scott Vonderheide | Chris Ahn | - | Nikita Harris | Peter Johnston | Mike Kim | - | Franco Cuminato | - | Nina Nguyen | 5% | 0 | 0 | Q4
| JC Penney | Catherine Simoes | Chris Ahn | Mike Harris | Chris Copass | Bill Douglass | Mike Kim | Humberto Cubillos | Andre Gibson | - | Nina Nguyen | 0% | 0 | 0 | -
| Kaiser Healthcare | Scott Vonderheide | Chris Ahn | George Waidelich | - | - | Ken Lee | - | - | - | - | 0% | 0 | 0 | -
| Lucent | Oliver Jones | Andy Chen | Tony Barnhart | - | Michael O Brown | Ken Lee | Matt Guin | - | - | - | 0% | 0 | 0 | -
| Macerich | Catherine Simoes | Chris Watts | Mike Harris | Brent Edwards | - | Dickson Koo | Catherine Simoes | Chad Corbit | - | David Saindon | 0% | 0 | 0 | -
| Ocean Spray Cranberries, Inc. | Terry Donovan | Andy Chen | Richard Zdunkewicz | Nikita Harris | Chris Wheeler | Mike Kim | - | Franco Cuminato | - | - | 0% | 0 | 0 | -
| Owens (includes Canada) | Catherine Simoes | Chris Ahn | Maureen Palmer | Lisa Polk | B Kortes | Ken Lee | - | Rajesh Dhir | Jim Keller | David Saindon | 0% | 0 | 0 | -
| Packaged Ice | Scott Vonderheide | Stephanie Segura | - | Ben Smith | Michell Faust | Mike Kim | - | Tim Sundel | Rich Freed | Nina Nguyen | 10% | 2001-08-20 | 0 | -
| Pilkington (includes Rossford, OH) | Oliver Jones | Chris Watts | Maureen Palmer | Lisa Polk | Barbara Kortes | Dickson Koo | Steve Nguyen | Andre Gibson | Ed Essandoh | Nina Nguyen | 50% | 2001-06-15 | 2001-08-31 | -
| Polaroid | Saji John | Stephanie Segura | Richard Zdunkewicz | Debra Blake | Chris Wheeler | Mike Kim | - | Rajesh Dhir | Marianne Castano | Nina Nguyen | 0% | 0 | 0 | -
| Prudential | Oliver Jones | Chris Watts | Tom Prisk | Nikita Harris | - | Dickson Koo | Jeff Cobb | - | - | David Saindon | 0% | 0 | 0 | -
| Quaker | Saji John | Andy Chen | Charlene Jackson | Rob Krotee | John Tickell | Jerald Surface | Steve Nguyen | Rajesh Dhir | - | Nina Nguyen | 0% | 0 | 0 | -
| Rich Product | Scott Vonderheide | Chris Ahn | Richard Zdunkewicz | - | Michael O Brown | Ken Lee | Matt Guin | - | - | - | 0% | 0 | 0 | -
| Ridge Tool | Scott Vonderheide | Stephanie Segura | - | Richard Hannum | John Nanof | Jerald Surface | Jodi Thrasher | - | - | David Saindon | 0% | 0 | 0 | -
| Rite Aid | Catherine Simoes | Chris Watts | Lamar Frazier | Nikita Harris | Steve Beck | Mike Kim | Nat MacAdams | Andre Gibson | - | - | 0% | 0 | 0 | -
| Saks | Terry Donovan | Stephanie Segura | Mike Harris | - | - | - | - | - | - | - | 0% | 0 | 0 | -
| Sonoco | Terry Donovan | Andy Chen | - | Whitney Fox | Bryan Gee | Mike Kim | Jeff Cobb | - | - | David Saindon | 0% | 0 | 0 | -
| UC/CSU | Catherine Simoes | Chris Watts | Lamar Frazier | - | Tom Riley | Joe Capasso | - | Chad Corbit | Andy Wu | - | 0% | 0 | 0 | -
| READY FOR REBOOK | REBOOK TARGET
| Starwood | 0
| Suiza Foods | 0
| COMPLETE | DATE
| American National Can/Rexam | 0
PERCENT COMPLETE (simple avg)
TOTAL PROJECT COMPLETENESS
| FZ | Florence Zoes - Lead
| SW | Steve Watson - Lead
| DB | Don Black

## Master Index (hidden)
PROJECT PHOENIX
CONTRACT MASTER INDEX
As of AUGUST 3, 2001
REQUIRED MASTER DATA
INITIALLY FOR PHASE I *
|  |  | CONTRACT REVIEW | SERVICE MGR/ | ACCOUNT | MODEL/BOOK | DEAL MGMT | DSM | LEGAL | TRANSACTION SUPPORT |  |  |  |  | 3/5 page | REVENUE |  | COPIES OF | BILLING | DEEP DIVE | CONSUMPTION
| Customer | DEAL TYPE | LEAD | ORIGINATION | MANAGER | CONTACT | CONTACT | CONTACT | CONTACT | CONTACT | CONTRACT | AMENDMENTS | SITE LIST | TAF/DASH | k overview | Allocation |  | INVOICES | FORMULA | SUMMARY | DATA | STATUS
| Priority | Catherine Simoes
| American National Can/Rexam | Commodity | Steve Swain | Becky Brakke | Javier Gallo | Ken Lee | Casey Ragsdale |  | Jim Keller | Nina Nguyen | X | X | X | X | X | NA | 1 | X | X | NA |  | 90%
| Chase | Outsource |  | Cindy Stephens | Dag Joraholmen | Ken Lee | Jodi Thrasher |  | Mike Smith |  | X | X | X | X | X | NA | 1 | X | X | NA |  | 90%
| Molded Fiber Glass | Outsource | Stephanie Segura | Terry Lacy | Peter Johnston | Mike Kim | Casey Ragsdale | Rajesh Dhir |  | David Saindon | X | X | X | X | X | NA | 1 | X | X | X |  | 90%
| Owens Illinois | Outsource |  | Lisa Polk | Tony Valenzuela | Dickson Koo | Ursula Brenner |  |  | David Saindon | X | NA | X | X | X | NA | 1 | X | X | NA |  | 90%
| Quebecor | - | Rogers Herndon | Whitney Fox | Bob Clifford | Ken Lee | Steve Nguyen | Chad Corbit | Michelle Maynard | David Saindon | X | X | X | X | X | NA | 1 | X | X | X |  | 90%
| Simon Property Group (EMA/OA) | Outsource | Terry Donovan | Ben Smith | J Paul Oxer | Mike Kim | Nat MacAdams | Chad Corbit | Michelle Maynard | John Mackel | X | X | X | X | X | X | 1 | X |  | X |  | 80%
| Springs Industries | Outsource | Andy Chen | Debra Blake | Kristin Griffin | Ken Lee | Jodi Thrasher | Pedro Man | Bill Rapp | Nina Nguyen | X | X | X | X | X | X | 1 | X |  | X |  | 80%
| Starwood | [9 empty] | X | X | X | X | X | NA |  | X |  | X |  | 80%
| Suiza Foods | Outsource | Terry Donovan | Kevin Boudreaux | C Allured | Joe Capasso |  | Andre Gibson | Michelle Maynard | Nina Nguyen | X | X | X | X | X | X | 1 | X | NA | X |  | 90%
| Tyco | [9 empty] | X | X | X | X | X | X |  | X | X | X |  | 90%
| ArchDiocese of Chicago | Catherine Simoes | JD Buss | Rob Smith | Tim Novacyk | Mike Kim |  | Andre Gibson | Mike Smith | Nina Nguyen | X | NA | X | X | X | NA | 1 | X | X | X |  | 90%
| BICCGeneral/General Cable | Outsource |  | Rhonda Short | Steve Swerdloff | Mike Kim |  | Franco Cuminato |  |  | X | X | X | X | X | NA | 1 | X | X | NA |  | 90%
| Eli Lilly | Outsource | Edith Cross | Whitney Fox | Peter D'Lassandro | Dickson Koo | Steve Nguyen | Tarek Dou-Saada | Jim Keller | David Saindon | X | NA | X | X | X | NA | 1 | X | X | NA |  | 90%
| GGP | Commodity |  | Becky Brakke | Victor Chael | Dickson Koo | Jeff Cobb |  |  |  | X | NA | X | X | X | NA | 1 | X |  | NA |  | 80%
| IBM | Outsource | Todd Perry | Ben Smith | Jeff Nieland | Ken Lee | Steve Nguyen |  | Mike Smith | Nina Nguyen | X | X | X | X | X | NA | 1 | X | X | X |  | 90%
| Infomart | Outsource | Vladimir Gorny | Nikita Harris | Peter Johnston | Mike Kim |  | Franco Cuminato |  | Nina Nguyen | X | X | X | X | X | X | 1 | X | X | X |  | 90%
| JC Penney | Outsource |  | Chris Copass | Bill Douglass | Mike Kim | Humberto Cubillos | Andre Gibson |  | Nina Nguyen | X | X | X | X | X | NA | 1 | X | X | NA |  | 90%
| Kaiser Healthcare | Commodity |  |  |  | Ken Lee |  |  |  |  | X | X | NA | X | X | NA | 1 | X | NA | NA |  | 90%
| Lucent | Commodity |  |  | Michael O Brown | Ken Lee | Matt Guin |  |  |  | X | NA | X | X |  | NA | 1 | X | X | NA |  | 80%
| Macerich | Outsource |  | Brent Edwards |  | Dickson Koo | Catherine Simoes | Chad Corbit |  | David Saindon | X | X | X | X | X | X | 1 | X | X | NA |  | 90%
| Ocean Spray Cranberries, Inc. | Outsource |  | Whitney Fox | Chris Wheeler | Mike Kim |  | Franco Cuminato |  |  | X | NA | X | X | X | NA | 1 | X | X | NA |  | 90%
| Owens (includes Canada) | Outsource | Brad Morse | Lisa Polk | B Kortes | Ken Lee | April Wu | Rajesh Dhir | Jim Keller | David Saindon | X | NA | X | X | X | NA | 1 | X | X | X |  | 90%
| Packaged Ice | Saji John | Scott Vonderheide | Ben Smith | Michell Faust | Mike Kim |  | Tim Sundel | Rich Freed | Nina Nguyen | X | X | X | X | X | NA | 1 | X | X | NA |  | 90%
| Pilkington (includes Rossford, OH) | Outsource | Andy Chen | Lisa Polk | Barbara Kortes | Dickson Koo | Steve Nguyen | Andre Gibson | Ed Essandoh | Nina Nguyen | X | X | X | X | X | NA | 1 | X | X | NA |  | 90%
| Polaroid | Outsource | Lacretia Davenport | Debra Blake | Chris Wheeler | Mike Kim |  | Rajesh Dhir | Marianne Castano | Nina Nguyen | X | X | X | X | X | X | 1 | X | X | NA |  | 90%
| Prudential | Commodity |  | Nikita Harris |  | Dickson Koo | Jeff Cobb |  |  | David Saindon | X | X | X | X | X | NA | 1 |  |  | X |  | 70%
| Quaker | Outsource |  | Rob Krotee | John Tickell | Jerald Surface | Steve Nguyen | Rajesh Dhir |  | Nina Nguyen | X | NA | X | X | X | X | 1 | X | X | NA |  | 90%
| Rich Product | Commodity |  | Whitney Fox | John Nanof | Jerald Surface | Jodi Thrasher |  |  | David Saindon | X | NA | X | X | X | NA | 1 | X | X | NA |  | 90%
| Ridge Tool | Outsource |  | Nikita Harris | Steve Beck | Mike Kim | Nat MacAdams | Andre Gibson |  |  | X | NA | X | X | X | NA | 1 | X | X | X |  | 90%
| Rite Aid | Commodity | [6 empty] | No one (purchased from PG&E) |  | X | X | X |  |  | NA | 1 |  |  | NA |  | 50%
| Saks | Commodity |  | Whitney Fox | Bryan Gee | Mike Kim | Jeff Cobb |  |  | David Saindon | X | NA | X | X | X | NA | 1 | X | X | NA |  | 90%
| Sonoco | Commodity |  | Debra Blake | Bryan Gee | Dickson Koo | Chris Riley |  |  | David Saindon | X | NA | X | X | X | NA | 1 | X | X | NA |  | 90%
| UC/CSU | Outsource | Todd Perry |  | Tom Riley | Joe Capasso |  | Chad Corbit | Andy Wu |  | X |  |  | X |  | NA | 1 |  |  | NA |  | 40%
% of contracts received
Other
1 | Air Products and Chemicals, Inc. | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
2 | Albertson's | [5 empty] | Matt Guin |  |  |  | X |  |  | X |  |  | 1 |  |  |  |  | 20%
3 | American Electric Commodity | Commodity | [13 empty] | NA | 0 |  |  |  |  | 10%
4 | American Stores | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
5 | Applied Material | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
6 | Aquila Energy | [15 empty] | 0 |  |  |  |  | 0%
7 | Atlantic Health | [5 empty] | Matt Guin |  |  |  | X | [5 empty] | 1 |  |  |  |  | 10%
8 | Beth Israel | Commodity |  |  |  |  | Jeanette Reese |  |  |  | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
9 | Blue Diamond Materials Div. / Sully Miller Contr. | Commodity | [13 empty] | NA | 0 |  |  |  |  | 10%
10 | Bridgestone Firestone | [9 empty] | X | [5 empty] | 1 |  |  |  |  | 10%
11 | Burger King | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
12 | Catholic Health East | [5 empty] | Jeanette Reese |  |  |  | X |  |  | X |  |  | 1 |  |  |  |  | 20%
13 | CCL | Commodity | [8 empty] | X | X |  |  |  | NA | 1 |  |  |  |  | 30%
14 | Checker | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
15 | Cisco | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
16 | Columbia Gas Transmission | [9 empty] | X | X |  |  |  |  | 1 |  |  |  |  | 20%
17 | Compaq | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
18 | Connect Energy Services, Inc. | [15 empty] | 0 |  |  |  |  | 0%
19 | Crossroads | [9 empty] | X | [5 empty] | 1 |  |  |  |  | 10%
20 | Darden Restaurants | Commodity | [8 empty] | X | X |  |  |  | NA | 1 |  |  |  |  | 30%
21 | DESC - Nellis | [12 empty] | X |  |  | 0 |  |  |  |  | 10%
22 | Developer's Funding Co. | [15 empty] | 0 |  |  |  |  | 0%
23 | Dominion Transmission | [9 empty] | X | [5 empty] | 1 |  |  |  |  | 10%
24 | Duke Energy Trading & Marketing, LLC | [9 empty] | X | [5 empty] | 1 |  |  |  |  | 10%
25 | Durst | [9 empty] | X | [5 empty] | 1 |  |  |  |  | 10%
26 | Dynegy | [15 empty] | 0 |  |  |  |  | 0%
27 | Enron Compression Services | [5 empty] | Jeanette Reese |  |  |  | X | [5 empty] | 1 |  |  |  |  | 10%
28 | Enserch Energy | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
29 | Equity Office | Commodity |  |  |  |  | Martinez |  |  |  | X | X |  |  |  | NA | 1 |  |  |  |  | 30%
30 | Family Restaurants | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
31 | Fidelity | [5 empty] | Gisselle Rohmer |  |  |  | X | [5 empty] | 1 |  |  |  |  | 10%
32 | Gen Probe | Commodity |  |  |  |  | Gisselle Rohmer |  |  |  | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
33 | Genentech Inc | Commodity | [8 empty] | X |  |  | X |  | NA | 1 |  |  |  |  | 30%
34 | Glen-Gery Corporation | [15 empty] | 0 |  |  |  |  | 0%
35 | Graniterock Company | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
36 | GSA | [9 empty] | X | [5 empty] | 1 |  |  |  |  | 10%
37 | Homestake Mining | [9 empty] | X | [5 empty] | 1 |  |  |  |  | 10%
38 | Hyatt | Commodity | [9 empty] | X |  |  |  | NA | 0 |  |  |  |  | 20%
39 | Illinois State | [9 empty] | X | [5 empty] | 1 |  |  |  |  | 10%
40 | International Paper | Commodity | [8 empty] | X | X |  |  |  | NA | 1 |  |  |  |  | 30%
41 | Irvine | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
42 | Kellogg - Pace Energy | [9 empty] | X | [5 empty] | 1 |  |  |  |  | 10%
43 | Lam Research | Commodity | [8 empty] | X |  |  | X |  | NA | 1 |  |  |  |  | 30%
44 | Marathon | [9 empty] | X |  |  | X |  |  | 1 |  |  |  |  | 20%
45 | McDonalds | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
46 | MRT Transport #434 | [15 empty] | 0 |  |  |  |  | 0%
47 | New Commodity Company | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
48 | Northrop Grumman | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
49 | Novellus | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
50 | Nummi | Commodity | [8 empty] | X |  |  | X |  | NA | 1 |  |  |  |  | 30%
51 | OCM Boces | Commodity |  |  |  |  | Jeanette Reese |  |  |  | X | X |  | X |  | NA | 1 |  |  |  |  | 40%
52 | Ohio MSG | Commodity |  |  |  |  | JD Burrows |  |  |  | X | X |  |  |  | NA | 1 |  |  |  |  | 30%
53 | Optical Lab | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
54 | PanCanadian | [15 empty] | 0 |  |  |  |  | 0%
55 | Promus Hotel | Commodity | [8 empty] | X | X |  |  |  | NA | 1 |  |  |  |  | 30%
56 | Raychem | Commodity | [8 empty] | X |  | X | X |  | NA | 1 |  |  |  |  | 40%
57 | Riverside County | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
58 | Robert Wood Johnson | [5 empty] | Jeanette Reese |  |  |  | X | X |  |  |  |  | 1 |  |  |  |  | 20%
59 | S. B. Linden | [15 empty] | 0 |  |  |  |  | 0%
60 | Safeway | Commodity | [8 empty] | X | X |  |  |  | NA | 1 |  |  |  |  | 30%
61 | Seagate | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
62 | Shaw Supermarket | Commodity |  |  |  |  | Gisselle Rohmer |  |  |  | X | X |  | X |  | NA | 1 |  |  |  |  | 40%
63 | Silicon Graphics | Commodity | [8 empty] | X |  |  | X |  | NA | 1 |  |  |  |  | 30%
64 | Solo Cup | [10 empty] | X |  | X |  |  | 0 |  |  |  |  | 20%
65 | Southern Management | Commodity | [13 empty] | NA | 0 |  |  |  |  | 10%
66 | Southland | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
67 | Sutter Healthcare | Commodity | [8 empty] | X |  |  | X |  | NA | 1 |  |  |  |  | 30%
68 | Target | [5 empty] | Tom Baldwin |  |  |  | X | [5 empty] | 1 |  |  |  |  | 10%
69 | Techneglas | [15 empty] | 0 |  |  |  |  | 0%
70 | Telecordia | [5 empty] | Tom Baldwin |  |  |  | X | [5 empty] | 1 |  |  |  |  | 10%
71 | Temple Steel | [9 empty] | X | [5 empty] | 1 |  |  |  |  | 10%
72 | Tenneco | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
73 | Texaco Natural Gas | [15 empty] | 0 |  |  |  |  | 0%
74 | TransCanada Energy Marketing USA | Commodity | [8 empty] | X |  |  |  |  | NA | 1 |  |  |  |  | 20%
75 | Transcontinental Gas Pipe Line Corp. | [15 empty] | 0 |  |  |  |  | 0%
76 | U of Chicago | [9 empty] | X | [5 empty] | 1 |  |  |  |  | 10%
77 | Verizon | Commodity |  |  |  |  | Matt Guin |  |  |  | X |  |  | X |  | NA | 1 |  |  |  |  | 30%
Note on B14: kharris2: also World Color
Note on B52: mbarrett: American Stores owns Albertson's. Contract is with Albertson's,
Note on B68: mbarrett: Darden and GMRI are the same. We have documentation to validate.

## Phase by Phase Status
PROJECT PHOENIX STATUS REPORT
AS OF AUGUST 17, 2001
| CUSTOMER | PHOENIX LEAD | PORTFOLIO ORIGINATION | SERVICE MGMT | ACCOUNT MGMT | RISK MODELS | DEAL MGMT | DSM | LEGAL | TRANSACTION SUPPORT | DEAL DOCUMENTATION |  | CONTRACT ANALYSIS |  | IMPLEMENTATION
Priority
| American National Can/Rexam | - | Craig Childers | Becky Brakke | Javier Gallo | Ken Lee | Gerri Gobbi | - | Jim Keller | Nina Nguyen | FZ | 90% |  | 100% | DB | 0%
| Chase | Scott Vonderheide | Mike Harris | Cindy Stephens | Dag Joraholmen | Ken Lee | Roger Persson | - | Mike Smith | - | FZ | 90% |  | 60% | DB | 0%
| Molded Fiber Glass | Catherine Simoes | Charlene Jackson | Terry Lacy | Peter Johnston | Mike Kim | Gerri Gobbi | Rajesh Dhir | - | David Saindon | FZ | 90% |  | 45% | DB | 0%
| Owens Illinois | Saji John | Maureen Palmer | Lisa Polk | Tony Valenzuela | Dickson Koo | Gerri Gobbi | - | Jim Keller | David Saindon | FZ | 90% |  | 45% | DB | 0%
| Quebecor | Oliver Jones | Maureen Palmer | Whitney Fox | Bob Clifford | Ken Lee | Gerri Gobbi | Chad Corbit | Michelle Maynard | David Saindon | FZ | 90% |  | 75% | DB | 0%
| Simon Property Group (EMA/OA) | Terry Donovan | Mike Harris | Ben Smith | J Paul Oxer | Mike Kim | Gerri Gobbi | Chad Corbit | Michelle Maynard | John Mackel | FZ | 80% |  | 25% | DB | 0%
| Springs Industries | Andy Chen | Charlene Jackson | Debra Blake | Kristin Griffin | Ken Lee | Roger Persson | Pedro Man | Bill Rapp | Nina Nguyen | FZ | 80% |  | 95% | DB | 0%
| Starwood | Saji John | Mike Harris | Kevin Boudreaux | Kevin Covack | Dickson Koo | Roger Persson | Rajesh Dhir | - | Nina Nguyen | FZ | 80% |  | 100% | DB | 0%
| Suiza Foods | Terry Donovan | Richard Zdunkewicz | Kevin Boudreaux | C Allured | Joe Capasso | Gerri Gobbi | Andre Gibson | Michelle Maynard | Nina Nguyen | FZ | 90% |  | 100% | DB | 0%
| Tyco | Terry Donovan | Craig Childers | Florence Zoes | Scott Layne | Ken Lee | Gerri Gobbi | Pedro Man | Debbie Asmus | Nina Nguyen | FZ | 90% |  | 85% | DB | 0%
| ArchDiocese of Chicago | Saji John | - | Rob Smith | Tim Novacyk | Mike Kim | - | Andre Gibson | Mike Smith | Nina Nguyen | FZ | 90% |  | 0% | DB | 0%
| BICCGeneral/General Cable | Saji John | Charlene Jackson | Rhonda Short | Steve Swerdloff | Mike Kim | - | Franco Cuminato | - | - |  | 90% |  | 0% |  | 0%
| Eli Lilly | Edith Cross | Craig Childers | Whitney Fox | Peter D'Lassandro | Dickson Koo | Steve Nguyen | Tarek Dou-Saada | Jim Keller | David Saindon | SW | 90% |  | 25% | DB | 0%
| GGP | Oliver Jones | Mike Harris | Becky Brakke | Victor Chael | Dickson Koo | Jeff Cobb | - | - | - | FZ | 80% |  | 0% | DB | 0%
| IBM | Todd Perry | Richard Zdunkewicz | Ben Smith | Jeff Nieland | Ken Lee | Steve Nguyen | - | Mike Smith | Nina Nguyen | FZ | 90% |  | 5% | DB | 0%
| Infomart | Scott Vonderheide | - | Nikita Harris | Peter Johnston | Mike Kim | - | Franco Cuminato | - | Nina Nguyen | FZ | 90% |  | 0% | DB | 0%
| JC Penney | Catherine Simoes | Mike Harris | Chris Copass | Bill Douglass | Mike Kim | Humberto Cubillos | Andre Gibson | - | Nina Nguyen | FZ | 90% |  | 0% | DB | 0%
| Kaiser Healthcare | Scott Vonderheide | George Waidelich | - | - | Ken Lee | - | - | - | - | FZ | 90% |  | 0% | DB | 0%
| Lucent | Oliver Jones | Tony Barnhart | - | Michael O Brown | Ken Lee | Matt Guin | - | - | - |  | 80% |  | 0% |  | 0%
| Macerich | Catherine Simoes | Mike Harris | Brent Edwards | - | Dickson Koo | Catherine Simoes | Chad Corbit | - | David Saindon |  | 90% |  | 0% | DB | 0%
| Ocean Spray Cranberries, Inc. | Terry Donovan | Richard Zdunkewicz | Nikita Harris | Chris Wheeler | Mike Kim | - | Franco Cuminato | - | - |  | 90% |  | 0% | DB | 0%
| Owens (includes Canada) | Catherine Simoes | Maureen Palmer | Lisa Polk | B Kortes | Ken Lee | - | Rajesh Dhir | Jim Keller | David Saindon | FZ | 90% |  | 10% | DB | 0%
| Packaged Ice | Scott Vonderheide | - | Ben Smith | Michell Faust | Mike Kim | - | Tim Sundel | Rich Freed | Nina Nguyen | FZ | 90% |  | 50% | DB | 0%
| Pilkington (includes Rossford, OH) | Oliver Jones | Maureen Palmer | Lisa Polk | Barbara Kortes | Dickson Koo | Steve Nguyen | Andre Gibson | Ed Essandoh | Nina Nguyen | FZ | 90% |  | 0% | DB | 0%
| Polaroid | Saji John | Richard Zdunkewicz | Debra Blake | Chris Wheeler | Mike Kim | - | Rajesh Dhir | Marianne Castano | Nina Nguyen | FZ | 90% |  | 0% | DB | 0%
| Prudential | Oliver Jones | Tom Prisk | Nikita Harris | - | Dickson Koo | Jeff Cobb | - | - | David Saindon | FZ | 70% |  | 0% | DB | 0%
| Quaker | Saji John | Charlene Jackson | Rob Krotee | John Tickell | Jerald Surface | Steve Nguyen | Rajesh Dhir | - | Nina Nguyen | FZ | 90% |  | 0% | DB | 0%
| Rich Product | Scott Vonderheide | Richard Zdunkewicz | Richard Hannum | John Nanof | Jerald Surface | Jodi Thrasher | - | - | David Saindon | FZ | 90% |  | 0% | DB | 0%
| Ridge Tool | Scott Vonderheide | - | Nikita Harris | Steve Beck | Mike Kim | Nat MacAdams | Andre Gibson | - | - | FZ | 90% |  | 0% | DB | 0%
| Rite Aid | Catherine Simoes | Lamar Frazier | - | - | - | - | - | - | - | FZ | 50% |  | 0% | DB | 0%
| Saks | Terry Donovan | Mike Harris | Whitney Fox | Bryan Gee | Mike Kim | Jeff Cobb | - | - | David Saindon | FZ | 90% |  | 0% | DB | 0%
| Sonoco | Terry Donovan | - | Debra Blake | Bryan Gee | Dickson Koo | Chris Riley | - | - | David Saindon | FZ | 90% |  | 0% | DB | 0%
| UC/CSU | Catherine Simoes | Lamar Frazier | - | Tom Riley | Joe Capasso | - | Chad Corbit | Andy Wu | - | FZ | 40% |  | 0% | DB | 0%
[11 empty] | % COMPLETE (simple avg) | 84.35% |  | 3.913% |  | 0%
10.5435
1 | Air Products and Chemicals, Inc. | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
2 | Albertson's | 0 |  | 0 | 0 | 0 | Matt Guin | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
3 | American Electric Commodity | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
4 | American Stores | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
5 | Applied Material | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
6 | Aquila Energy | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 0% |  | 0% | DB | 0%
7 | Atlantic Health | 0 |  | 0 | 0 | 0 | Matt Guin | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
8 | Beth Israel | 0 |  | 0 | 0 | 0 | Jeanette Reese | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
9 | Blue Diamond Materials Div. / Sully Miller Contr. | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
10 | Bridgestone Firestone | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
11 | Burger King | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
12 | Catholic Health East | 0 |  | 0 | 0 | 0 | Jeanette Reese | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
13 | CCL | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 30% |  | 0% | DB | 0%
14 | Checker | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
15 | Cisco | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
16 | Columbia Gas Transmission | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
17 | Compaq | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
18 | Connect Energy Services, Inc. | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 0% |  | 0% | DB | 0%
19 | Crossroads | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
20 | Darden Restaurants | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 30% |  | 0% | DB | 0%
21 | DESC - Nellis | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
22 | Developer's Funding Co. | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 0% |  | 0% | DB | 0%
23 | Dominion Transmission | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
24 | Duke Energy Trading & Marketing, LLC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
25 | Durst | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
26 | Dynegy | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 0% |  | 0% | DB | 0%
27 | Enron Compression Services | 0 |  | 0 | 0 | 0 | Jeanette Reese | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
28 | Enserch Energy | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
29 | Equity Office | 0 |  | 0 | 0 | 0 | Martinez | 0 | 0 | 0 | SW | 30% |  | 0% | DB | 0%
30 | Family Restaurants | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
31 | Fidelity | 0 |  | 0 | 0 | 0 | Gisselle Rohmer | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
32 | Gen Probe | 0 |  | 0 | 0 | 0 | Gisselle Rohmer | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
33 | Genentech Inc | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 30% |  | 0% | DB | 0%
34 | Glen-Gery Corporation | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 0% |  | 0% | DB | 0%
35 | Graniterock Company | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
36 | GSA | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
37 | Homestake Mining | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
38 | Hyatt | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
39 | Illinois State | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
40 | International Paper | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 30% |  | 0% | DB | 0%
41 | Irvine | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
42 | Kellogg - Pace Energy | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
43 | Lam Research | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 30% |  | 0% | DB | 0%
44 | Marathon | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
45 | McDonalds | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
46 | MRT Transport #434 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 0% |  | 0% | DB | 0%
47 | New Commodity Company | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
48 | Northrop Grumman | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
49 | Novellus | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
50 | Nummi | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 30% |  | 0% | DB | 0%
51 | OCM Boces | 0 |  | 0 | 0 | 0 | Jeanette Reese | 0 | 0 | 0 | SW | 40% |  | 0% | DB | 0%
52 | Ohio MSG | 0 |  | 0 | 0 | 0 | JD Burrows | 0 | 0 | 0 | SW | 30% |  | 0% | DB | 0%
53 | Optical Lab | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
54 | PanCanadian | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 0% |  | 0% | DB | 0%
55 | Promus Hotel | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 30% |  | 0% | DB | 0%
56 | Raychem | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 40% |  | 0% | DB | 0%
57 | Riverside County | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
58 | Robert Wood Johnson | 0 |  | 0 | 0 | 0 | Jeanette Reese | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
59 | S. B. Linden | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 0% |  | 0% | DB | 0%
60 | Safeway | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 30% |  | 0% | DB | 0%
61 | Seagate | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
62 | Shaw Supermarket | 0 |  | 0 | 0 | 0 | Gisselle Rohmer | 0 | 0 | 0 | SW | 40% |  | 0% | DB | 0%
63 | Silicon Graphics | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 30% |  | 0% | DB | 0%
64 | Solo Cup | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
65 | Southern Management | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
66 | Southland | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
67 | Sutter Healthcare | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 30% |  | 0% | DB | 0%
68 | Target | 0 |  | 0 | 0 | 0 | Tom Baldwin | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
69 | Techneglas | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 0% |  | 0% | DB | 0%
70 | Telecordia | 0 |  | 0 | 0 | 0 | Tom Baldwin | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
71 | Temple Steel | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
72 | Tenneco | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
73 | Texaco Natural Gas | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 0% |  | 0% | DB | 0%
74 | TransCanada Energy Marketing USA | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 20% |  | 0% | DB | 0%
75 | Transcontinental Gas Pipe Line Corp. | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 0% |  | 0% | DB | 0%
76 | U of Chicago | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SW | 10% |  | 0% | DB | 0%
77 | Verizon | 0 |  | 0 | 0 | 0 | Matt Guin | 0 | 0 | 0 | SW | 30% |  | 0% | DB | 0%
0 | subtotal of other | [8 empty] | 0 |  | 1310% |  | 63.91% |  | 0%
[8 empty] | PERCENT COMPLETE (simple avg) |  |  |  | 17.01% |  | 0.83% |  | 0%
[8 empty] | TOTAL PROJECT COMPLETENESS |  |  |  | 22.22%
| FZ | Florence Zoes - Lead
| SW | Steve Watson - Lead
| DB | Don Black