## Sheet1
Transwestern Project Sun Devil
ENSR Cost Estimate for Environmental Support
Project Manager: Scott Patti
|  | Phase I | Phase II
|  | thru 3/2002 | thru 12/2002
TASKS |  | SUBTOTAL | SUBTOTAL
1 | Data Collection and Review | 30000
2 | Agency Consultation | 30000 | 10000
3 | Route Selection | 30000
4 | Wildlife Habitat/Land Use Field Surveys | 30000
5 | T&E Species Surveys |  | 160000
6 | Wetland Delineation and Report | 120000
7 | Cultural Resources Survey and Report | 400000 | 100000
8 | Cultural Resources Testing/Mitigation |  | 300000
9 | FERC Resource Reports | 100000
10 | Response to FERC Data Requests |  | 20000
11 | Biological Assessment | 30000
12 | Map/Alignment Sheet Review | 15000
13 | Section 404 Permits |  | 25000
14 | Air Quality Permits | 20000 | 20000
15 | Water Withdrawal/Discharge Permits |  | 25000
16 | Agency/Public Meetings | 30000 | 20000
17 | Coordination Meetings | 30000 | 30000
18 | Project Management | 75000 | 75000
19 | GIS Web Page Set Up & Maintenance | 20000 | 30000
| ENSR PROJECT TOTAL | 930000 | 815000
Third-Party Contractor |  | 150000 | 350000
|  | Phase I | Phase II
| PROJECT GRAND TOTAL | 1080000 | 1165000