## Summary
Work Order | Budget | YTD Actuals thru Nov* | Projected for Dec** | Balance | 2000 Accruals | Comments
c.006216/c.006243 Marketing Dashboard - Phase I | 263433 | 262638 | 0 | 795 | 0 | 1) PPA for 4,177.40 to c.00000753 for Bobby Mason consulting. 2) Submit Project Completion Form
c.006227/c.006253 Capacity Books | 672000 | 694411 | 44603 | -67014 | 0 | 1) PMF for 72,600 which includes Nov/Dec IT labor, and outside consulting on optimization. 2) PPA for 30,803 to ???? For Sean Bolks/Sheryl Kimes consulting 3) Submit Project Completion Form
c.006215/c.006242 Pipeline Profile Proof-of-Concept | 669161 | 620225 | 47000 | 1936 | 45000 | 1) PPA for 93,450.00 to c.006216 for Prominex Consulting 2) PPA for 26,444 to c.000850 for all Nov labor cost 3) Accrue 45,000 for ESRI software purchased in Dec. 4) Submit Project Completion Form
c.006211 CMS/CAS Enhancements | 80250 | 0 | 0 | 80250 | 0
c.006240 CBS Enhancements | 22062 | 0 | 0 | 22062 | 0
c.00???? TW CAS | 200000 | 0 | 0 | 200000 | 0
c.000753/c.000752 Marketing Dashboard - Phase II | 402590 | 27570 | 320000 | 55020 | 65000 | 1) Accrue for Luminant Consulting fees for Dec estimated at 65,000.
c.000852/c.000850 Pipeline Profile - Phase I | 228275 | 3814 | 147000 | 77461
c.000851/c.000848 Risk Management System | 650000 | 0 | 506000 | 144000 | 506000 | 1) Accrue for Caminus consulting fees for Dec estimated at 10,000. 2) Accrue for Caminus software 496,000
c.000???/c.000??? SAS Project | 70000 | 0 | 0 | 70000 | 0 | Check with Jane Porter.
c.000979 Science W.O. | 569500 | 0 | 176000 | 393500 | 0 | 1) Accrue for Sheryl Kimes consulting fees of 12,000.
Totals | 3827271 | 1608658 | 1240603 | 978010 | 616000
* PPA adjustments have been subtracted from actuals
** Includes accruals
Note on D3: ETS IT Labor for Dec $28,000 Hyperion/McAnalyst Consulting $16,603 Total $44,603
Note on D4: ESRI Software $42,000 Direct Connect Software $5,000 Total $47,000
Note on D8: Luminant Consulting $265,000 ETS IT $25,000 Hardware $30,000 Total $320,000
Note on D9: GeoDynamics Consulting $42,000 ETS IT $40,000 Harware/Software $65,000 Total $147,000