## Sheet1
|  |  | Approved | Work Orders | Work Orders | Work Orders | Work Orders |  | Work Orders
System Name | Account Number | System Number | Capital Cost | Capital Cost | Capital Cost | Capital Cost | Accrual for Materials |  | Estimate at
|  |  | RAROC | Approved | Thru June 30th | 6-30 to 8-31 | not yet invoiced |  | Completion
House Creek | 11025 | 100 | 11944234 | 5151501 | 2930353 | 3200 | 5000 | 2938553 | 11944234
Caballo Lateral | 11026 | 200 | See Note 2 | 2511400 | 2703658 | 65000 | 10000 | 2778658 | 2800000
Caballo Compression | 11026 | 200 | 8062497 | 5740000 | 6498109 | 933000 | 40000 | 7471109 | 7750000
Clydesdale | 11027 |  | 3254256 | 3370675 | 933169 | 909000 | 750000 | 2592169 | 3254256
South Kitty | 11028 |  | 7462998 | 9413156 | 1500547 | 1441000 | 1500000 | 4441547 | 7462998
Hoe Creek | 11029 |  | 6735882 | 4661220 | 654157 | 131000 | 350000 | 1135157 | 6735882
Box Draw | 11030 | 400 | 6707026 | 7053775 | 7402549 | 218000 | 10000 | 7630549 | 7900000
Maverick | 11030 | 300 | 1650000 | See Note 1 | See Note 1 | See Note 1 | See Note 1 | 0 | See Note 1
Kudzu |  |  | 4729128 | 0 | 0 | 0 | 0 | 0 | 4729128
Fort Union Receipt Points |  |  | 676713 | 1194000 | 1104406 | 129000 | 10000 | 1243406 | 1300000
|  | Grand Total = | 51222734 | 39095727 | 23726948 | 3829200 | 2675000 | 30231148 | 53876498
Note 1: All of Maverick's Capital cost is included in the Box Draw work order.
Note 2: This cost was included in the Caballo Compression RAROC number.