## Sheet1
|  |  | Approved | Work Orders | Work Orders | Work Orders | Work Orders Estimated |  | Work Orders
System Name | Account Number | System Number | Capital Cost | Capital Cost | Capital Cost | Capital Cost | Accrual for Mat.&Labor |  | Estimate at
|  |  | RAROC | Approved | Thru June 30th | 6-30 to 9-11 | Thru 9-15 |  | Completion
House Creek | 11025 | 100 | 11944234 | 5151501 | 2930353 | 3800.93 | 5000 | 2939153.93 | 11944234
Caballo Lateral | 11026 | 200 | See Note 2 | 2511400 | 2703658 | 59226.71 | 10000 | 2772884.71 | 2800000
Caballo Compression | 11026 | 200 | 8062497 | 5740000 | 6498109 | 855571.69 | 83000 | 7436680.69 | 7900000
Clydesdale | 11027 |  | 3254256 | 3370675 | 933169 | 938918.85 | 750000 | 2622087.85 | 3254256
South Kitty | 11028 |  | 7462998 | 9413156 | 1500547 | 1728058.11 | 1500000 | 4728605.11 | 7462998
Hoe Creek | 11029 |  | 6735882 | 4661220 | 654157 | 133999.61 | 350000 | 1138156.61 | 6735882
Box Draw | 11030 | 400 | 6707026 | 7053775 | 7402549 | 207606.48 | 90000 | 7700155.48 | 7900000
Maverick | 11030 | 300 | 1650000 | See Note 1 | See Note 1 | See Note 1 | See Note 1 | 0 | See Note 1
Kudzu |  |  | 4729128 | 0 | 0 | 0 | 0 | 0 | 7153363
Fort Union Receipt Points |  |  | 676713 | 1194000 | 1104406 | 130511.65 | 12000 | 1246917.65 | 1325000
|  | Grand Total = | 51222734 | 39095727 | 23726948 | 4057694.03 | 2800000 | 30584642.03 | 56475733
Note 1: All of Maverick's Capital cost is included in the Box Draw work order.
Note 2: This cost was included in the Caballo Compression RAROC number.
The Following Contractors are currently providing services for the listed Work Orders.
1.La-Tex Associates under a Master Construction Agreement ("MCA") dated June 15, 1996 between La-Tex and Gulf Coast Operations, and billing in accordance with Affiliate Work Offer dated July 31, 2000
and the attached rate schedule.
2.ForeRunner Corporation under a MCA dated effective September 1, 1999 between ForeRunner and Enron Midstream Services, L.L.C. ("EMS"), billing in accordance with the applicable rate schedule
3.Flint Engineering & Construction Co. under MCA dated February 1, 1996 between Flint and Transwestern Pipeline Company, bulling pursuant to Affiliate Work Offer dated July 28, 2000
with a lump sum of $93,772.00.
4. Watkins Construction CO., Inc. under MCA dated December 15, 1999 between Watkins and EMS, billing under unit price schedule attached to Work Offer dated July 19, 2000.
5. Gas Gathering Specialist, Inc. under MCA dated January 1, 1995 between Gas Gathering and Florida Gas Transmission, et al, billing in accordance with Affiliate Work Offer dated June 29, 2000
and priced in accordance with the rate schedule.
6. Pacific Industrial Electric, Inc. under MCA dated April 15, 2000 between Pacific Industrial and EMS, billing in accordance to the rate schedule.
7. Okemah Construction, Inc. under MCA dated October 18, 1999 between Okemah and Northern Natural Gas Company, billing in accordance with the Affiliate Work offer dated July 10, 2000
for a lump sum of $535,774.50.
8. Ken Small Construction of Wyoming, Inc. contract and work offer in process and work to begin September 25, 2000.