## Sheet1
Project Status Report
Technical Support | Project/Description | Originator | Key Staff | T.L./Type/Budget/Spent | Last Updated | Status/Comments
Austin, Terri | Georgia Peakers: Sites at Hartwell and Athens under Review | East Orig: | EE&CC: Mike Nanny |  | 2001-02-26 | Air permit in progress, E&S plan in progress
Austin, Terri | Fuel Cells | East Orig: | EE&CC:Mike Nanny | Budget :$60k, Spent $45K | 2001-02-26 | Waiting on final PO with FCE
Austin, Terri | Cogentrix Coal Plants (ALAMAC) - Performance Test Protocol | East Orig: Ozzie Pagan/ Dwight Beach | Dwight Beach Dan Williams | No Budget | 2001-02-26 | D.Williams sent Rich Kottke to plants to find a way to parrallel BFPs
Austin, Terri | Cleburne Review | East Orig: John Moore |  | No Budget | 2001-02-26
Booth, Eric | GE 7FA Combined Cycle for Longview, Washington | West Orig: Jake Thomas Bill Williams |  |  | 2001-06-13
Booth, Eric | Austin Power: 4 x LM6000 Simple Cycle Power Project | East Orig: Jim Ducote |  |  | 2001-06-13 | Project in Commercial Operation
Chmielewski, Bob | LVC II | Ed Clark, Bil Williams | EEAS:Ed Dannhaus |  | 2001-06-14 | Working with DHEC on design issues, Working with Modern Continental on EPC issues. Ongoing project development. Site meeting planned for 6/20/01
Chmielewski, Bob | AMPS: Mobile Power Generation Systems | Bob Virgo | EE&CC: G. Zelondgev |  | 2001-06-14 | Answering marketing questions.
Coleman, Mike | Fort Pierce, Fla.: Repowering of existing Steam Plant. 1 X M501F + HRSG | East Orig: Dave Fairley | EEOS: Darrell Stovall | TL's approved up to $1,700,000 - waiting management approval of additional funds | 2001-04-30 | Team working last revision on FPUA agreements. Engineering on hold waiting on DASH. Looking for final negotiation.
Golden, Bruce | Coal Initiative, Southeast USA, Texas and West USA | Mitch Robinson | EEOS: No one assigned | TL approved up to $85,000 | 2001-06-15 | Seminole Tribe - clean draft LOI in Council hands - planned presentation meeting possible 6/19 - completed initial site visit - tech visit in two weeks - investigating possible coal supply opportunities to get cost below $1.25/MMBtu Seminole Electric Cooperative -re-revised draft LOI sent next week - site visit planned for week of 6/25 conceptual layout in preparation (received SECI site and underground drawings) Ormet - further review of local culm piles, analizing raw or clean waste coal TNP One - attended bidders meeting TMPA - preparing possible layout (waiting EEOS resources) and review common facilities Talahassee - project conceptual meeting on 6/21 Orlando Utility Commission - possible expansion at the Stanton Energy Center Florida Crystal - two sites for repowering or possible coal conversion/expansion Ft Mohave Tribe - contact regards possible site
Hammond, Don | Coburg - 2x1 7FA project development | Jeff Shields | Bill Williams Mark Mullen |  | 2001-07-02 | Continuing to investigate alternatives to reduce the cost of gas transport to the site.
Hammond, Don | AMPS: Mobile Power Generation Systems | West Orig: Jim Buerkle Chris Lackey | Mark Mullen |  | 2001-07-02 | Reduced power prices have led to discontinuance of siting efforts.
Kraszewski, Bob | Florida Greenfield Projects: Including Pompano Beach, Deerfield Beach, Midway, South Dade (Certosa), Medley & Corbett | East Orig.: Steve Krimsky Greg Krause | EE&CC: David McDeed Bob Greene Mario Brunasso |  | 2001-07-02 | Preparing FPL submittals, SwYd layouts and One Line Diagrams. Interface with FPL on SwYd design.
Kraszewski, Bob | TexMex, Texas: Installation of AC/DC tie, power export to Mexico | East Orig: Ozzie Pagan | EE&CC: Scot Laidlaw |  | 2001-07-02 | Interface with Bpub and ABB Engineering
Kraszewski, Bob | Mexico Projects - Copamex Fersinsa, FAPSA, Arancia Corn Products, Willamette de Mexico, CIPSA | East Orig: Matt Duffy | EE&CC: Dan Christie OEC: Scot Chambers EA: Dan E. Williams |  | 2001-07-02 | Project proposal input.
Mays, Wayne | EEStor | Phillip Durst |  |  | 2001-06-14 | Investigate new business which is attempting to develop a capacitor energy storage device for use in electric vehicles.
Mullen, Mark | PSCo, Colorado: 6 x LM6000 Simple Cycle Peaker | West Orig.: Jake Thomas Steve Thome | Don Hammond EE&CC: Ed Dannhaus |  | 2001-05-24 | Sale complete. Technical support activities concluded.
Rimbau, Robert | Vitro: 1 x 1 Combine Cycle Cogen in Monterrey, Mexico | EdM: Steve Irvin Marc Sabine | EE&CC: Manuel Cavazos Gari Ramirez Duncan McCaig Bob Moss | Auth $2.5 MM for OE to be revised on 12/30/01 | 2001-06-18 | Const Mob 03/26/01 Sell Down in progress Contractor's Change Request Under Discussion Appling for cogeneration customs exemption
Rimbau, Robert Elam, Ed | Fapsa: 12 MW Cogen, Mexicali | EdM: Matt Duffey |  |  | 2001-03-26 | Provided EPC quote, waiting on PPA, preparing the dash for management approval
Rose, Steve | Florida Greenfield Projects: Including Pompano Beach, Deerfield Beach, Midway, South Dade (Certosa), Medley & Corbett | East Orig.: Steve Krimsky Greg Krause | EE&CC: Bob Greene Mario Brunasso | Auth: $690,000 Spent: $736,026.04 thru 1/31/01 | 2001-05-24 | Midway: Rezoning approved by 3-2 vote in Commission Hearing of 3 April. Air permit in hand. ERP & WUP expected by mid-July. Midway now being developed as an '02 play. Negotiations under way with potential partner who is bringing 2 x 7FA to the deal. Preparing to option long lead electrical equipment. Working on locking in FPL outage schedule & FGT gas interconnect. Pompano Beach: P&Z hearing #3 scheduled for 12 June. Local opposition is very vocal and very visible. Deerfield Beach: Ad Hoc Energy Advisory Committee report issued this week - favorable to project. Public hearing tentatively set for 8 June. South Dade (Certosa): Biscayne National Park Buffer Review Committee meeting held 14 May - vote was 4-3 to recommend denial of project. CZAB hearing tentatively scheduled for 6 June. Corbett: Preliminary drawing package issued. Air permit application prepared & filed.
Virgo, Bob | Doyle Ins. Claim |  |  |  | 2001-01-08
Williams, Dan | Mexico Projects - Copamex Fersinsa, FAPSA, Arancia Corn Products, Willamette de Mexico, CIPSA | East Orig: Matt Duffy | EEOS: Dan Christie OEC: Dirk Johnson EA: Bob Kraszewski | Level-of-effort Tasking Letter/$78,300 Spent $13,570 | 2001-06-29 | Presentation to Copamex last week, Arancia configuration & CAPEX updated last week.Developing alt. Hitachi for FAPSA
Williams, Dan | Stoneybrook University of New York | East Orig: David Marks, ENA: Bill Keeney, Victor Munoz, Greg Martin |  | No Budget/Spent $0 | 2001-06-29 | Developing performance estimates to add a STG, evap cooler or chiller to existing LM6000, possible second unit.
Williams, Dan | ProjectBattleship - Brooklyn Navy Yard | East Orig: David Marks, Bill Keeney for ENA Transaction Structuring | EEOS: Karl Masani & Dirk Johnson, EA: Wayne Mays | Budget :$17,000 Spent:$8,358 | 2001-06-29 | Due Diligence report was submitted on 6-20-01. Updated performance model with inlet chillers.
Williams, Dan | Baja Coal Project, La Jovita Rosarita,Baja California | East Orig: Matt Duffy, Naveed Ahmed, also Jaime Alatorre in Mexico | EA: Bob Kraszewski, OEC: Dirk Johnson | No Budget/Spent $0 | 2001-06-29 | Site surveys on 4/3/01 completed at Rosarito and La Jovita, Bruce Golden is developing
Williams, Dan | York CoGen Facility, York, Pennsylvania | EES Orig: Mark Bernstein & Scott Laidlaw | EEOS: David Kwok, Don Stevens, Ron C. Smith, Kelly Merritt | Budget $17,000 Spent:$3,214 | 2001-06-29 | Plant visits on 5/11 & 6/7 Due diligence report was submitted on 6-18-01.
Williams, Dan | Keenansville, N.C., 35 Mw Stoker Coal Plant | East Orig: Heather Kroll | EES: Don Stevens, John Cates, Jerry Campbell | No Budget/Spent $0 | 2001-06-29 | Due diligence trip after July 4th to be scheduled.
Williams, Dan | Project Goliath - Ontario Power Generation, Lakeview & Lennox Stations | Enron Canada Orig: Jan Wilson, Trader is Garrett Tripp | ENA: Jim Meyn, Terri Austin EEOS: Rod Griscom | No Budget/Spent $0 | 2001-06-29 | Provided perf & CAPEX data to Canada Desk for repowering one Lakeview unit in combined-cycle.
Williams, Dan | Sithe Independence Power, Oswego,New York | East Orig: Charles Ward | EEOS: Karl Masani, Lebouf & Lamb: Jim Thompson | No Budget-Done Spent:$3,865 | 2001-06-29 | Plant visit on 5-30-01, Issued trip report. Provided O&M Budget. DASH approved last week.
Williams, Bill | Columbia (Port of Longview) | Laura Wente | Hammond, Mullen, |  | 2001-06-14 | Modern Continental South has agreed to be EPC for a full project wrap on LED. They will manage 4 sub contracts under the wrap. Scott Co., RCI, will be mechanical and civil respectively. Amec-Simons will be design engineer. Electrical is YTBD. Draw down schedule is being prepared. LNTP expected July 1 with FNTP sometime in October if not sooner. Water becoming an issue. Major equipment identified. E-next will be needed.
Williams, Bill | Las Vegas Cogeneration II (Priscilla) | Jim Gilbert | Hammond, Mullen,Chmielewski, Ed Dannhaus, Randy Campbell | Contact Jody Blackburn for Details. | 2001-06-14 | Working Sale Process, near completion. Noise mitigation still needs discussion. Sound walls and Transmission hardware concerns need to be run to ground.
ProjStatRep
Project Status Report
Technical Support | Project/Description | Originator | Key Staff | T.L./Type/Budget/Spent | Last Updated | Status/Comments
Mario Brunasso | Florida Greenfield Projects: Including Pompano Beach, Deerfield Beach, & Corbett | Krimsky |  | Tasking Letter under general ENA Support. | 2001-06-22 | Continuing to support permitting and rezoning efforts for Deerfield Beach & Corbett Energy Centers. Found that Gulfstream Pipeline from Alabama to Florida is moving into construction phase. This may mean distillate backup needs will deminish.
Mario Brunasso | COGENTRIX , Keenansville |  |  | Tasking Letter To Be Developed if deal goes forward. | 6/22/01 NO CHANGE | On 5-21-01 Tony Halcombe of COGENTRIX advised he is still not able to conduct site Due Dilignece visit as CP&L still has right of 1st refusal.
Ed Dannhaus |  |  |  |  | 6/13/01 (See weekly reports for a more detailed update.) | Project kick-off meeting was conducted with MCS on 6 June whereby ENA outline their expectations of MCS. MCS has reached contract agreements with Dleta Hudson, Lauren Engineering, and Lauren Constructors, Copies have been forwarded to Portland and the site. Contractor continues to obtain building permit which should come no later than next week. The first monthly review meeting will be on site on 20 June and the weekly meeting on the status of Engineering will be in Abeline on 26 June. Contractor continues to expedite ENA for Glegg drawings.
John Garrison
Bob Greene | Florida Greenfield Projects: primarily Midway & South Dade, but including Pompano Beach, Deerfield Beach, & Corbett | Greg Krause Steve Krimsky |  | Tasking Letter under general ENA Support. | 2001-06-22 | Continuing to support permitting and rezoning efforts for Midway & South Dade.
Mike Nanny | Fort Pierce Repowering Project | Dave Fairley | Darrell Stovall - PM Ray McPhail - Pem | Tasking Letter under general ENA Support. | 2001-07-02 | Reviewing contracts and responding to Due Deligence Inquiries of potential project partners. We have strarted daily contract status meetings and working to resolve the testing and related tolling issues.
Technical Support | Travel Schedule | Dates | Hotel | Contact Numbers |  | Comments
Austin, Terri | Houston Holiday | July 2,3,5,6 July 4 |  | (cell) 281-455-5900
Booth, Eric | Houston Holiday Austin | July 2,3,5 July 4 July 6 |  | (cell) 713-412-6873 |  | Can reach on cell
Brunasso, Mario | Sudbury, Mass. |  |  | 978-579-7999, (cel)l 713-206-4835
Chmielewski, Bob | Houston Holiday | July 2,3,5,6 July 4 |  | (cell) 713-569-4105 |  | Can reach on cell
Christie, Dan | Houston Holiday | July 2,3,5,6 July 4
Coffer, Walter | Houston Holiday | July 2,3,5,6 July 4 |  | (cell) 713-594-9014 |  | Can reach on cell
Coleman, Mike | Houston Holiday | July 2,3,5,6 July 4 |  | (cell) 713-557-4529
Dannhaus, Ed |  |  |  | (cell) 713-503-8720 |  | The initial project review meeting was conducted with Modern Contiental on 20 June 01 with moderate success. Minor demolition was started and Modern Contiental is beginning to get control of the project. Progress is being made in the area of construction permits.A number of issues regarding change orders are outstanding and a technical solition to the sound level has not been fuly resolved. Next meeting on the 26 of June in Abilene
Golden, Bruce | Houston Holiday | July 2,3,5,6 July 4 |  | (cell) 281-797-4924 |  | Can reach on cell
Garrison, John | Houston Holiday | July 2,3,5,6 July 4
Greene, Bob | Houston Holiday | July 2,3,5,6 July 4 |  | (cell) 713-503-7556 |  | Can reach on cell
Hammond, Don | Portland |  |  | (cell) 503-703-4600 |  | Can reach on cell
Kraszewski, Bob | Houston Holiday | July 2,3,5,6 July 4 |  | (cell) 713-444-5863 |  | Can reach on cell
Mays, Wayne | Portland |  |  | (cell) 503-701-3154 |  | Can reach on cell
Nanny, Michael | Houston - EEOS |  |  | (Office) 281-368-4805 or 4804 |  | Expecting to stay in Houston.
Rimbau, Robert | Houston Holiday | July 2,3,5,6 July 4 |  | (cell) 713-560-4807 (Int. cell) 011-528-170- 7111 |  | Can reach on cell
Rose, Steve | Houston Holiday | July 2,3,5,6 July 4 |  | (cell) 713-854-4971 |  | Can reach on cell
Williams, Bill |  |  |  | (cell) 503-704-9801 Plant- 702-642-0331
Williams, Dan | Houston Holiday | July 2,3,5,6 July 4 |  | (cell) 713-906-3821 |  | Can reach on cell