## 130 MW
Pueblo 140 MW CC
EPC Price
(Million $)
Item |  |  |  | Total | %
GE LM-6000 Sprint Gas Turb. Gen. | 3 | @ | 14.8 | 44.4
Chiller / Evaporative Cooler | 0 | @ | 0 | 0 |  | none
Steam Turbine Generator | 1 | @ | 5.5 | 5.5 |  | 44 MW
Heat Recovery Steam Generator | 3 | @ | 3.5 | 10.5
Power Island |  |  |  | 60.4 | 55.597
Mechanical BOP
Condensers |  |  |  | 0.6 | 0.55229
Pumps |  |  |  | 0.9 | 0.82843
Cooling Tower |  |  |  | 0.8 | 0.73638
Water Treatment |  |  |  | 0.5 | 0.46024
SCR |  |  |  | 0 | 0 | assume not required
Gas Compressor |  |  |  | 0 | 0 | assume not required
Auxiliary Boiler |  |  |  | 0 | 0
Miscellaneous |  |  |  | 0.7 | 0.64434
Instrumentation & Controls |  |  |  | 0.8 | 0.73638
Electrical BOP |  |  |  | 2.1 | 1.933
Switchyard |  |  |  | 3.5 | 3.2217 | $2mm substation allowance
Storage Tanks |  |  |  | 0.5 | 0.46024
Total Equipment |  |  |  | 70.8 | 65.17
Turnkey Equipment Margin |  |  | 5 | 3.54 | 3.2585
Buildings |  |  |  | 0.4 | 0.36819
Engineering |  |  |  | 3 | 2.7614
Project Management |  |  |  | 6 | 5.5229
Start-up |  |  |  | 2 | 1.841
Installation
Direct |  |  |  | 14.864 | 13.682
Indirect |  |  |  | 3.8646 | 3.5573
Construction Profit |  |  | 14 | 2.081 | 1.9155
Subtotal Installation |  |  |  | 20.8096 | 19.1548
Contingency |  |  | 2 | 2.0894 | 1.9232
Contractor's Price |  |  |  | 108.639 | 100
MW Output |  |  |  | 143.7
$ per KW |  |  |  | 756.0123