## Summary with Project Scope
ENA TECHNICAL SERVICES
|  |  |  | 10% | Estimate
PROJECT COST ESTIMATE
2025-09-26
| CUSTOMER COMPANY NAME: | Enron North America (Houston Pipe Line Co.)
| PROJECT NAME: | Temporary Meter & Reg. Sta. for Midcon's Carbon Black
W.O. NUMBER:
| PROJECT ENGINEER: | Rodney Rogers
REVISION NUMBER:
| PLANNER / MARKETER: | Ginger Causey/ Lauri Allen
Summary Page
Estimate with
|  | Estimate | Contingencies | Contingencies
| Material and Equipment Cost | 20035 | 846 | 20880
| Field Direct Costs | 8960 | 0 | 8960
| Project Support Costs | 1675 | 250 | 1925
| Other (Overhead, AFUDC, & As-Builts) | 4869 | 174 | 5043
| Total | 35539 | 1270 | 36808
Does Not Include Any Amount for Income Tax Gross Up
Project Scope
This work order will capture the costs to install a Custody Transfer Sales Meter & Regulator Station at the existing HPL Port Arthur Field-Clark Refinery
Sales Station for the TEMPORARY service to Midcon's Carbon Black Station in Jefferson County, Texas. The temporary meter and regulator station will
be installed on Clark Refinery Plant Property adjacent to the existing HPL Clark Refinery Meter and Regulator Station. For the general project location,
see the following drawings: Valve Location Maps (VLM) 54 & 54A and station drawings HC-3037-25-H and HC-3037-26-H.
The temporary facilities will consist of the following facilities:
1. One (1) 3" Senior Orifice Skid Mounted Meter Run with Pressure and Temp. Chart Recorders (Note: Orifice Meter will be designed for 3 to 5 MMCF/Day.
2. One (1) 2" Primary Regulator Run with Monitor Regulator for Overpressure Protection and a 2" By-Pass Line (Note: Primary and Monitor Regulators
will be designed for 3 to 5 MMCF/Day @ a minimum upstream pressure of 550 psig and downstream MAOP of 340 psig.) Midcon's MAOP is 340 psig.
3. Midcon will furnish and install the proposed 3" pipeline to connect the proposed temporary meter and regulator station to their piping. Pipeline is
approximately 300 feet in length.
HPL will design, install and operate the meter and regulator station to Enron Engineering Standards. Per Lauri Allen, ENA Deal Maker, Midcon
will own all of the temporary facilities. Therefore, an Income Tax Gross-up Charge will NOT be charged to Midcon. Once the temporary service is
terminated, the temporary meter and regulator station will be disconnected and hauled to a Midcon Facility in the near vicinity of the project.
Per Property Accounting, a retirement work order to remove the temporary meter and regulator station will NOT be required.
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/REIMBMIDCONCARBONBLACKMTRREGSTA.xls'#$Summary with Project Scope
This is where you would enter the
"Level
of the
Estimate."
For Example (30%, 10%, etc.)
Start Typing in Column "A" of Row "36".

## Notes and Assumptions
ENA TECHNICAL SERVICES
PROJECT COST ESTIMATE
2025-09-26
| CUSTOMER COMPANY NAME: | Enron North America (Houston Pipe Line Co.)
| PROJECT NAME: | Temporary Meter & Reg. Sta. for Midcon's Carbon Black
W.O. NUMBER:
| PROJECT ENGINEER: | Rodney Rogers
REVISION NUMBER:
| PLANNER/MARKETER: | Ginger Causey/ Lauri Allen
Notes and Assumptions
1. A surface site will NOT be required. Plan to install temporary facilities on existing Clark Refinery Meter Station Site. (N)
2. Ingress and egress for construction activities can be obtained from Clark Refinery at no costs. (A)
3. Job duration is estimated at 5 days (mobilization to clean-up), weather permitting. (N)
4. Cost est. is + or - 10%. (N)
5. Cost est. is based on HMS completing calibration of pressure and temperature recorders and tubing and adjustment of regulators. (N)
6. A fence is NOT required. (N)
7. Cost est. is based on starting construction activities on May 1, 2000 and completing construction activities on May 14, 2000. (N)
8. Project will be released by Marketing in a timely manner to allow materials to be obtained without expediting or hot shot services. (N)
9. Since no digging will be required, no environmental costs are included in the cost estimate. (N)
10. Cost estimate does include moneys for overpressure protection. (N)
11. Per Midcon, redundant parallel regulator runs will NOT be required. (N)
12. Cost est. does NOT include moneys for extensive safety requirements by Clark Refinery or Midcon. Clark Refinery will require all workers to
attend a one day safety training class. (N)
13. COST EST. DOES NOT INCLUDE MONEYS FOR INCOME TAX GROSS-UP. IF INCOME TAX GROSS-UP IS REQUIRED, DEAL
MAKER SHALL DETERMINE AND PROVIDE INCOME TAX GROSS-UP PERCENTAGE PRIOR TO SUBMITTING WORK ORDER
AUTHORIZATION. MIDCON TO OWN FACILITIES. NO INCOME TAX GROSS-UP CHARGE. (N)
14. Per Facility Planning, the minimum pressure and maximum flow at the proposed meter station will be 550 psig and 5 MMCF/Day. (N)
15. Per Midcon, the feed to the Carbon Black Station is steady (i.e. No Swings). (N)
16. Cost est. is based on the proposed meter and regulator station being in-service for approximately 3 to 4 weeks (N)
17. Cost est. is based on the proposed meter and regulator station being installed and ready for service on May 14, 2000.
18. Project will be constructed using hand sketches due to facilities being temporary (i.e. no detailed Cad Drawings will be prepared). (N)
19. Cost est. does not include any moneys for rock. All of the proposed facilities will be above grade. (N)
20. Cost est. is based on utilizing the Special Project Team to perform and manage the physical construction activities. (N)
21. Cost est. is valid for 120 days. (N)
(A) - Assumption
(N) - Note
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/REIMBMIDCONCARBONBLACKMTRREGSTA.xls'#$Notes and Assumptions

## Notes (hidden)
ENA TECHNICAL SERVICES
PROJECT COST ESTIMATE
2025-09-26
| CUSTOMER COMPANY NAME: | Enron North America (Houston Pipe Line Co.)
| PROJECT NAME: | Temporary Meter & Reg. Sta. for Midcon's Carbon Black
W.O. NUMBER:
| PROJECT ENGINEER: | Rodney Rogers | 0 | 0
REVISION NUMBER:
| PLANNER / MARKETER: | Ginger Causey/ Lauri Allen
NOTES AND ASSUMPTIONS
(A) - Assumption
(N) - Note

## M&E Costs (hidden)
ENA TECHNICAL SERVICES
PROJECT MATERIAL (Attachment A.)
2000-03-13
CUSTOMER COMPANY NAME:
PROJECT NAME:
W.O. NUMBER:
|  | PROJECT ENGINEER: | FILE NAME:
REVISION NUMBER:
PLANNER / MARKETER:
MATERIAL AND EQUIPMENT COSTS
[6 empty] | W.O.A. | W.O.A.
|  |  | Est. | Est. | W.O.A. | COST | CONTINGENCY
Property |  |  | Quantity | Unit | Unit Cost | ESTIMATE | ESTIMATE
Unit | MATERIAL AND EQUIPMENT
903-00 | FREIGHT (4.50% of materials) |  |  |  |  | 0
904-00 | TAX (8.25% of materials) |  |  |  |  | 0
| MATL. & EQUIP. SUB-TOTAL |  |  |  |  | 0
534-00 | CONTINGENCIES |  |  |  |  | 0
| MATL. & EQUIP. SUB-TOTAL WITH CONTINGENCIES |  |  |  |  | 0