## PROS
ET&S REVENUE MANAGEMENT PROJECT
Timeline Differences
High Level Timeline
| 1999-07-01 | 1999-08-01 | 1999-09-01 | 1999-10-01 | 1999-11-01 | 1999-12-01 | 2000-01-01 | 2000-02-01 | 2000-03-01 | 2000-04-01 | 2000-05-01 | 2000-06-01 | 2000-07-01 | 2000-08-01 | 2000-09-01 | 2000-10-01
| Stage 1 |  |  |  |  | 12/99
|  |  | Stage 2 |  |  | 12/99
[6 empty] | Stage 3 |  |  | 3/99
[7 empty] | Stage 4 |  |  |  |  | 6/00
[13 empty] | Stage 5 |  |  | 10/00
Project Plan Detailed Timeline
| 1999-07-01 | 1999-08-01 | 1999-09-01 | 1999-10-01 | 1999-11-01 | 1999-12-01 | 2000-01-01 | 2000-02-01 | 2000-03-01 | 2000-04-01 | 2000-05-01 | 2000-06-01 | 2000-07-01 | 2000-08-01 | 2000-09-01 | 2000-10-01 | 2000-11-01
| Pre-Launch 7/6/99 | 8/16/99
| Stage 1 7/6/99 |  |  |  |  | 12/16/99
|  | Stage 2 8/16/99 |  |  |  | 12/16/99 | 1/26/00
[6 empty] | Stage 3 12/16/99 |  |  |  | 4/13/00 |  |  | 7/26/00
[7 empty] | Stage 4 1/4/00 |  |  |  |  | 6/29/00 | 7/26/00
[12 empty] | Stage 5 6/29/00 |  |  |  | 10/27/00 | 11/2/00

## New
ET&S REVENUE MANAGEMENT PROJECT
Possible Alternative
High Level Timeline
|  | 1999-08-01 | 1999-09-01 | 1999-10-01 | 1999-11-01 | 1999-12-01 | 2000-01-01 | 2000-02-01 | 2000-03-01 | 2000-04-01 | 2000-05-01 | 2000-06-01 | 2000-07-01
Stage 1
EDP | T/S | 1999-08-01: Design/Req.; 1999-12-01: Training
CAS Enhancements | T | 1999-08-01: Design/Req.
Pre-Launch F/O | T/S
Price Trend Analysis | S | 1999-09-01: Design/Req; 1999-12-01: ??????????????
Analysis-Utilization? | T | 1999-09-01: R & D
Stage 2
FDD Utilization | S | 1999-10-01: Design/Req; 2000-01-01: Training
IDD Optimization | S | 1999-11-01: Design/Req; 2000-02-01: Training
Stage 3
Pricing Module | T | 2000-01-01: Design/Req
Forecaster | T | 2000-01-01: Design/Req; 2000-05-01: Training
Stage 4
Optimization | T | 2000-03-01: Design/Req; 2000-07-01: Training
What-if's | T | 2000-03-01: Design/Req; 2000-07-01: Training
(New)
EDS
PROS

## New (2)
ET&S REVENUE MANAGEMENT PROJECT
Possible Alternative
PHASE I
High Level Timeline
|  | 1999-08-01 | 1999-09-01 | 1999-10-01 | 1999-11-01 | 1999-12-01 | 2000-01-01 | 2000-02-01 | 2000-03-01 | 2000-04-01 | 2000-05-01 | 2000-06-01 | 2000-07-01
Stage 1
EDP | T/S | 1999-08-01: Design/Req.; 1999-12-01: Training
CAS Enhancements/ Data Issues | T | 1999-08-01: Design/Req.
Pre-Launch of F/O | T/S
Price Trend Analysis | S | 1999-10-01: Design/Req
Analysis-Utilization? | T | 1999-09-01: R & D
Stage 2
FDD Utilization | S | 1999-10-01: Design/Req; 2000-01-01: Training
IDD Optimization | S | 1999-11-01: Design/Req; 2000-02-01: Training
Stage 3
Price Trend Analysis | T | 2000-01-01: Design/Req
Forecaster | T | 2000-01-01: Design/Req; 2000-05-01: Training
Stage 4
Optimization | T | 2000-03-01: Design/Req; 2000-07-01: Training
What-if's | T | 2000-03-01: Design/Req; 2000-07-01: Training
(New)
EDS
PROS

## New(B & W)
ET&S REVENUE MANAGEMENT PROJECT
Possible Alternative
PHASE I
High Level Timeline
|  | 1999-08-01 | 1999-09-01 | 1999-10-01 | 1999-11-01 | 1999-12-01 | 2000-01-01 | 2000-02-01 | 2000-03-01 | 2000-04-01 | 2000-05-01 | 2000-06-01 | 2000-07-01
Stage 1
EDP | T/S | 1999-08-01: Design/Req.; 1999-12-01: Training
CAS Enhancements/ Data Issues | T | 1999-08-01: Design/Req.
Pre-Launch of F/O | T/S
Price Trend Analysis | S | 1999-10-01: Design/Req
Analysis-Utilization? | T | 1999-09-01: R & D
Stage 2
FDD Utilization | S | 1999-10-01: Design/Req; 2000-01-01: Training
IDD Optimization | S | 1999-11-01: Design/Req; 2000-02-01: Training
Stage 3
Price Trend Analysis | T | 2000-01-01: Design/Req
Forecaster | T | 2000-01-01: Design/Req; 2000-05-01: Training
Stage 4
Optimization | T | 2000-03-01: Design/Req; 2000-07-01: Training
What-if's | T | 2000-03-01: Design/Req; 2000-07-01: Training
(New Group)
EDS
PROS