## Sheet1
Power Risk Management
Re-start/Integration Plan for NETCO
Plan Descriptions |  | Responsible Individual(s) | Due Date
Applications Needed |  |  | Testing to begin 1/14/2002
Terminal server for Portland |  | IT Infrastructure Team | Migration must be complete
|  | John Postlethwaite (user) | first day of trading
New instance of EnPower – this includes: |  | Steve Nat (IT)
Stacey White (user)
PortCalc (valuation engine)
Deal Entry
Deal Blotter
EOL interfaces
Curve Manager
Consolidated Position Manager
Pub Posting (external rates interface)
Report Tools
Scheduling Tools
Including VMS and FSP
New instances of Global Data to feed EnPower |  | Steve Nat (Power IT); Sundar Chitradurga (Global IT)
Stacey White (user)
Counterparty information
This includes all new desks
Curve (region) information
Delivery Point information
New instance of TAGG/ERMS for power futures trading |  | Steve Nat (Power IT); Zhiyong Wei (Gas IT)
Stacey White (user)
Ensure all contracts are still valid
Set up clearing brokers
Executive Reports Viewer |  | Hal McKinney (IT)
Stacey White (user)
To post management reports to website
RAC Website |  | Ganapathy Ramesh (IT)
Frank Hayden (user)
Interfaces to the following downstream systems: |  | Ganapathy Ramesh (IT) | Testing to begin 1/14/2002
Migration must be complete
CAS (Credit Aggregation System) |  | Debbie Brackett, Stacey White (users) | first day of trading
RisktRAC (for VAR reporting) |  | Frank Hayden, Stacey White (users)
Infinity or its equivalent for cash flow hedging |  | Unknown
Interfaces from the following downstream systems: |  |  | Testing to begin 1/14/2002
Migration must be complete
ERMS Curves Application |  | Steve Nat (Power IT); Zhiyong Wei (Gas IT) | first day of trading
Interest rate curve |  | Harry Arora, Jeff Gossett & Stacey White (users)
Gas curves needed in heat rate swaps and spread-options |  | Jeff Gossett, Stacey White (users)
Futures Curves |  | Stacey White (user)
Management Report Set-up |  | Stacey White (user) | 2002-01-14
Min Zheng (IT)
P&L reports by trader
Position reports by trader
Position reports by curve/region
Price reports by curve/region
VaR reports by trader
Directories To Be Transferrred |  | IT Infrastracture Team | 2002-01-14
Stacey White (user)
m:\common\power\ and all subdirectories
m:\riskmgt\ and all subdirectories
m:\power2\new_sys\region\
m:\power_devel\
o:\erms\controls\rmsdata\
Commercial Information Needed |  |  | 2002-01-14
List of tradeable commodities, other than power |  | John Lavorato
Trader desk assignments and hierarchy for VaR reporting |  | Kevin Presto & Tim Belden
Process for entering into interest rate hedges |  | John Lavorato