## Regulatory
ENRON NORTH AMERICA
REGULATORY REPORT
Support Type | Deal Name | Responsible Person | $ Impact (MM) | Key Issues | Updated | Strategies/Comments
Deal Support | Project Tex Mex | Bob Frank |  | US Export License, Transmission Ownership, Long-Term Firm Transmission Service; Market Reform in Mexico | 2000-09-08 | B&P finished the draft OATT. Export permit issues have been reviewed. Received legal memo discussing the ERCOT ISO transmission issues.
| CT Fuel Cell Farm | Dan Allegretti |  | CT funding for green energy. | 2000-09-08 | Enron is close to receiving a "firm" commitment for state funds. Intend to meet with Governor Rowland to support transaction.
| Texas Wind Plant | Ron McNamara |  | QF vs. EWG Status; renewable resource rules in ERCOT ISO. | 2000-09-08 | Researching issues. ERCOT ISO discussions continue to have issues "fitting" this project into the market rules. PUCT has taken this issue on as "critical" and will carry the key issues of market barriers to ERCOT ISO.
| Rock House | Frank Rishe |  | Siting & Permitting; FERC approvals | 2000-09-08 | Becky Merola has left Enron to go to TNPC. Frank Rishe is replacing her on this project.
| Project Moore | Aleck Dadson |  | Transmission access. | 2000-07-28 | No update.
| Project PeakCo | Bob Frank |  | Regulatory ability to sell power from Industrial on-site generation. | 2000-09-08 | Finished review and presentation of Industrial IT rates throughout US.
| EnerConnect | Aleck Dadson |  | Retail restructuring. | 2000-07-28 | No update.
| NSTAR Asset Management | Dan Allegretti |  | MA DTE approval. | 2000-09-08 | Discussions continuing with counterparty.
| Pastoria | Sandi McCubbin | 10 | Siting and Permitting. | 2000-09-08 | Received Cal Legislative approval for necessary fixes to allow continued development of Pastoria power plant in 2000. Awaiting Governor's signature.
| Project Neptune | Steve Montovano |  | Siting & Permitting; FERC approvals | 2000-07-28 | No update.
| Project Lincoln Center / Project Great Plains Center | Sue Landwehr |  | Siting & Permitting | 2000-09-08 | Continued legislative interactions on power plant issues. Participating through MWIPS on water and noise pollution issues in Illinois before Pollution Control Board.
| Wheatland Peaker | Barbara Hueter |  | Siting & Permitting; Interconnection; MAIN Control Area Status | 2000-09-08 | Working with Environmental Strategies to develop rules in Indiana NOX SIP process. Established relationships with Williams Company and are jointly filing writing comments to Indiana Dept of Environmental Management.
Regulatory Risk | United Illuminating - ICAP | Dan Allegretti | -100 | ICAP obligation | 2000-09-08 | Sought rehearing of initial FERC decision on ICAP. Filed with coalition to support NE-ISO filing of $0.17/kw-month on ICAP. Decision pending at FERC.
| Brownsville Peaker Air Permits | Mary Schoen |  | TN is modifying / responding to SIP Call due 10/1/00 - may reduce pollution amount. | 2000-09-08 | SIP Call Implementation Meetings with TN Air Board. Meetings with TVA upcoming.
| NYISO TCCs | Howard Fromer | -9 | NYISO market structure changes; NYISO price caps. | 2000-07-28 | FERC ordered $1,000/Mwh price cap through 10/1/00.
| Cal ISO Bid Cap | Jeff Dasovich / Sue Mara | -100 | Cal ISO Board vote on reducing real-time market to $250/Mwh; | 2000-09-08 | Cal ISO Board approved $250/MW bid cap. Recent vote to reduce bid cap to $150/MW was defeated, although Cal ISO Board approved indefinite term for $250/MW bid cap. EOB continues to try and seek lower bid cap. CPUC has held public meetings in San Diego to discuss "the guilty". Enron is responding formally to CPUC Investigation at end of this week.
| SDG&E Complaint Seeking Cost-Based Rates for All Sellers into Cal ISO and Cal PX | Mary Hain |  | SDG&E sought relief at FERC that would have removed Market-Based rate authority for all parties selling into the Cal ISO and Cal PX. | 2000-09-08 | EPMI and EES responded to Complaint. EPSA responded to Complaint. FERC rejected the Complaint. FERC opened Section 206 Proceeding to consider future changes to Cal ISO and Cal PX tariff as well as consider appropriateness of Market-Based rate authority for Western Power market participants.
| CFTC Reauthorization | Chris Long |  | Congressional reauthorization of CFTC agency. Form and structure of OTC Derivatives regulation. | 2000-07-28 | Legislation pending in Congress.
Advocacy | Federal Wholesale Restructuring Legislation | Cynthia Sandherr |  | Congressional mandate authorizing FERC to regulate bundled retail transmission service. | 2000-09-08 | Probability of Comprehensive Electricity Reform legislation passing is extremely low. Congress is considering partial reform bills on PUHCA, Public Use Tax issues, and Reliability. Enron is opposing all partial reform bills.
| Project Bluegrass | Richard Shapiro |  | Transmission access. | 2000-09-08 | Attempting to "jumpstart" FERC Commissioners into taking "significant" action related to Open Access. Retained key Democratic lobbyists. Meetings with Sect of Energy Richardson and Asst Sect of Energy Glick. Retained Luntz Consulting to field test key policy messages - 5 focus groups completed.
| FERC State of the Market Investigation | Joe Hartsoe |  | FERC Investigation on price spikes. | 2000-09-08 | EPSA continues to develop formal response to FERC with Boston-Pacific Consulting. Enron and EPSA have met with key FERC staff members to discuss market problems in California. This activity now includes Section 206 Proceeding created in SDG&E Complaint. FERC is focusing primarily on Western power markets. FERC staff members recognize key problems. Enron is preparing TOP 5 issues for "fixing" markets in West to deliver to FERC.
| RTO West | Steve Walton |  | Transmission access. | 2000-09-08 | Progress is being made on Physical Rights model for Congestion Management System. Expect NW RTO filings to be made to FERC at end of Sept 2000.
| MISO / Alliance RTO | Jeff Brown |  | Transmission access. | 2000-07-28 | Attending meetings; See Transmission Exchange.
| California ISO | Sue Mara |  | Transmission access. | 2000-09-08 | Responded to Cal ISO initial questionnaire related to future Congestion Management. Cal ISO has until 1/1/2001 to respond to Order 2000. Seeking to stop implementation of LMP.
| ERCOT ISO | Robin Kittel |  | Transmission access. | 2000-07-28 | Attending meetings; See Transmission Exchange.
| AEP Power Marketing Certificate | Sarah Novosel |  | Transmission access. | 2000-09-08 | Submitted testimony in AEP's Power Marketer Certificate case to seek additional transmission access.
| SPP RTO | Ron McNamara |  | Transmission access. | 2000-09-08 | Ron McNamara replaced Sarah Novosel to cover SPP. R. McNamara was nominated and approved for SPP Markets Working Committee responsible for key market structure issues.
| NERC Electronic Scheduling Task Force / OASIS Phase II | Charles Yeung |  | Transmission access. | 2000-09-08 | Developing mechanisms to combine OASIS, Tagging, and Transmission Scheduling to simplify business practices via electronic media.
| NEPOOL Congestion Management System | Dan Allegretti |  | Transmission access. | 2000-07-28 | FERC order mandated CMS and quicker implementation.
Regulatory Ventures | Project E-Trans | Jeff Brown |  | Vendor acceptance; market willingness; Regulatory approval. | 2000-09-08 | Meetings with all key vendors (ESCA, Cal PX, APX, PJM IA) have occurred. Next steps involve finalizing the key operational decisions by Sept 20, 2000. Enron has completed 1st draft of new RTO Tariff utilizing Capacity Reservation Model and Real Flow Congestion Management. Working to finalize vendor commercial structure (consultant and JV).
| Caledonia Tax Audit | Marchris Robinson | 0.285 | Tax Commission review. | 2000-07-28 | Achieved result.
| New Albany Tax Audit | Marchris Robinson | 0.21739 | Tax Commission review. | 2000-07-28 | Achieved result.
| PG&E Gas Outsourcing | Mona Petrochko | ? | CPUC approval of any commercial arrangement. | 2000-09-08 | Held first meeting with PG&E including M. McDonald, J, Thomas, T. Bottorff. Discussed commercial opportunity. Informed PG&E of our interest in working on retail and wholesale policy matters involving market price spikes.
| City of Cleveland Power Aggregation | Janine Migden | ? | City of Cleveland buying rules; Ohio retail access implementation. | 2000-09-08 | Working with ENA Origination to develop response to City of Cleveland RFP. Working with City Counsel to develop RFP to support Enron's market solution.
| SDG&E Full Requirements Supply | Jim Steffes | ? | CPUC approval of any commercial arrangement. | 2000-09-08 | SDG&E did not receive initial CPUC pre-approval of its structured RFT seeking supplies. Cal Legislature has voted to mandate a 6.5c/kwh rate through 12/31/2001 in SDG&E. Details of implementation still being considered.