## eolrelaunch
NewCoOnline Project Plan
Name | Resource Names | Notes
Non-secure Web Site Development | Erica B./Kal
Slightly update look for garden pages | Heather | Victoria and Heather workingon some designs.
Remove all Market Info. Content on current site |  | Done on development site. (Hyperion:7943)
Update which products appear on the delayed quotes on home page
Remove or modify Tour EnronOnline |  | Removed from development site; Updating text for release sometime post-Jan launch.
Change Homepage Intro. Text
Update Registration Wizard and Pages
Update About X, Contact, Press Room, FAQs
Secure Web Site Development | Rahil J.
Remove EnronOnline name from all sections including Help |  | RJ is working w/Teresa Smith on databases
Assist Product Control in any mass updating of databases
Eliminate options for Links and Auctions from navigation |  | Given to developers
Change New Features Option to What's New and link to FAQs |  | Given to developers
Prepare pop-up announcement for EOL users
Determine process of storing data (O Drive, H Drives etc) |  | Will be checking w/Jenny Rub
Marketing | Teresa M.
Prepare master/sub-user mailing list by trade vol. |  | TM is working w/PCG on counterparty lists. Should include top transacting counterparties with credit approval
Provide list of counterparties to Credit for pre-approval | Bob S. | Waiting on meeting with Debbie Brackett
Come up with a employee/customer promotion for top traders
Develop list of clients by city for road show
Mark to Market Lists | D. Diamond | Get w/Debbie Brackett on who we owe $$ to.
Specs for addt'l admin fields for sub-users | L. Hernandez | Working w/T. Smith on this
Schedule meetings with key clients
Broker Client Issues
Put together proposals for usage for Broker Clients | D. Diamond/B. Shults | idea is to give 3 free months to help w/the marketing aspect of using newco
Rework Broker Client contracts
Legal Set Up | Carl Carter
Update all contracts ETA, PA, GTCs |  | PA and ETA revisions sent to Mark T. on 12/12; Update GTC's…may use standard master agreement
What data will NewCo be able to obtain? Contracts? Databases?
Update Legal and Privacy Statement |  | Sent revision to Mark T. on 12/13
Trademark new name and tagline
Product Control | Jennifer D.
Gather Lists: Product Types | Kevin Meredith | Done (in O drive)
Gather Lists: Data components | Kevin/Chris/Charlie | Done (in O drive)
Gather Lists: Top Transacting Counterparties | Tara/Tom | Done
Gather Contract Numbers for top transacting CPs | Lisa/Tom | Coordinating with Global Contracts--In Progress
Determine Top 10 Products (Kal requested) |  | JDD gave list to Kal; Kal will sort to get what he needs
Need list of possible mid/back office internal users
Develop process to issue or map new passwords to internal users | ?
Bridging | Torrey/Tara | Work through bridging issues (redirect to new downstream systems)
Identify and update all product types and descriptions | Kevin Meredith/Melba Lozano | Identification of Ptypes complete (see "Gather Lists" above); creating list of elements to be updated (Kevin/Melba); List of database elements containing reference to Enron, EnronOnline, etc in development
Define an accelerated customer registration process | Bob S./Lisa Lees
Develop new templates for public and management reports | Torrey/Tara
Register users for new web site
Credit Set Up | Bob S./Jennifer D.
Get credit pre-approvals for all counterparties in mailing list
List of Gas & Power Spreadsheets for Stack & Website | Stephanie Sever | Created spreadsheet & sent to head Gas & power traders to determine level of access for Stack & Website; 12/18 still waiting to hear back from head traders
Call Center
Determine FAQ's - and potential FAQ's for turnover | Mary Griff Gray | In Progress
Determine Call Center telecomm and software requirements | Mary Griff Gray | Done
Website testing
User Acceptance Testing
Complete quotes control testing in progress in EOLTEST | Tom/Matt/Ricky/Sunil
Work with IT on outstanding items in progress - Options Mgr | Tom
Work with IT on requirements
Get all test plans ready - and set up test machines | Sunil
Determine potential data conversion issues | UAT/PCG
Enter change request on id/password rules | Tom | entered
Training and Operations Support
Internal training | Lindsay/Angie | Lindsay Renaud and Angie Zeman to train internal traders
Help guide and training manuals | Lindsay/Angie | Getting RoboHelp and existing guides/manuals
Brand Management/Public Relations | Kal S.
Develop new tagline |  | Just name changes right now. Look shouldn't change right now
Request look and branding guidelines (if they exist) from Suiter company
Design new logo and tagline
Write Press Release
Draft text for e-mail/letter to customers for registration
Develop FAQs Document | Kal S./Bob S.
Develop PowerPoint Presentation | Bob S.
Develop new collateral materials -- letterhead, envelopes, folders | Heather | Keep it simple. Folders to customers to include: FAQ, letter, and PA forms
Develop and print new customer registration and PA forms
Print new secure password envelopes
Develop new marketing brochure | Heather
Drop snail mail and e-mail announcing launch
Issue Press Release
Charges to Customers |  | Should we charge for view only access?
New Buyer Online Deal Packet | Bob S.
Credit Proposal
Broker Client Proposal
Legal Structure
Brand Management/Public Relations
Internal Access |  | done - Traders manual
Operations procedures |  | done
NewCo Needs
New Email address for all employees | Tom Engel
New Email address for Call Center/PCG | Tom Engel
New Phone Number Help and Fax numbers for PCG | Lo
New Main Number | Lo
New P. O. Box | Lo
Marketing Database |  | Kara wanted to know what reports would be accessible. Dave said that high level reports should be accessible. The marketing database itself should be accessible but will purge transactional data
Migration of info on O & H Drives | Rahil/Everyone | Rahil will find out what the process is but everyone will be responsible for migrating over their own information.