## Sheet1
# | Category | Finding | Action Item | Responsible Person | Target Date | Confirm Reviewer | Completion Date | Comments
33 | HAZARDOUS WASTE Regulation Condition | An assessment of the area of the pipeline meter located in the northern portion of the Main Plant Area found elevated levels of mercury. | Determine extent of mercury contamination. | Butch Russell | 2001-06-30 | Rick Suderman
35 | HAZARDOUS WASTE Regulation Condition | Unknown whether abandoned concrete surface impoundment has ever been assessed for sub-surface soil contamination. | Verify closure of concrete surface impoundment for presence or absence of sub-surface soil contamination. | Butch Russell | 2001-06-30 | Rick Suderman
36 | HAZARDOUS WASTE Regulation Condition | An assessment documented mercury contamination in vicinity of former meter shop. | Develop plan to address mercury contamination. | Butch Russell | 2001-06-30 | Larry Campbell
37 | HAZARDOUS WASTE Regulation Condition | An assessment of the loading rack documented hydrocarbon levels at concentrations exceeding action levels established by the Kern County Environmental Health Services Department. | Develop plan to address hydrocarbon contamination. | Butch Russell | 2001-06-30 | Larry Campbell
29 | HAZARDOUS WASTE Regulation Condition | An assessment of cooling tower area found chromium contamination, but no plan for remediation has been developed. | Determine vertical and lateral extent of chromium contamination. | Larry Campbell | 2001-06-30 | Rick Suderman
30 | HAZARDOUS WASTE Regulation Condition | An assessment of the wash rack area found elevated levels of lead, barium, chromium, copper, and mercury. | Determine extent of metals contamination. | Larry Campbell | 2001-06-30 | Rick Suderman
31 | HAZARDOUS WASTE Regulation Condition | An assessment of the propane compressor area found elevated levels of lead and chromium. | Determine extent of metals contamination. | Larry Campbell | 2001-06-30 | Rick Suderman
32 | HAZARDOUS WASTE Regulation Condition | An assessment of the propane compressor area found elevated levels of benzene. | Determine extent of benzene contamination. | Larry Campbell | 2001-06-30 | Rick Suderman