## To do
To dos |  |  | For which book | Person/group responsible | Date to start | Date to complete
1 |  | All books have been sorted to determine which have had activity in the recent past. The ones that had not were sent to the individual commodity groups and they determined which books should be deleted, archived, or marked as inactive. | Dormant | Risk Controls
| a | We have received all of these back from the commodity groups with the exception of east power.
| b | We need to confirm that the list we used is a complete list and there are no hidden books that should have been on the list
2 |  | Procedures and processes need to be developed to ensure that ERMS books established flow properly into RiskTrac. This does not address any clean-up that needs to take place, but what we should do going forward, once clean-up has occurred | Open | Risk Controls
| a | What rules need to be made? One commodity per book? Should ERMS to RiskTrac books be one-to-one?
| b | Further establish set-up procedures for new books in ERMS & RiskTrac
3 |  | We need to get the system to archive/delete closed books | Dormant | IT
4 |  | We need to get the system to mark books as active or inactive | Open | IT
5 |  | Risk controls needs to have an up-to-date list of all ERMS and RiskTrac Books |  | Risk Controls
| a | Monitor the differences in books between the two systems
6 |  | Clean-up - The existing portfolio structure needs to be reviewed by going through all books to ensure that all ERMS books are mapped to RiskTrac. | Open | Risk Controls
| a | Currently, for books with more than one commodity, only the last added commodity flows to RiskTrac
7 |  | A further understanding between the information going from RiskTrac to Credit and Market Risk (V@R engine) needs to be obtained | Open | Risk Controls
| a | If a book is not officialized, credit takes the last officialized info. If there are no more positions in that book, they could be picking up incorrect information.
8 |  | We need a system to deal with vacations and holidays. | Open | IT
9 |  | Risk leads should maintain a list of all books and how they are allocated to each book administrator. | Open | Commodity groups
10 |  | Book administrators should have a list of all books they are required to officialize each night. | Open | Commodity groups
11 |  | Commodity groups should reconcile ERMS output to RiskTrac each night before leaving. | Open | Commodity groups
| a | Global liquids is putting this in place.
| b | Gas should have this in place.
12 |  | Risk contols needs to be able to tell if books had positions or not | Open | IT
11 |  | The process for uploading spreadsheets needs to be documented and standardized. | Open | Risk Controls

## DATA
Books in RiskTrack - Estimates
Dormat or need to be deleted | 1000 | Dormat or need to be deleted 35.71%
Active | 930 | Active 33.21%
Inactive | 870 | Inactive 31.07%
Total | 2800