## Hoja1
STAKEHOLDERS ACTION PLAN - CHORETY
STAKEHOLDER | IMPORTANCE POSITIONS | ACTION | RESPONSIBILITY / SPOKESPERSON | TARGET DATE | OUTCOME
SANTA CRUZ PREFECTO Lic. Ramon Prada | He wants to go to the site July 23 |  | Teresita Arandia
DEPARTMENTAL RESOURCES ENVIRONMENT PREFECTURA Dr. Rafael Soto Pinto Director | Is key advisor to Prefecto on spill. He flew over the spill site. He needs the social and clean-up plans from Transredes by Wednesday July 19. Plans to take water samples together with Transredes representatives on Sunday, July 23. He is supportive. | Send social and cleaning plan of action from Transredes by Wednesday, July 19. | Frank Sugrañes / Teresita Arandia
SUPER-INTENDENCIA DE HIDROCARBUROS José Alberto Ruiz Representative Regional |  | Provide info updates.
VM ENERGY Regional Representation Edwin Terán | He flew over the spill site. Wants to be kept informed. Supportive. | Provide info updates. | Teresita Arandia / Frank Sugrañes
MIN. SUSTAINABLE DEV. AND ENVIRONMENT Representation Mauricio Mesa |  | Provide info updates.
CIVIC COMMITTEE Alfonso Moreno President Comité Pro-Santa Cruz |  | Send information.
CAMIRI SUBPREFECTO Ing. David Vaca Diez | Does not want to make the issue bigger. His office is coordinating work with Transredes. However he asked for the water sample result from Santa Cruz Prefectura. |  | Teresita Arandia/Frank Sugrañes/Gin Carrión
DEPUTIES Offman Blanco (MNR Camiri) | Criticized Transredes for not informing the Camiri water company about the spill. He also accused Transredes for not properly maintaining the pipeline. (Newspaper El Nuevo Dia) | Need to consider community programs. | Teresita Arandia / Frank Sugrañes
ALCALDIA CAMIRI MAYOR Lic. Lázaro Vargas | Is key local political leader. Under pressure to not cooperate with Transredes. Does not want to make the issue bigger, but is concerned about the social impact of the spill. His office is coordinating work with Transredes. However he asked for the water sample result from Santa Cruz Prefectura.
ENVIRONMENTAL Guido Vega | Does not want to make the issue bigger, but is concerned about the social impact of the spill. His office is coordinating work with Transredes. However he asked for the water sample result from Santa Cruz Prefectura. |  | Teresita Arandia /Frank Sugrañes
CIVIC COMMITTEE Jorge Michel | Does not want to make the issue bigger, but is concerned about the social impact of the spill.
PARISH PRIEST César | Influential in local communities. | Personal visit. | Teresita Arandia | July/19 | Positive, appreciated the breafing.
CUARTEL ABAROA Cnl. Carlos Torrico | Influential in local communities. | Personal visit to thank for providing soldier for Transredes clean up. | Teresita Arandia
INDIGENOUS PARQUE NAL. KAA-IYA GRAN CHACO Luis Fernando Tercero Director
ALTO Y BAJO IZOZOG Bonifacio Barrientos Capitán Grande
CONF. DE PUEBLOS INDIGENAS DE BOLIVIA Nicolas Montero Presidente | Organizing march for July 27/28
NGO'S WWF Patricia |  | Send both press release | Dany Dunlop
MEDIA EL DEBER | Critical. Reports that 230 families along river are exposed to health dangers | Meet with editor. | Teresita Arandia
EL NUEVO DIA | Neutral Describes spill and Transredes says that contractor is responsible. Reported that water plant official and University allege that water is contaminated.
EL MUNDO | Balanced. Focus on health concerns along the river. Balanced by describing Transredes clean up response. Reports that Greenpeace will come to Camiri to investigate. | Meet with reporter to clarify fonts. | Teresita Arandia
LA ESTRELLA DEL ORIENTE | Neutral. Describes Transredes cleaning. Decision to suspend contractors.
RADIO MILENIUM | Critical. One of two more important stations. | Visit station manager and journalists. Invite to lunch with the radio stations. | Teresita Arandia | July/19
RADIO CAMIRI | Neutral. Based on Transredes press release and conference. One of two more important stations |  | Teresita Arandia | July/19 | Favorable. Station issued story correcting erroneous information for broadcast.
RADIO CHACO | Neutral. Based on Transredes press release and conference. | Invite to lunch. | Teresita Arandia | July/19
RADIO SANTA CRUZ | Neutral. Based on Transredes press release and conference. | Invite to lunch. | Teresita Arandia | July/19 | Positive.
LA PAZ MINISTRIES SUSTAINABLE DEVELOPMENT José Luis Carvajal |  | Meeting on July 20 | Steve Hopper/ Frank Sugrañes/ Fernando Gonzales/ Teresita Arandia
VM SUSTAINABLE DEVELOPMENT Neiza Roca | Representative from Ministry, flew over site. Wants to be kept informed. |  | Teresita Arandia
AGRICULTURE O. Antezana
COMMUNICATION M. Kempff
VM COMMUNICATION H. Terrazas
ECONOMIC DEV. J. L. Lupo
VM ENERGY C. Contreras
INTER- INSTITUTIONAL COMMITTEE HEALTH G. Cuentas
REGULATORY SIRESE C. Besse
HYDROCARBONS SUPERINTENDENT C. Miranda
DIPLOMATIC US Embassy |  | Send spill information.
USAID
British Embassy |  | Send spill information.
Dutch Embassy |  | Send spill information.
NGOs Lidema
Care |  | Send spill information, consider managing social plan.
Amazon Watch
Bank Information Center
WCMC
Conservation International
Pro-Natura
Living Earth
MEDIA State Television Ch7 |  | Interviewed Steve 7/18 | Steve
Unitel Ch9 | Positive. Used Transredes information. | Attended press conference in Camiri
ATB Ch5 | Presented facts based on Transredes information. But also interviewed President of Youth Union.
PAT Ch90 | Positive. Used Transredes information.
Megavisión Canal 18 | Positive. Used Transredes information.
Red Uno Ch 13 | Positive. Used Transredes information.
Presencia | Neutral. Reported that 3 communities along the river are affected by the oil spill. Other coverage reflects Transredes press releases.
La Prensa | Positive. Used Transredes information.
Ultima Hora | Positive. Coverage reflects Transredes press releases.
El Diario | Positive. Coverage reflects Transredes press releases.
La Razón | Positive. Coverage reflects Transredes press releases.
WEEKLY’s Bolivian Times
Nueva Economía
Pulso
WIRE SERVICES
Associated Press
Bridge News
France Press
Italian News Agency ANSA
Spanish News Agency EFE
Agencia Boliviana de Información (ABI)
Reuters/Jatha
Agencia Nacional Fides
German News Agency DPA
The Economist
New York Times
CNN
WEB PAGE | Press releases, photos, fact sheet, map posted. | Teresita / Patricia Gomez / Emilio Peña
TRANSREDES EMPLOYEES | Preocupation about the spill, along with other issues. Can affect morale. | Steve Hopper | Address staff. | July 19 | Favorable.

## Hoja2
Stakeholder
LA PAZ
MINISTRIES
Sustainable Development – Jose Luis Carvajal
VM Sust Dev - Neiza Roca
Agriculture – O. Antezana
Communication – M. Kempff
VM Comms – H. Terrazas
Economic Dev. – JL Lupo
VM Energy – C. Conteras
Inter-Instit Committee
Health – G. Cuentas
REGULATORY
SIRESE – C. Besse
Hydrocarbons Superint. – C. Miranda
INSTITUTIONS
Private Sector Conf CEPB
Nat Chamber Commerce
Nat Chamber Industry
American Chamber of Commerce - AMCHAM
Anglo-Bolivian Committee
National Institute of Statistics
DIPLOMATIC
US Embassy
US Information Services
USAID
US Commercial Office
British Embassy
Dutch Embassy
NGOs
Lidema
Care
WWF
USAID
Save the Children
EDUCATIONAL
Ecology Inst. – UMSA
Catholic University
MEDIA
State Televisión Ch7
Unitel Ch2
ATB Ch9
PAT Ch90
Bolivsion
Red Uno Ch 11
Presencia
La Prensa
Ultima Hora
El Diario
La Razón
WEEKLY’s
Bolivian Times
Nueva Economía
Pulso
Radio Panamericana – JJ Hidalgo
Radio Fides – Padre Pérez
Radio Libertad
State Radio Illimani
Radio Altiplano
WIRE SERVICES
Associated Press
Bridge News
France Press
Italian News Agency ANSA
Spanish News Agency EFE
Agencia Boliviana de Información (ABI)
Reuters/Jatha
Agencia Nacional Fides
German News Agency DPA
The Economist
New York Times
CNN
WEB PAGE
TRANSREDES EMPLOYEES