## summary
2025-09-26
MARINER ENERGY, INC.
APPENDIX
WEEKLY DRILLING AND COMPLETION SUMMARY
[7 empty] | PRESENT | PROPOSED
|  | PROSPECT | AREA | WELL | E/D | WI% | DEPTH | TD | COMMENT
| I. | WELLS CURRENTLY DRILLING
None to report.
| II. | WELLS REACHING TOTAL DEPTH, TESTING, OR TURNED TO SALES THIS WEEK
|  | Green Canyon 472 | Deepwater | OCS-G #2 ST #1 | D | 50% | 11,484' | 11,625' | Completing.
(King Kong)
|  | Mississippi Canyon 322 | Deepwater | OCS-G #3 ST 1 | E | 40% | 7,300' | 7,518' | Rig released.
(Crater Lake)
| III. | WELLS ANTICIPATED TO SPUD WITHIN 90 DAYS
|  | Green Canyon 473 | Deepwater | OCS-G #2 | D | 50% |  |  | Completion.
(King Kong)
|  | Green Canyon 136 | Deepwater | OCS-G #8 | D | 25% |  |  | Drill.
(Shasta)
| IV. | OTHER
None to report.