## summary
2025-09-26
MARINER ENERGY, INC.
APPENDIX
WEEKLY DRILLING AND COMPLETION SUMMARY
[7 empty] | PRESENT | PROPOSED
|  | PROSPECT | AREA | WELL | E/D | WI% | DEPTH | TD | COMMENT
| I. | WELLS CURRENTLY DRILLING
|  | Mississippi Canyon 561 | Deepwater | OCS-G #1 | E | 16.7% | 13101 | 15,500' | Preparing to sidetrack.
(Monet/Hells Canyon)
|  | Mississippi Canyon 322 | Deepwater | OCS-G 19936 #2 | E | 40% | 9,820' | 9,712' | Completing.
(Crater Lake)
|  | Green Canyon 516 | Deepwater | OCS-G # 1 | E | 44% | 9,290' | 11,700' | Preparing to squeeze 13 3/8" shoe.
(Yosemite)
|  | Sandy Lake | Hardin Co. | BSM #B-1 ST 2 | D | 72% |  | 10,862' | Sidetracking.
TX
|  | Galveston 151 | Offshore, TX | A-1 | D | 33% | 11,365' |  | Recompletion.
| II. | WELLS REACHING TOTAL DEPTH, TESTING, OR TURNED TO SALES THIS WEEK
|  | Green Canyon 472 | Deepwater | OCS-G #2 | D | 50% | 11,625' | 11,625' | Preparing to run 9 5/8" casing.
(King Kong)
| III. | WELLS ANTICIPATED TO SPUD WITHIN 90 DAYS
|  | East Breaks 981/AC 13 | Deepwater | OCS-G #1 | E | 25% |  |  | Expect to spud test well in July.
(Argo/Mockingbird)
|  | Green Canyon 473 | Deepwater | OCS-G #2 | D | 50% |  |  | Completion.
(King Kong)
|  | Mississippi Canyon 322 | Deepwater | OCS-G #3 | E | 40% |  |  | Expect to spud early July.
(Crater Lake)
| IV. | OTHER
None to report.