## summary
2025-09-26
MARINER ENERGY, INC.
APPENDIX
WEEKLY DRILLING AND COMPLETION SUMMARY
[7 empty] | PRESENT | PROPOSED
|  | PROSPECT | AREA | WELL | E/D | WI% | DEPTH | TD | COMMENT
| I. | WELLS CURRENTLY DRILLING
|  | Green Canyon 136 | Deepwater | OCS-G 4508 #8 | D | 25% | 2,140' | 7,600' | Repair and test mud line equipment.
(Shasta)
| II. | WELLS REACHING TOTAL DEPTH, TESTING, OR TURNED TO SALES THIS WEEK
|  | Green Canyon 473 | Deepwater | OCS-G #2 | D | 50% |  |  | Completed well. Pulling riser.
(King Kong)
| III. | WELLS ANTICIPATED TO SPUD WITHIN 90 DAYS
None to report.
| IV. | OTHER
None to report.