## summary
2025-09-26
MARINER ENERGY, INC.
APPENDIX
WEEKLY DRILLING AND COMPLETION SUMMARY
[7 empty] | PRESENT | PROPOSED
|  | PROSPECT | AREA | WELL | E/D | WI% | DEPTH | TD | COMMENT
| I. | WELLS CURRENTLY DRILLING
|  | Viosca Knoll 962 | Deepwater | OCS-G 15445 #1 | E | 15% | 7,544' | 13,760' | Drilling.
(Swordfish)
|  | South Timbalier 316 | Deepwater | OCS-G 22762 #2 | E | 20% | 3,800' | 13,000' | Drilling.
(Roaring Fork)
| II. | WELLS REACHING TOTAL DEPTH, TESTING, OR TURNED TO SALES THIS WEEK
None to report.
| III. | WELLS ANTICIPATED TO SPUD WITHIN 90 DAYS
|  | Visoca Knoll 962 | Deepwater | OCS-G 15445 #2 | E | 15% |  | 3,835' | Expected spud date mid December 2001.
(Swordfish)
|  | Mississippi Canyon 205 | Deepwater | OCS-G #1 | E | 25% |  | 3,500' | Expected spud date mid December 2001.
(Piston)
| IV. | OTHER
None to report.