## Scope of Work
EXHIBIT A
Summary of ENRON and FCE Scope of Supply
| ENRON | FCE
Initial Stack Module Fabrication |  | x
22 skids: Each skid includes the following: |  | x
DC Power Generator : 2 Carbonate Fuel cell modules per slab |  | x
Fuel Treatment: Preconverter afterfilter, cold gas desulifurizer, desulfurizer afterfilter |  | x
Oxidant Supply: Air supply blower, air filter / silencer, oxidizer / heater |  | x
Heat Recovery Unit: Fule Superheater, fuel heater, deaerator / boiler, HRU polisher, Preconverter, exhaust stack |  | x
Water Treatment: Treated water transfer pumps: treated water storage tank, water pretreatment & RO SKID |  | x
Compressed Air: Air Dryer, Air receiver, air compressors |  | x
Nitrogen Supply: N2 Bottle rack, N2 Bottles |  | x
Power plant Engineering |  | x
Equipment Procurement(Plant Skids) |  | x
BOP(FCE Skids) equipment warranty |  | x
Site specifications and laydown specifications |  | x
Equipment loading specification for foundations |  | x
Freight & Heavy Haul | x
Powerplant construction:
equipment unloading and laydown |  | x
equipment installation and and checkout (electrical) |  | x
piping installation |  | x
initial stack module installation |  | x
Initial Fill: Sulfur Sorbent, Preconverter Catalyst, De-Oxidizer Catalyst, Anode Exhaust Catalyst, Salt |  | x
permitting | x
taxes - sales,use,excise | x
Development Fees | x
Geotech Study | x
Electrical Load Study | x
Owners Engineer | x
Project Management | x
Site Selection and preparation:
Land | x
Foundations |  | x
Site to Spec | x
Underground conduit and piping | x
Fill & Grade | x
Piling | x
Access roads | x
Fencing | x
Site Remediation | x
Site Demolition | x
Gas Connection | x
Gas Fuel metering | x
Gas fuel let-down station | x
Gas Distribution piping to each slab | x
Water Connection | x
Water metering | x
Water distribution to each slab | x
Sewer Connection | x
Fire water | x
Non standard exhaust manifolding or cogeneration | x
Grid Interconnection | x
Ground Grid | x
Electrical interconnection of individual plants (above 480v) | x
Step up transformers | x
HV Breakers | x
Electrical metering, HV-side | x
Individual power plant control systems |  | x
Emergency Lighting/ UPS | x
Spare parts list |  | x
O&M Manuals |  | x
O&M Training Three(3) -one(1) week courses |  | x
Operations and Maintanence | x
Start up Consumables: Filters, lube oil, etc. |  | x
Startup and Acceptance Test | x
Startup and Acceptance Testing Advisory Support (TDOI) |  | x
Control Room/Spare parts Building | x
Supervisoy dispatch/control of multiple-plant site | x
Remote monitoring of individual powerplants | x | x
Co-branding and signage | x | x
Outside of initial purchase scope:
Stack replacement/service contract |  | x