## Enron
Site Name | Permit Application No. | Permit Number | Legal Description |  |  |  | UTM Coordinates |  |  | No. of Pieces of Equipment |  |  |  |  | Dates
Written Notifications
|  |  | 0.25 | S | T | R | Zone | East | North | H24GL | 7044GSI | 3516 | Start of Complete Review | Start of Technical Review | Start of Public Comment | Permit Approved | Start of Construct | Date of Startup - Anticipate | Date of Startup - Actual | "As Built" Site Plan | Engine Testing
House Creek | AP-940 | [13 empty] | 1999-09-08
Main Site |  | CT1616 |  | 33 | 46N | 74W | 13 | 439200 | 4862850 | - | 2 | -
Pod 1 |  | CT1617 |  | 34 | 46N | 75W | 13 | 431000 | 4863200 | 2 | - | -
Pod 2 |  | CT1618 |  | 34 | 46N | 75W | 13 | 434800 | 4870500 | 2 | - | -
Pod 3 |  | CT1619 |  | 29 | 46N | 74W | 13 | 437400 | 4863800 | 2 | - | -
Pod 4 |  | CT1620 |  | 10 | 45N | 74W | 13 | 440900 | 4859300 | 2 | - | -
Maverick | AP-170
Main Site |  | CT1621 | NW NE | 32 | 49N | 75W | 13 |  |  | - | - | 3
Box Draw | AP-960 | [13 empty] | 1999-09-08
Main Site |  | CT1622 | NW | 3 | 51N | 73W | 13 | 449747 | 4919743 | - | 2 | -
Pod 1 |  | CT1623 | NE | 30 | 52N | 73W | 13 | 445921 | 4923170 | 2 | - | -
Pod 2 |  | CT1624 | NE | 6 | 51N | 73W | 13 | 446394 | 4919470 | 2 | - | -
Pod 3 |  | MD478 | NE | 4 | 51N | 73W | 13 | 448996 | 4919424 | 2 | - | -
Pod 4 |  | MD479 | NW | 9 | 51N | 73W | 13 | 448378 | 4917829 | 2 | - | -
Pod 5 |  | CT1627 | SW | 2 | 51N | 73W | 13 | 451376 | 4919132 | 1 | - | -
Pod 6 |  | CT1628 | SE | 35 | 52N | 73W | 13 | 452236 | 4920978 | 1 | - | -
Hannum | AP-950 | [13 empty] | 1999-09-22
Main Site |  | CT1640 | NW of SW | 9 | 47N | 73W | 13 | 448069 | 4878898 | - | 2 | -
Pod 1 |  | CT1640 | NW of SW | 9 | 47N | 73W | 13 | 448069 | 4879111 | 4 | - | -
Caballo
Quantum/a.k.a. Mustang (revised) |  | CT1783 | SE of SE | 16 | 48N | 72W | 13 | 459291 | 4886429 | 3 | 4 | -
Pod 1 (revised) |  | CT1784 | NW of SW | 9 | 48N | 72W | 13 | 458240 | 4888426 | 5 | - | -
Pod 2 |  | CT1785 | SE of NW | 16 | 48N | 72W | 13 | 458685 | 4887296 | 2 | - | -
Pod 3 |  | CT1786 | SW of NE | 16 | 48N | 72W | 13 | 459093 | 4887305 | 2 | - | -
Pod 4 |  | CT1787 | NE of SW | 16 | 48N | 72W | 13 | 458672 | 4886849 | 1 | - | -
Yates/a.k.a. Haracz (revised) |  | CT1788 | SW NE | 36 | 48N | 73W | 13 | 453861 | 4882238 | - | 2 | -
Petrogulf/a.k.a. Palomino (revised)
Main Site |  | CT1778 | SW NW | 5 | 47N | 72W | 13 | 459862 | 4881232 | 6 | 3 | -
Pod 1 (revised) |  | CT1779 | SW NE | 13 | 47N | 73W | 13 |  |  | 3 | - | -
Screw Site 3 (revised) |  |  | NE NE | 20 | 47N | 73W | 13 | 447805 | 4876397 | 2 | - | -
Petrogulf Bonepile/a.k.a. Clydesdale
Main Site (revised) |  | CT1780 | NE of SW | 29 | 48N | 73W | 13 | 447063 | 4883770 | 2 | 2 | -
Pod 1 (revised) |  | CT1781 | SW of NW | 29 | 48N | 73W | 13 | 446652 | 4884197 | 2 | - | -
Pod 2 (revised) |  | CT1782 | NE of SW | 30 | 48N | 73W | 13 | 445511 | 4883836 | 2 | - | -
South Kitty
Main Site |  | CT1870 | SE of SE | 32 | 50N | 73W | 13 | 447806 | 4900924 | - | 3 | -
Pod 1 |  | CT1871 | SE of SE | 27 | 50N | 73W | 13 | 451096 | 4902559 | 2 | - | -
Pod 2 |  | CT1872 | NE of NW | 36 | 50N | 73W | 13 | 453507 | 4902203 | 3 | - | -
Pod 3 |  | CT1873 | NE of SW | 3 | 49N | 73W | 13 | 450262 | 4899750 | 2 | - | -
Pod 4 |  | CT1874 | NE of NW | 4 | 49N | 73W | 13 | 448629 | 4900543 | 2 | - | -
Pod 5 |  | CT1875 | SW of SW | 21 | 50N | 73W | 13 | 448251 | 4904220 | 3 | - | -
Kudzu
Main Site |  | CT1862 | SW/NW | 2 | 45N | 75W | 13 | 432450 | 4861400 | 2 | 3 | -
Pod 1 |  | CT1863 | SW/SE | 31 | 46N | 75W | 13 | 426486 | 4862349 | 2 | - | -
Pod 2 |  | CT1864 | NE/SW | 33 | 46N | 75W | 13 | 419450 | 4862777 | 2 | - | -
Pod 3 |  | CT1865 | NW/SE | 6 | 45N | 75W | 13 | 426457 | 4861085 | 2 | - | -
Pod 4 |  | CT1866 | SE/SW | 8 | 45N | 75W | 13 | 427560 | 4859242 | 2 | - | -
Pod 5 |  | CT1867 | SE/SE | 10 | 45N | 75W | 13 | 431635 | 4859019 | 2 | - | -
Pod 6 |  | CT1868 | NE/SE | 21 | 45N | 75W | 13 | 429206 | 4856352 | 2 | - | -
Hoe Creek
Main Site |  | CT1856 | SW SE | 5 | 47N | 74W | 13 | 437749 | 4880197 | - | 2 | -
Pod 1 |  | CT1857 | NE SW | 5 | 47N | 74W | 13 | 437336 | 4880605 | 2 | - | -
Pod 2 |  | CT1858A | NE SW | 31 | 48N | 74W | 13 | 435676 | 4872417 | 2 | - | -
Pod 3 |  | CT1859 | NW SE | 30 | 48N | 74W | 13 | 436093 | 4874026 | 2 | - | -
Pod 4 |  | CT1860 | NE SW | 29 | 48N | 74W | 13 | 437285 | 4874026 | 2 | - | -
Pod 5 |  | CT1861 | SE NW | 16 | 47N | 74W | 13 | 439160 | 4877789 | 2 | - | -
Hannum (addition)
Main Site (w/add'n) |  | MD460 | NW of SW | 9 | 47N | 73W | 13 | 448069 | 4878898 | - | 4 | -
Maverick (addition)
Main Site (w/add'n) |  | MD463 | NW NE | 32 | 49N | 75W | 13 |  |  | - | - | 4
Natural Gas Fuels
Main Site |  | CT1923 | NE | 13 | 46N | 73W | 13 |  |  | 1 | 1 | -
Pod 1 |  | CT1924 | SE | 12 | 46N | 73W | 13 |  |  | 1 | - | -
Pod 2 |  | CT1925 | SW | 7 | 46N | 72W | 13 |  |  | 1 | - | -
Pod 3 |  | CT1926 | NW | 19 | 46N | 72W | 13 |  |  | 1 | - | -
Jim's Water Service
Wolf Pack |  |  | NE/NW | 22 | 50N | 74W | 13 | 440587 | 4905285 | - | 3 | -
JWS Screw Site 1 |  |  | SE/SE | 16 | 50N | 74W | 13 | 439758 | 4905786 | 2 | - | -
JWS Screw Site 2 |  |  | SW/SW | 15 | 50N | 74W | 13 | 440185 | 4905760 | 2 | - | -
JWS Screw Site 3 |  |  | SE/SE | 15 | 50N | 74W | 13 | 441490 | 4905772 | 2 | - | -
JWS Screw Site 4 |  |  | SW/NE | 15 | 50N | 74W | 13 | 441036 | 4906555 | 2 | - | -
JWS Screw Site 5 |  |  | NE/SW | 14 | 50N | 74W | 13 | 442260 | 4906176 | 2 | - | -
JWS Screw Site 6 |  |  | NW/NW | 14 | 50N | 74W | 13 | 441882 | 4907035 | 2 | - | -
JWS Screw Site 7 |  |  | NW/SE | 11 | 50N | 74W | 13 | 441882 | 4907830 | 2 | - | -
True Oil
Pod 1 |  | CT1927 | NE/NE | 26 | 48N | 74W | 13 | 442935 | 4884559 | 3 | - | -
Hi Pro
Pinto |  |  | SW NW | 24 | 48N | 72W | 13 | 463702 | 4885999 | - | 2 | -
HP Screw Site 1 |  |  | NW NE | 24 | 48N | 72W | 13 | 463100 | 4885569 | 3 | - | -
HP Screw Site 2 |  |  | SE NE | 35 | 48N | 72W | 13 | 462602 | 4882355 | 3 | - | -
Prima
Prima Screw Site 1 |  |  | SE SW | 3 | 50N | 74W | 13 | 441448 | 4909010 | 2 | - | -
Prima Screw Site 2 |  |  | NW NW | 5 | 50N | 74W | 13 | 437097 | 4910208 | 2 | - | -
Penneco
House Creek |  |  | NE NE | 33 | 46N | 74W | 13 | 439609 | 4863418 | - | 4 | -
Pennaco SK Screw Site 2 |  |  | NE NW | 36 | 50N | 73W | 13 | 453460 | 4902200 | 2 | - | -
Schlautman Groves |  |  | SE SE | 10 | 45N | 74W | 13 | 441264 | 4858951 | 2 | - | -
Schlautman 10 |  |  | NW SW | 10 | 45N | 74W | 13 | 440038 | 4859411 | 4 | - | -
Schlautman 8 |  |  | NW NW | 8 | 45N | 74W | 13 | 436851 | 4860230 | 3 | - | -
Groves Ranch 14 |  |  | SE NW | 14 | 45N | 74W | 13 | 442015 | 4858161 | 4 | - | -
Groves Ranch 12 |  |  | NW SW | 12 | 45N | 74W | 13 | 443284 | 4859384 | 4 | - | -
Jordan 33 |  |  | NE NW | 33 | 46N | 74W | 13 | 438754 | 4863384 | 3 | - | -
Innes |  |  | NE NE | 26 | 46N | 75W | 13 | 442876 | 4865034 | 2 | - | -
Mcbeth 27 |  |  | NE SW | 27 | 46N | 74W | 13 | 440379 | 4864205 | 2 | - | -
Mcbeth 28 |  |  | SW NE | 28 | 46N | 74W | 13 | 439223 | 4864615 | 4 | - | -
Mcbeth 20 |  |  | SE NW | 20 | 46N | 74W | 13 | 437230 | 4866266 | 5 | - | -
Mcbeth 7 |  |  | SE NE | 7 | 46N | 74W | 13 | 436450 | 4869542 | 3 | - | -
Rassbach |  |  | NE NE | 21 | 46N | 74W | 13 | 439684 | 4866694 | 5 | - | -
Davis 36 |  |  | NE SE | 36 | 47N | 75W | 13 | 434046 | 4872550 | 4 | - | -